## All tables combined
Vi rgi n ia Dep a rt men t of
Tra nspo rt at ion
SOLICITATION FOR CONCEPTUAL
PROPOSALS
U.S. Route 460 Corridor Improvements Project
through the
Public-Private Transportation Act
May 5, 2010
TABLE OF CONTENTS
1 | EXECUTIVE SUMMARY .............................................................................................. 3
1.1 | Introduction..................................................................................................................... 3
1.2 | Purpose............................................................................................................................ 3
1.3 | Project Objectives ........................................................................................................... 4
1.4 | Document Disclosure...................................................................................................... 4
1.5 | Legislative Authority for the Project .............................................................................. 4
1.6 | Procurement Process....................................................................................................... 4
2 | BACKGROUND ............................................................................................................... 6
2.1 | Introduction..................................................................................................................... 6
2.2 | Project Information ......................................................................................................... 6
2.3 | Map of Project................................................................................................................. 6
2.4 | Progress to Date .............................................................................................................. 6
3 | PROJECT SCOPE............................................................................................................ 8
3.1 | Project Requirements ...................................................................................................... 8
| 3.1.1 | Key Assumptions ....................................................................................... 8
| 3.1.2 | Route 460 ................................................................................................... 9
| 3.1.3 | Tolling......................................................................................................... 9
3.2 | Regulatory Approvals ..................................................................................................... 9
4 | GENERAL PROCEDURES AND REQUIREMENTS............................................... 11
4.1 | Short Listing.................................................................................................................. 11
4.2 | Schedule........................................................................................................................ 11
4.3 | VDOT’s Point of Contact and Project Reference ......................................................... 11
4.4 | Advertising the SFP ...................................................................................................... 12
4.5 | SFP Information............................................................................................................ 12
4.6 | Pre-Submittal Responsibilities...................................................................................... 13
4.7 | Delivery of Proposal ..................................................................................................... 13
4.8 | Format of Proposal........................................................................................................ 14
4.9 | Formal Presentation and Interviews.............................................................................. 15
5 | QUESTIONS AND CLARIFICATIONS ..................................................................... 16
6 | RIGHTS AND OBLIGATIONS OF VDOT................................................................. 17
6.1 | Specific Rights and Obligations of VDOT ................................................................... 17
6.2 | Assumption of Liability ................................................................................................ 18
7 | COMPREHENSIVE AGREEMENT – MATERIAL TERMS .................................. 20
8 | MISCELLANEOUS ....................................................................................................... 21
8.1 | Virginia Freedom of Information Act........................................................................... 21
8.2 | Requirement to Keep Team Intact ................................................................................ 22
8.3 | Disadvantaged Business Enterprises/Small, Women and Minority Owned |  | Businesses
22
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
8.4 | Administrative Requirements ....................................................................................... 22
9 | CONFLICT OF INTEREST.......................................................................................... 25
9.1 | Conflict of Interest Determination ................................................................................ 25
9.2 | Ethics in Public Contracting Act................................................................................... 25
10 | CONTENTS OF CONCEPTUAL PROPOSAL .......................................................... 26
10.1 | Confidentiality .............................................................................................................. 26
10.2 | Letter of Submittal ........................................................................................................ 26
10.3 | Executive Summary ...................................................................................................... 27
10.4 | Conceptual Proposal Submittal Criteria........................................................................ 27
11 | EVALUATION PROCESS ............................................................................................ 33
11.1 | Evaluation Rating System............................................................................................. 33
APPENDICES
A | Definitions
B | Information Package Request Form
C | Certification Regarding Debarment
D | Work History Forms
E | Resume Form
F | Contract Term Sheet
G | Conceptual Financial Plan Pro Forma
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
3
1 | EXECUTIVE SUMMARY
1.1 | Introduction
The U.S. Route 460 Corridor Improvements Project (Project) is located from the existing
U.S. Route 460 near its Interstate-295 interchange in Prince George County to a new
| interchange |  | with | the | U.S. | Route | 58 | bypass | in | the | City | of | Suffolk. | The | Project | is
comprised of approximately 55 miles of limited access, four-lane, divided highway along
a new alignment.
| In | accordance | with | the | Public-Private |  |  | Transportation |  |  | Act | of | 1995 | (the | “PPTA”), | as
amended, the Virginia Department of Transportation (VDOT) is hereby requesting the
submittal of Conceptual Proposals for the finance, design, construction, operation, and
maintenance of the Project.
Capitalized terms used in this Solicitation for Conceptual Proposals (SFP) are defined in
Appendix A. If a term is not specifically defined in Appendix A, then such term shall
have the definition ascribed to it in this SFP or the SFP Documents.
1.2 | Purpose
The purpose of this SFP is to:
|  | inform the industry of the Project;
|  | identify VDOT’s objectives and priorities for the Project’s delivery;
|  | set out the evaluation criteria and selection process to select the short listed Offerors;
and
|  | request submittal of Statements of Qualifications including a Conceptual Financial
Plan to enable VDOT to identify Offerors qualified to submit Detailed Proposals to
finance, design, construct, operate and maintain the Project.
Offerors must demonstrate their ability to undertake the development and operations of
| the | Project | within | a | legislative, |  | contractual |  | and |  | regulatory |  | environment |  | that | will
| necessitate |  | working | effectively |  | with |  | VDOT, | other |  | Responsible |  | Public |  | Entities, | the
community and other stakeholders.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
4
1.3 | Project Objectives
VDOT is procuring this Project under the provisions of the PPTA to secure private sector
funds and offset the need for public allocations to fund the Work. A successful project
shall satisfy the following transportation objectives:
|  | Improve travel safety along the corridor;
|  | Create at new westbound emergency evacuation route for Hampton Roads;
|  | Accommodate increases in freight movements along the corridor; and
|  | Improve military strategic connectivity.
1.4 | Document Disclosure
| VDOT | shall | disclose | to | the | public, |  | in | accordance |  | with | the | Virginia | Freedom | of
Information Act, all information received in response to this SFP including any proposed
product, service, or idea for the Project that enhances or augments VDOT’s minimum
| requirements and/or project objectives, unless determined by VDOT to be exempt | [13 empty] | in
| accordance with Section 8.1 of this SFP. | [6 empty] | Noting VDOT’s intent to disclose, Offerors are
expected to submit Conceptual Proposals with no requests or very limited requests for
exceptions to disclosure.
1.5 | Legislative Authority for the Project
The PPTA is the legislative framework enabling the Commonwealth of Virginia (the
“Commonwealth”) to enter into agreements authorizing private entities to develop and/or
| operate | qualifying |  | transportation |  |  | facilities. |  |  | The | Commonwealth |  | of | Virginia | adopted
| Implementation |  | Guidelines |  | (Guidelines) |  |  | in |  | accordance | with | the | PPTA. | The | current
| Guidelines |  | were | revised |  | as | of | December |  |  | 2008 | and | are | available | at
http://www.virginiadot.org/business/ppta-Guidelines.asp. In accordance with § 56-556 et
seq. of the Code of Virginia, VDOT shall be the coordinating Responsible Public Entity
for the Project.
VDOT previously solicited conceptual proposals for this Project on February 15, 2006.
| VDOT | received | three | responses |  |  | to | that | earlier |  | solicitation. | VDOT |  | terminated | that
solicitation process on May 3, 2010.
1.6 | Procurement Process
| This | SFP | commences | the | first-phase |  |  | of | a | procurement | process. |  | The | following | is | a
summary of VDOT’s standard six-phase PPTA procurement process, which is defined in
detail in the Guidelines:
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
5
1. | Phase | One |  | – |  | Quality |  | Control: |  | a | VDOT | level |  | review | to | determine |  | whether
| Conceptual |  |  | Proposals |  |  | meet |  | the | requirements |  |  | of | the | Law | and | the | Guidelines.
| Please |  | refer |  |  | to | VDOT’s |  | IPD |  | Memorandum |  |  | IPD |  | 05-02 | available |  | at
http://www.virginiadot.org/business/resources/IPD_Memorandum_05_02_0_dlh_
051206.pdf.
2. | Phase Two - Independent Review Panel (IRP): The IRP, which is appointed by
| the | Secretary |  |  |  | of | Transportation, |  |  |  | will | review | and |  | evaluate |  | the | Conceptual
Proposal(s) and provide a recommendation as to whether to advance one or more
of the Conceptual Proposal(s).
3. | Phase Three – Commonwealth Transportation Board (CTB) Approval: The CTB
will review the Conceptual Proposal(s), along with the IRP’s recommendation
and recommend that VDOT either reject the Conceptual Proposal(s) or seek a
Detailed Proposal from one or more of the Offerors.
4. | Phase Four – Submission and Selection of Detailed Proposals: Offerors advancing
| to | Phase | Four |  |  | will | be | requested |  | to | submit | Detailed |  |  | Proposals. |  | VDOT |  | shall
evaluate the Detailed Proposals and select none, one or more proposals by the
Commonwealth Transportation Commissioner for negotiation of an interim and/or
a comprehensive agreement.
5. | Phase | Five |  |  | – | Negotiation |  |  | of | interim | and/or |  | comprehensive |  |  |  | agreement: |  | The
| process |  | of |  | completing |  |  | negotiations |  |  | of | an | interim |  | and/or |  | comprehensive
agreement.
6. | Phase | Six |  | – | Execution |  |  | of | interim |  | and/or | comprehensive |  |  | agreement: |  |  | The | final
stage of review and includes the execution of an interim and/or comprehensive
agreement by the Commonwealth Transportation Commissioner and the selected
Offeror.
VDOT | will | issue |  | a | draft |  | Request |  | for | Detailed |  | Proposals |  | (RFDP) |  | to | the | short | listed
Offerors. |  | Prior to issuing a final RFDP, VDOT will host meetings with the short listed
Offerors with the intent of allowing further development of concepts and issues raised
during the preceding phases of the PPTA procurement process.
The Commonwealth Transportation Commissioner may decide to streamline this process
because | earlier |  | activities |  |  |  | have | included |  |  | substantial |  | public |  | information |  |  | and | public
involvement, including an Independent Review Panel.
While the RFDP will contain specific requirements for Detailed Proposals, as well as a
specific selection criteria process, VDOT anticipates that Detailed Proposals will include,
among other things, requirements for conceptual design plans, a financial plan, a tolling
schedule, |  | and | a | schedule |  |  | for | development, |  |  |  | construction, |  |  | and | implementation |  |  | of
operations and maintenance for the duration of the concession period. | [16 empty] | Based on the
responses to the RFDP, the Commonwealth Transportation Commissioner will make a
selection of a successful Offeror(s), if any, to initiate negotiations for an interim and/or
comprehensive agreement to finance, design, construct, operate and maintain the Project.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
6
2 | BACKGROUND
2.1 | Introduction
| The | Project | contemplated |  | in | this | SFP | includes | the | construction |  | of | a | new | west-east
transportation link between the existing U.S. Route 460 near its interchange with I-295 in
| Prince | George | County | to | a | new | interchange |  | with | U.S. | Route | 58 | along | the | Suffolk
| Bypass. | The Project includes only minor adjustments to the existing I-295 interchange.
The adjustments to this interchange are minor realignments of two existing ramps, the
westbound U.S. Route 460 to I-295 northbound ramp and the northbound I-295 ramp to
| eastbound | U.S. | Route | 460. |  | The | Project | area | extends |  | approximately |  |  | 55 | miles | and
includes a four-lane divided, limited access highway along a new location.
The proposed improvements will include, among other things, new roadway, drainage,
| communications/intelligent |  |  |  | transportation |  |  | systems, | lighting, |  | flood | protection, |  |  | and | toll
collection facilities.
2.2 | Project Information
VDOT has developed information that may assist Offerors as they develop Conceptual
| Proposals. | Information |  | is |  | available |  | on | VDOT’s | external |  | project |  | website |  | at
| http://route460ppta.org/. |  |  | Additional information is available through the purchase of CD.
Instructions for purchase of the information package are included in Section 4.5.
2.3 | Map of Project
Several illustrations of the Project are included on the external project website at
http://route460ppta.org/.
2.4 | Progress to Date
An overview of the work undertaken by VDOT on the Project to date is briefly described
| below. | Note that all completed studies, reports, and documents referenced below are
provided on VDOT’s external project website at http://route460ppta.org/ or included in
the Information Package.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
7
Environmental Studies
2005 | VDOT | completed |  |  | its | Draft | Environmental | Impact | Statement |  | (DEIS) |  | and
associated technical reports.
2008 | VDOT completed additional hazardous materials investigations (Phase I and
Phase II Environmental Site Assessments) (Information Package)
2008 | VDOT | completed |  |  | additional |  | cultural | resource | investigations |  | (Information
Package)
2008 | Final Environmental Impact Statement (FEIS) approved by FHWA
2008 | FHWA Issued the Record of Decision.
Geotechnical Studies
2008 | VDOT | completed |  | additional |  |  | geotechnical | borings | along | the | corridor | and | at
| locations anticipated for major structures. | [6 empty] | This information is included in the
Geotechnical Engineering Data Report. (Information Package)
Data from other projects in the vicinity of the Project has been identified and is
included on the Project website at
http://www.virginiadot.org/ppta_projects/route_460/geotechnical_documents.a
sp
Preliminary Engineering
2008 | VDOT | has |  | developed |  | a | Preliminary | Reference | Design | for | the | corridor.
(Information Package)
Procurement
2006 | In compliance with the legislative requirement identified in Section 1.5, VDOT
| initiated a PPTA procurement of the Project. | [6 empty] | VDOT cancelled the procurement
| on | May | 3, | 2010. | Additional |  | Project | information | related |  | to | the | prior
procurement is available on the Project website at http://route460ppta.org/.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
8
3 | PROJECT SCOPE
The scope includes the development and operation of the proposed Project. The Offeror’s
Conceptual Proposal shall take into consideration the Project objectives and requirements
| listed | herein. |  |  | Short | listed |  | Offerors | that | are | advanced | to | Phase | Four | may | undertake
| further |  | investigations |  |  |  | and | develop |  | Detailed | Proposals |  | in | accordance |  | with | the
environmental, technical, and functional requirements that will be issued at the RFDP
stage.
3.1 | Project Requirements
The Project shall be developed and operated in accordance with applicable Regulatory
Approvals and Laws, AASHTO standards and industry best practices.
3.1.1 | Key Assumptions
| Offerors |  | shall |  | use | the | following |  | key | assumptions | in | developing |  | their | approaches |  | to
financing, designing, constructing, operating, and maintaining the Project:
• | Hurricane |  |  | evacuation |  |  | capabilities |  | and | improving | military |  | strategic |  | connectivity |  | are
| priorities |  |  | of | the | project | and | the | public. | The | Governor | will | consider |  | waiving |  | certain
statutory mandates and regulations in order to facilitate the development of the Project, if
| a | part | of | his | emergency |  | preparedness |  |  | plan, in accordance |  |  | with | the | Code | of | Virginia
§33.1-223.2:5.
• | The Commonwealth will support the Concessionaire’s innovative ideas to increase truck
traffic in the corridor, including truck traffic to and from the Port of Virginia.
• | VDOT will accept a phased approach to develop the Project and a minimum scope of
work for the first phase (e.g., the first phase may include only one interchange at each
terminus, with future interchanges or phases constructed as funding becomes available).
• | The Concessionaire shall complete right of way (ROW) acquisition at its sole cost and
| expense in accordance with all applicable Regulatory Approvals and Laws. | [14 empty] | VDOT will
handle condemnation proceedings, should the need arise.
• | There is no state or federal funding planned or programmed for this Project.
• | VDOT welcomes proposals for innovative financing alternatives.
• | VDOT will perform only minimal construction oversight and will rely primarily on the
| Concessionaire’s |  |  |  |  | quality | assurance/quality |  |  | control | work | and | on | the | Concessionaire’s
certifications that the work complies with contract requirements. The Concessionaire will
be responsible for VDOT’s construction oversight costs, estimated at two (2) percent of
the design and construction costs.
• | Offerors |  | may |  | propose |  | more | efficient |  | operating conditions |  |  | than | currently | provided by
state Law, subject to compliance with all applicable design standards and safety factors.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
9
• | The | Comprehensive |  |  | Agreement |  |  | will | include |  | provisions |  | to | address |  | a | number | of
commercial issues, including but not limited to the following:
|  | 1. | a concession term of up to 75 years, with the potential to extend the term up to a
maximum of 99 years;
|  | 2. | support for the development of commercial facilities determined to be essential
for the transportation of persons or goods, together with any buildings, structures,
parking areas, appurtenances, and other property needed to operate such facility in
accordance with the Code of Virginia Section 56-557 and applicable Law; and
|  | 3. | funding for compensation events shall be limited as set forth in the term sheet.
• | The | Comprehensive |  |  | Agreement |  |  | will | include | an | enforceable |  |  | goal | for | Disadvantaged
| Business |  | Enterprise |  | (DBE) | and |  | the | Commonwealth’s |  |  | Small, |  | Women, |  | and | Minorities
(SWAM) participation in the Project.
3.1.2 | Route 460
The following requirements shall be implemented on the proposed Project:
|  | Provide | for | 4-lane |  | divided |  | roadway | built |  | to | AASHTO |  | interstate |  | standards |  | and
|  | designed | with |  | sufficient | vertical |  |  | elevation |  | and | clearance | to | enable |  | safe | operation
during a 100-year flood event;
|  | Provide a system for reversing eastbound traffic flow to accommodate westbound
travel on all lanes for hurricane and emergency evacuation; and
|  | Acquire | sufficient |  |  | ROW | to | enable | future |  | expansion | of | phased |  | interchanges |  |  | and
widening from a 4-lane to 6-lane roadway, subject to availability of funding.
3.1.3 | Tolling
| Any | new | roadway |  | on | which | a | toll | would | be | implemented |  | must |  | be | capable | of | fully
electronic toll collection techniques and technologies and employ Open Road Tolling for
| the Project’s main lines. |  |  |  |  | Traditional toll collection systems may be an option for initial
| operations, |  | in | conjunction |  | with |  | open-road |  | tolling. |  | Electronic |  | toll | equipment |  | shall | be
compatible with E-Z Pass or any successor network and VDOT’s existing electronic toll
| collection system. |  |  |  | Offerors may have the option of contracting with VDOT’s Violation
Enforcement and Electronic Toll Collection services.
3.2 | Regulatory Approvals
Offerors shall be responsible for the implementation of all National Environmental Policy
| Act | of | 1969 | (NEPA) |  | commitments |  |  | and | restrictions. |  | The | Project |  | is | subject | to | all
applicable Regulatory Approval and Laws, to include but not limited to the requirements
of the NEPA.
| Offerors |  | shall | be | required | to |  | obtain | all | necessary |  | remaining |  | regulatory |  |  | clearances
| required to accomplish the Project. | [7 empty] | The Offeror shall be responsible for obtaining and
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
10
coordinating any necessary water quality permits and any modifications of water quality
permits.
If VDOT approves any deviations or change in scope or design proposed by the Offeror,
Offeror shall be responsible for providing VDOT with environmental data in support of
any | re-evaluation | of | the | NEPA | document | that | is | necessary | due | to | such | proposed
deviation or change in scope or design. |  |  |  |  | The Offeror shall reimburse VDOT for its costs
in the preparation of any additionally required environmental documents.
Conceptual Proposals shall be consistent with the environmental documents.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
11
4 | GENERAL PROCEDURES AND REQUIREMENTS
4.1 | Short Listing
The Conceptual Proposals received in response to this SFP will be used to short list the
most qualified Offerors who will be invited to submit Detailed Proposals. It is anticipated
| that | no | more | than | three | (3) | Offerors | will | be | short-listed. |  |  | Evaluation |  | of | Detailed
Proposals may lead to final selection of one or more Offerors with whom VDOT may
enter into an interim and/or comprehensive agreement to obtain the right and obligation
to finance, design, construct, operate, and maintain the Project.
4.2 | Schedule
VDOT currently anticipates conducting the procurement of the Project in accordance
| with | the | following |  | list | of | milestones | leading |  | to | an | interim |  | and/or | comprehensive
| agreement. |  | This schedule is subject to revision and VDOT reserves the right to modify
this schedule as it finds necessary, in its sole discretion.
|  | Procurement Phase | [11 empty] | Date
| 1. | SFP Document Available to Offerors | [9 empty] | 05/05/10
| 2. | Deadline for Questions or Clarifications | [9 empty] | 06/21/10
| 3. | Conceptual Proposal Submission Deadline | [9 empty] | 08/05/10 (4:00 PM prevailing local time)
| 4. | Quality Control Report Submitted to Secretary | [9 empty] | 08/20/10
| 5. | Secretary Appoints Independent Review Panel | [9 empty] | 09/15/10
| 6. | Local Comments Due | [9 empty] | 10/20/10
| 7. | Independent Review Panel Recommendation | [9 empty] | 11/03/10
| 8. | CTB Resolution | [9 empty] | 11/17/10
| 9. | Request for Detailed Proposals (if applicable) | [9 empty] | 12/20/10
| 10. Detailed Proposal Submission Deadline (if applicable) | [10 empty] | 05/15/11 (4:00 PM prevailing local time)
| 11. Interim and/or Comprehensive Agreement (if applicable) | [10 empty] | 09/15/11
4.3 | VDOT’s Point of Contact and Project Reference
| VDOT’s |  | sole | Point | of | Contact | (POC) | for | the | Project |  | shall | be | the | person | designated
| below. |  | VDOT’s POC is the only individual authorized to discuss this SFP with any
| interested parties, including Offerors. | [5 empty] | All communications with VDOT’s POC shall be in
| writing, as required by the applicable provisions of this SFP. | [11 empty] | Offerors may not rely on
oral responses to any inquiries.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
12
VDOT’s POC is:
| Name: |  | Margie Ray
| Title: |  | Program Manager
| Address: |  | Innovative Project Delivery Division
Virginia Department of Transportation
1401 East Broad Street
|  |  | Richmond, VA |  | 23219
| Phone: |  | (804) 786-9537
| Fax: |  | (804) 786-7221
| E-Mail: |  | margit.ray@VDOT.Virginia.gov
4.3.1 | VDOT | disclaims |  | the | accuracy | of | information |  | derived |  | from | any | source | other | than
VDOT’s POC and the use of any such information is at the sole risk of the Offerors.
4.3.2 | All written communications to VDOT from the Offerors shall specifically reference the
| correspondence |  | as | being | associated |  | with | the | “Route |  | 460 | Corridor | Improvements
Project”.
4.4 | Advertising the SFP
The SFP shall be advertised on VDOT’s website at http://route460ppta.org/, and on eVA,
| Virginia’s electronic procurement website (www.eva.state.va.us). | [10 empty] | The SFP shall also be
advertised in major regional newspapers in accordance with Innovative Project Delivery
(IPD) Division Memorandum IPD 05-01.0, available for review at
http://www.virginiadot.org/business/resources/IPD_Memorandum_05_01_0_dlh_050930
.pdf.
| Addenda to the SFP will only be posted on the VDOT website above. | [11 empty] | Offerors should
monitor the VDOT website for the posting of any addenda to this SFP.
4.5 | SFP Information
Additional information regarding the Project may be downloaded from VDOT’s website
| at | http://route460ppta.org/. |  |  | An | information |  | package |  |  | which | includes: | preliminary
| reference | design, |  | typical | sections, |  | environmental |  |  | studies, | geotechnical |  | investigation
| reports, | and | other | project | information, |  | is | available |  | to | interested | Offerors |  | on | CD | for
| $50.00. | Interested |  | Offerors | should |  | completed |  | the | Information |  | Package | Order |  | Form
| included as Appendix B. |  |  |  | The instructions for submittal and payment are included on the
form.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
13
4.6 | Pre-Submittal Responsibilities
Each Offeror shall be solely responsible for examining the SFP, including any addenda,
and any and all conditions which may in any way affect their proposal or the performance
of the Work on the Project, including but not limited, to the following responsibilities:
4.6.1 | Examining and carefully studying the SFP, including any addenda and other information
or data identified in the SFP.
4.6.2 | Visiting | the | Project |  | area | and | becoming |  | familiar |  | with | and | satisfying | itself | as | to | the
general, local, and site conditions that may affect the cost, progress, or performance of its
Work on the Project.
4.6.3 | Becoming familiar with and satisfying itself as to Regulatory Approvals and Laws that
may affect the cost, progress, or performance of its Work on the Project.
4.6.4 | Determining that the SFP and any addenda thereto are sufficient to indicate and convey
understanding of all terms and conditions for the performance of Offeror’s Work on the
Project.
4.6.5 | Providing prompt written notice of all conflicts, errors, ambiguities, or discrepancies that
the Offeror discovers in the SFP and addenda, and any aspects of the SFP and addenda
| that the Offerors do not understand. | [6 empty] | Any failure to do so shall be at Offeror’s sole risk,
and no relief for error or omission will be provided by VDOT.
4.7 | Delivery of Proposal
| Conceptual |  | Proposals |  | are | to | be | sealed | in | mailing | envelopes |  | or | packages | bearing |  | the
| Offeror’s | name, | address |  |  | and | the | words |  | “Route | 460 | Corridor |  | Improvements | Project
| PPTA” clearly written on the outside. | [6 empty] | All Conceptual Proposals must be received by the
| date and time as designated in Section 4.2. | [8 empty] | Conceptual Proposals must be delivered to
| the | VDOT | POC | as | designated |  |  | below. |  | Neither | fax | nor | email | submissions | will |  | be
| accepted. | Hand delivered responses to the SFP must be received by the date and time as
designated in Section 4.2, and must be delivered to:
Mrs. Brenda Williams
Administrative Services Division
Virginia Department of Transportation
1 st Floor Reception Desk
|  |  | 1201 E. |  | Broad Street
|  |  | Richmond, VA |  |  |  | 23219
Offerors are responsible for effecting delivery by the deadline above and late submissions
will be rejected without consideration or evaluation, and will be returned unopened to the
| sender. | VDOT accepts no responsibility for misdirected or lost Conceptual Proposals.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
14
4.7.1 | The Conceptual Proposals should be as clear and concise as possible in accordance with
the requirements of this SFP, so that a proper evaluation can be made of the Offeror’s
capabilities and intent to complete the proposed Project.
4.7.2 | Offerors | submitting |  |  | Conceptual |  | Proposals |  | to | VDOT | are | required | to | deliver | ten | (10)
| identical | hard |  | copies, | one | (1) | of | which | must | bear | original | signatures |  | and | one | (1)
electronic copy (a “.pdf” file in the most current version of Adobe Acrobat), of their
| Conceptual Proposal for all Volumes on CD-ROM. | [8 empty] | Offerors passing VDOT’s Quality
Control review will be required to submit additional hard copies at VDOT’s request.
4.8 | Format of Proposal
Conceptual Proposals shall follow the format prescribed in this section and the current
| version of the Guidelines as referenced herein. | [8 empty] | Submittals that do not follow the format
prescribed below may be considered non-responsive and may be eliminated from further
consideration.
4.8.1 | Conceptual |  | Proposals |  | should |  | be | prepared | simply |  | and | economically, |  | providing |  | a
straightforward, concise description of the Offeror’s capabilities to complete the Project.
Emphasis should be on completeness and clarity.
4.8.2 | All pages of the Conceptual Proposal shall be numbered in the lower right hand corner.
| Offerors | shall |  | use | cross | referencing |  | rather | than | repetition |  | throughout |  | the | Conceptual
| Proposal. | The Conceptual Proposal shall contain a table of contents which shall follow
the format described herein.
4.8.3 | Conceptual |  | Proposals |  | shall | be | placed | in | a | three-ring |  | binder. | All | documentation
| submitted with the Conceptual Proposal shall be contained in two volumes: | [13 empty] | Volume I
shall contain all of the material requested in Section 4.8.4, with the exception of the
financial commitments and reports, and Volume II shall contain financial statements and
reports. Conceptual Proposals shall also meet the following requirements:
|  | Consist of no more than 50 pages (VDOT will remove and discard all pages in excess
|  | of the stipulated page limit). |  |  |  |  | The following items shall not be counted against the
|  | page limit: |  | Letter of Submittal; Executive Summary; tabs; Certification Regarding
Debarment Forms, Appendix C; financial statements and reports requested in Section
10.4.1.1 and contained in Volume II; Work History Forms, Appendix D; Resume
Forms, Appendix E; and Conceptual Financial Plan Pro Forma, Appendix G;
|  | Except | for | charts, | exhibits, |  | and | other | illustrative |  | and | graphical |  | information, |  | all
information shall be prepared on 8.5”X 11” white paper. Charts, schedules, exhibits
and other illustrative and graphical information may be on 11” x 17” paper, but must
be folded to 8.5” X 11”;
|  | Typed on one (1) side only; and
|  | Separated by numbered tabs with sections corresponding to the order set forth in
|  | Section 4.8.4. |  |  | Tabs should not contain Project-specific information, or they will
count against the page limit.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
15
|  | All | printing, | except | for | the | front | cover | of | the | Conceptual |  | Proposal | and |  | any
appendices, must be:
|  | o | Times New Roman, with a font of 12-point; and
|  | o | Offeror may use Times New Roman 10 point font for filling out information on
the Work History Forms, Appendix D and the Resume Forms, Appendix E.
4.8.4 | Each Conceptual Proposal shall be organized as follows:
|  | 1. | Letter of Submittal (maximum Four Pages)
|  | 2. | Executive Summary (maximum Five Pages)
|  | 3. | Table of Contents
|  | 4. | Responses to Conceptual Proposal Evaluation Criteria:
|  |  | Section 10.4.1: |  | Qualifications Criteria
.1 Financial Capacity
.2 Project Finance Experience
.3 Design, Construction, Maintenance and Operations
.4 Toll Facility Operations
.5 Conceptual Financial Plan
4.9 | Formal Presentation and Interviews
Offerors may be required to give oral presentations of their Conceptual Proposal to an
| IRP | and/or | the | public. | The | format |  | of | these | presentations |  | may | include | a | formal
| presentation |  | by | Offerors, | followed |  | by |  | questions | from | the | IRP | pertaining |  | to | the
Conceptual Proposals or the presentations. The IRP may also ask Offerors to address
| concerns expressed through the public comment process. | [9 empty] | Such presentations will provide
| opportunities to inform VDOT and the public and/or clarify aspects of the Project. | [14 empty] | The
| presentations |  | will | also | allow | the | IRP | to | seek | clarification | of | Project | elements, |  |  | the
Conceptual Proposal’s response to the Project objectives and needs, complete deliverable
| requirements |  | and | provide | Offerors |  | with |  | the | opportunity | to | further | explain |  | their
| Conceptual Proposal. |  |  | If there is an issue to which the Offerors are unable to respond
during the formal presentation, the IRP may, at their discretion, grant the Offerors a
reasonable period of time in which to submit a written response.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
16
5 | QUESTIONS AND CLARIFICATIONS
| All | questions |  | and | requests | for | clarification |  | regarding |  | this | SFP | shall | be | submitted |  | in
| writing |  | to | VDOT’s | POC | designated |  | in | Section |  | 4.3. | No | requests | for | additional
information, clarification or any other communication should be directed to any other
| individual. |  |  | VDOT’s | responses |  | to | questions |  | or | requests | for | clarification |  | shall | be | in
| writing and may be accomplished by an addendum to this SFP. | [11 empty] | VDOT will not be bound
by any oral communications, or written interpretations or clarifications that are not set
| forth | in | an | addendum. |  | VDOT, | at | its | sole | discretion, |  | shall | have | the | right | to | seek
| clarifications |  |  | from | any | Offeror | to | fully | understand |  |  | information |  | contained |  | in | the
| Conceptual Proposal. |  |  |  | All questions submitted by the Offerors shall be published on the
VDOT website, in the form in which they were received.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
17
6 | RIGHTS AND OBLIGATIONS OF VDOT
In connection with this procurement, VDOT reserves to itself all rights (which rights
shall be exercisable by VDOT in its sole discretion) available to it under applicable Law.
6.1 | Specific Rights and Obligations of VDOT
In addition to all rights reserved as specified by Law, VDOT further reserves to itself,
without limitation or with or without cause and with or without notice, the following:
6.1.1 | The right to cancel, withdraw, postpone or extend this SFP in whole or in part at any time
prior to the execution by VDOT of an interim and/or comprehensive agreement, without
incurring any obligations or liabilities.
6.1.2 | The right to issue a new SFP.
6.1.3 | The right to reject any and all submittals, responses and proposals received at any time.
6.1.4 | The right to modify all dates set or projected in this SFP.
6.1.5 | The right to terminate evaluations of responses received at any time.
6.1.6 | The right to suspend and terminate the procurement process for the Project at any time.
6.1.7 | The right to revise and modify, at any time prior to the proposal submittal date, factors it
will consider in evaluating responses to this SFP and to otherwise revise its evaluation
methodology.
6.1.8 | The right to waive or permit corrections to data submitted with any response to this SFP
until such time as VDOT declares in writing that a particular stage or phase of its review
of the responses to this SFP has been completed and closed.
6.1.9 | The right to issue addenda, supplements, and modifications to this SFP.
6.1.10 | The right to permit submittal of addenda and supplements to data previously provided
| with | any | response | to | this | SFP | until | such | time | as | VDOT | declares | in | writing | that | a
particular stage or phase of its review of the responses to this SFP has been completed
and closed.
6.1.11 | The right to hold meetings and conduct discussions and correspondence with one or more
of the Offerors responding to this SFP to seek an improved understanding and evaluation
of the responses to this SFP.
6.1.12 | The right to seek or obtain data from any source that has the potential to improve the
understanding and evaluation of the responses to the SFP, including the right to seek
clarifications from Offerors.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
18
6.1.13 | The right to permit Offerors to add or delete firms and/or key personnel.
6.1.14 | The right to add or delete the Offeror’s responsibilities from the information contained in
this SFP.
6.1.15 | The right to appoint and change appointees of the Independent Review Panel.
6.1.16 | The | right | to | use | assistance | of | outside | technical, |  |  | financial, | and | legal |  | experts | and
Consultants in the evaluation process.
6.1.17 | The right to waive deficiencies, informalities and irregularities in a proposal, accept and
review a non-conforming proposal or seek clarifications or supplements to a proposal.
6.1.18 | The right to disqualify any Offeror that changes its submittal without VDOT approval.
6.1.19 | The right to respond to all, some, or none of the inquiries, questions and/or request for
clarifications received relative to the SFP.
6.1.20 | The right to use all or part of an unsuccessful Conceptual Proposal if the Offeror of said
proposal accepts a payment, if applicable.
6.1.21 | The | right | to | suspend, | discontinue |  | and/or |  | terminate |  | interim |  | and/or | comprehensive
| agreement |  | negotiations |  | with | any | Offeror | at | any | time | prior | to | the | actual | authorized
execution of such agreement by all parties, subject to appropriate documentation.
6.1.22 | The | right | to | negotiate | with | an | Offeror | without |  | being | bound | by | any | provision | in | the
proposal.
6.1.23 | The right to enter into one or more interim and/or comprehensive agreements with one or
| more | Offerors, |  | as | permitted | by | the | PPTA, | in | furtherance |  | of | the | development |  | and
operation of the Project or any of its components, or to modify or abandon procurement
of the Project.
6.1.24 | The right to request revisions to the Conceptual Proposal.
6.1.25 | The right to short list from among the highest rated Offerors, and to provide an RFDP
| only to those short listed Offerors. | [5 empty] | VDOT anticipates short listing no more than three (3)
| highest | rated |  | Offerors. | VDOT |  | may | increase | or | decrease | the | number |  | of | short | listed
Offerors, if it is in the best interest of VDOT to do so.
6.2 | Assumption of Liability
| VDOT | assumes |  | no | obligations, |  | responsibilities, |  |  | and | liabilities, |  | fiscal | or | otherwise, | to
reimburse all or part of the costs incurred or alleged to have been incurred by parties
| considering a response to and/or responding to this SFP. | [9 empty] | All such costs shall be borne
solely by each Offeror and its team members.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
19
6.2.1 | In no event shall VDOT be bound by, or be liable for, any obligations with respect to the
Project until such time (if at all) an interim and/or comprehensive agreement, in form and
substance satisfactory to VDOT, has been executed and authorized by VDOT and, then,
only to the extent set forth therein.
6.2.2 | Any and all information made available to the Offerors is made for convenience purposes
only and is without representation or warranty of any kind.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
20
7 | COMPREHENSIVE AGREEMENT – MATERIAL TERMS
VDOT issues this SFP, inclusive of all appendices and addenda (collectively the “SFP
Documents”) as a preliminary step in the PPTA procurement process, which, if carried
| through | to | the | conclusion, |  | will | result | in | VDOT | entering |  | into | an | interim | and/or
| comprehensive |  |  | agreement | with | the | successful |  | Offeror, | who |  | will | obtain | the | right | and
| obligation to finance, design, construct, operate and maintain the Project. | [12 empty] | Several terms
of the interim and/or comprehensive agreement, which VDOT proposes to execute for the
| Project are included as Appendix F. | [5 empty] | Additionally, a draft comprehensive agreement, will
be included with the RFDP. The RFDP will, among other things, detail the technical
requirements for the design, construction, maintenance and operations components of the
| Project; | the | scope | of | the | services | to | be | provided | by | the | successful |  | Offeror; |  | and
commercial terms.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
21
8 | MISCELLANEOUS
8.1 | Virginia Freedom of Information Act
8.1.1 | All proposals submitted to VDOT are subject to the disclosure requirements of the PPTA,
Section 2.2-4342 of the Virginia Public Procurement Act, and the Virginia Freedom of
| Information Act (VFOIA) (Section 2.2--3700 et seq.). | [6 empty] | Offerors are advised to familiarize
themselves with the provisions of each Act referenced herein to ensure that documents
| identified as confidential will not be subject to disclosure under VFOIA. | [9 empty] | In no event
shall the Commonwealth, the Commonwealth Transportation Commissioner, or VDOT
be liable to an Offeror for the disclosure of all or a portion of a Conceptual Proposal
submitted pursuant to this request.
8.1.2 | If a responding Offeror has special concerns about information which it desires to make
| available | to | VDOT | but | which | it | believes | constitutes | a | trade | secret, | proprietary
| information, |  | or | other | confidential |  | information | exempted |  | from | disclosure, | such
responding Offeror should specifically and conspicuously designate that information as
such in its proposal and state in writing why protection of that information is needed.
| The Offeror should make a written request to VDOT’s POC. | [7 empty] | The written request shall:
| 1. | Invoke such exemption upon the submission of the materials for which protection
is sought;
| 2. | Identify specifically and conspicuously the data or other materials for which the
protection is sought;
| 3. | State the reasons why protection is necessary; and
| 4. | Indicate that a similar process with the appropriate officials of the affected local
|  | jurisdictions has or will be conducted. | [5 empty] | Failure to take such precautions prior to
submission of a proposal may subject confidential information to disclosure under
the VFOIA.
8.1.3 | Blanket designations that do not identify the specific information shall not be acceptable
| and may be cause for VDOT to treat the entire proposal as public information. | [10 empty] | Nothing
contained in this provision shall modify or amend requirements and obligations imposed
on VDOT by applicable Law, and the applicable Law(s) shall control in the event of a
conflict between the procedures described above and any applicable Law(s).
8.1.4 | In the event that VDOT receives a request for public disclosure of a portion of a proposal,
VDOT will determine whether or not the requested materials are exempt from disclosure.
In the event that VDOT elects to disclose the requested materials, it will endeavor to
provide notice to the Offeror of its intent to disclose.
8.1.5 | Offerors are on notice that VDOT will post on its webpage all responsive Conceptual
Proposals and other relevant information and agreements, in accordance with applicable
Regulatory Approvals and Laws.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
22
8.1.6 | Offerors are advised that portions of the Project documents may be considered Critical
| Infrastructure |  |  | Information/Sensitive | [5 empty] | Security |  |  | Information |  | (CII/SSI) |  |  | and | any | VFOIA
requests for such documents will be processed in accordance with the Code of Virginia
Section 2.2-3705.2.
8.2 | Requirement to Keep Team Intact
| The | Key | Personnel |  |  | proposed |  |  | by | the | Offeror |  | shall | remain |  | on | Offeror’s |  | team | for | the
duration of the procurement process and, if the Offeror is selected and enters into an
interim and/or a comprehensive agreement, the requirement will be as more specifically
| defined in the comprehensive agreement. | [10 empty] | If circumstances require a proposed change, it
| must | be | submitted |  |  | in | writing |  | to | VDOT’s |  |  | POC. | VDOT |  | will | determine |  | whether |  | to
| authorize |  | a | change, |  |  | which |  | authorization |  |  |  | will | not | be | unreasonably |  |  | withheld.
Unauthorized changes to the Offeror’s Key Personnel at any time during the procurement
process may result in the elimination of the Offeror from further consideration.
8.3 | Disadvantaged |  |  |  | Business |  |  | Enterprises/Small, | [5 empty] | Women |  | and |  | Minority |  | Owned
Businesses
| The | participation |  |  | goals |  | for | this |  | Project |  | will | be | set | forth | in | the | RFDP, | wherein |  | a
| commitment |  |  | will | be |  | required |  | from |  | Offerors |  | to | achieve | the |  | goals. | Offerors |  |  | shall
| anticipate |  | compliance |  |  |  | with | relevant |  |  | Federal |  | and | State | DBE/SWAM |  |  |  | policies |  | and
regulations.
8.4 | Administrative Requirements
In addition to the specific submittal requirements set forth elsewhere in this SFP, all
Offerors shall comply with the following:
8.4.1 | Prior | to | the | execution |  |  | of | an | interim |  | and/or |  | comprehensive |  |  | agreement, |  |  | all | business
entities, except for sole proprietorships, are required to be registered with the Virginia
State Corporation Commission (a Business Registration Guide is available on the Internet
| at | http://www.state.va.us/scc/division/clk/brg.htm). | [11 empty] | Foreign |  | Professional |  |  | Corporations
and Foreign Professional Limited Liability Companies must possess a Commonwealth of
| Virginia |  | Certificate |  |  | of | Authority |  |  | from |  | the | State | Corporation |  |  | Commission |  | to | render
professional services.
| All | Offerors |  | and | Submittals |  |  | must |  | at | the | time | of | their | Conceptual |  |  | Proposal | submittal
comply with the law and nothing herein is intended to contradict, nor supersede, any
| applicable Regulatory Approvals and Laws. | [11 empty] | All Offerors shall be eligible at the time of
their Conceptual Proposal submittal, under the law and relevant regulations, to offer and
| to provide all services proposed and related to the Project. | [13 empty] | Unless exempted by §§ 54.1-
| 401, | 54.1-402, |  |  | or | 54.1-402.1 |  |  | of | the |  | Code | of | Virginia, |  | any | person, |  | partnership,
| corporation, |  |  | or | other |  | entity | offering |  |  | or | practicing |  | architecture, |  |  | engineering, |  |  | or | land
| surveying shall be registered or licensed in accordance with the provision of | [17 empty] | Chapter 4,
Title 54.1 of the Code of Virginia. Offerors shall satisfy, at the time of their Conceptual
Proposal submittal, all commercial and professional registration requirements, including,
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
23
| but | not | limited | to | the | requirements |  | of | the | State |  | Corporation | Commission |  | and | the
Department of Professional and Occupational Regulations.
8.4.2 | VDOT will not consider for award any proposals submitted by any Offerors and will not
consent to subcontracting any portions of the proposed contract to any subconsultants in
violation of the provisions of the Federal Immigration Reform and Control Act of 1986,
which prohibits employment of illegal aliens.
8.4.3 | Prior to the execution of an interim and/or comprehensive agreement all Offerors must
have internal control systems in place that meet federal requirements for accounting.
| These | systems |  | must |  | comply | with | requirements |  |  | of | 48CFR31, | “Federal | Acquisition
Regulations, Contract Cost Principals and Procedures,” and 23CFR172, “Administration
of Negotiated Contracts.”
8.4.4 | VDOT assures compliance with Title VI of the Civil Rights Act of 1964, as amended.
The Consultant and all subconsultants selected for this Project shall be required to submit
a Title VI Evaluation Report (EEO-D2) when requested by VDOT to respond to the SFP.
This requirement applies to all consulting firms with fifteen (15) or more employees.
8.4.5 | VDOT does not discriminate against an Offeror because of race, religion, color, sex,
national origin, age, disability, or any other basis prohibited by state Law relating to
discrimination in employment.
8.4.6 | Please indicate in the Letter of Submittal, Section 10.2, and by executing and returning
the attached Certification Regarding Debarment Forms, provided in Appendix C, if your
firm, subconsultant, subcontractor, or any person associated therewith in the capacity of
owner, partner, director, officer or any position involving the administration of federal or
state funds:
| 1. | Is currently under suspension, debarment, voluntary exclusion or determination of
ineligibility by any State or federal agency;
| 2. | Has been suspended, debarred, voluntarily excluded or determined ineligible by
any federal agency within the past three years;
| 3. | Has a proposed debarment or suspension pending; or
| 4. | Has been indicted, convicted, or had a civil judgment rendered against it or them
|  | by | a | court | of | competent | jurisdiction |  |  | in | any | matter | involving | fraud | or | official
misconduct within the past three years.
Any of the above conditions will not necessarily result in denial of award, but will be
| considered in determining Offeror responsibility. | [9 empty] | For any condition noted, indicate to
| whom it applies, initiating agency, and dates of action. | [10 empty] | Providing false information may
| result in federal criminal prosecution or administrative sanctions. | [11 empty] | Certifications should
be submitted directly behind the Letter of Submittal.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
24
8.4.7 | Offerors shall note and comply with the requirements relative to the eVA Business-to-
| Government Vendor system. |  |  |  | The eVA Internet electronic procurement solution, web site
| portal | (http://www.eva.state.va.us), |  |  |  | streamlines |  |  | and | automates |  | government |  | purchasing
| activities | in | the | Commonwealth. |  | The |  | portal | is | the | gateway | for | vendors | to | conduct
| business with state agencies and public bodies. | [8 empty] | All vendors desiring to provide goods
and/or services to the Commonwealth shall participate in the eVA Internet e-procurement
solution through either eVA Basic Vendor Registration Service or eVA Premium Vendor
| Registration |  | Service. | For | more | detail |  | information |  | regarding |  | eVA, | registrations, |  | fee
| schedule, | and | transaction |  | fee, | use | the | website |  | link: | http://www.eva.state.va.us. |  |  |  | All
Offerors must register in eVA; failure to register will result in a Conceptual Proposal
being rejected.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
25
9 | CONFLICT OF INTEREST
9.1 | Conflict of Interest Determination
9.1.1 | VDOT will apply the procedures set forth in the Innovative Project Delivery Division
Memorandum 07-2.0, dated August 1, 2007, for identification and review of potential
organizational conflicts of interest related to VDOT procurement of contracts under the
PPTA or design-build legislation. This memorandum is available at VDOT’s website at
http://www.virginiadot.org/business/bu-ipd-memo.asp.
9.1.2 | Offerors |  | shall | note | that | portions | of | the | SFP | Documents |  | will | include | work |  | product
developed by the others.
| 1. | The firms listed below will not be allowed to participate as a team member with an
|  | Offeror | for | this | Project | due | to | their |  | participation |  | in | assisting | VDOT |  | with:
|  | procurement |  | documents; |  | negotiations |  |  | strategies |  | and | negotiations; |  |  | business | and
|  | policy | decisions; |  |  | contract | management |  |  | and | administration; |  |  |  | development,
negotiation, and execution of interim and/or comprehensive Agreement; and reports
|  | and contact language. |  |  |  | Any proposal received in violation of this requirement may be
rejected.
|  | Halcrow | Inc.; |  | Public | Resources |  | Advisory |  | Group |  | (PRAG); |  | C&M; |  | Jeffrey | A.
Parker and Associates, KPMG Corporate Finance LLC; Warner Construction
|  | Consultants, |  | Inc.; |  | Capital | Project |  | Strategies, |  | LLC, | and |  | Nossaman |  | LLP | /
Nossaman, O’Conner & Hannan LLP
| 2. | The firms listed below have completed work that is available to prospective Offerors
|  | and | VDOT | has | determined | that, |  | at | this | time, | they | would | not | have | a | conflict | of
interest if they chose to pursue the Project with a private developer.
Parsons Brinkerhoff, Michael Baker and Rummel, Klepper, and Kahl LLP
9.2 | Ethics in Public Contracting Act
VDOT may, in its sole discretion, disqualify the Offeror from further consideration for
the award of the contract if it is found by VDOT that there is a violation of the Ethics in
Public Contracting Act, Section 2.2-4367 of the Virginia Code, or any similar statute
involving the Offeror in the procurement of the contract.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
26
10 | CONTENTS OF CONCEPTUAL PROPOSAL
The Conceptual Proposals should provide sufficient information to facilitate evaluation of
| the Offeror’s qualifications and Conceptual Financial Plan. | [10 empty] | Section 10 describes the type
of information that must be included in the Conceptual Proposals. The format for the
presentation of such information within the Conceptual Proposal is described in Section
4.8.
| Offerors |  | shall | be | aware | that | VDOT | reserves | the | right |  | to | conduct | an | independent
investigation of any information, including prior experience, identified in a proposal by
| contacting |  |  | project | references, |  | accessing | public | information, |  |  |  | contacting |  | independent
| parties, |  | or | any | other | means. | VDOT | also | reserves |  | the | right | to | request | additional
information from an Offeror during the evaluation of its Conceptual Proposal.
10.1 | Confidentiality
| Confidentiality requests should be consistent with Section 8.1 of this SFP. | [12 empty] | It is VDOT’s
| policy to be transparent throughout the entire procurement process. | [11 empty] | The classification of
| the entire Conceptual Proposal as confidential is not acceptable. | [11 empty] | Offerors shall clearly
disclose any anticipated source and amount of public funds, programs or services in the
Executive Summary and in the Conceptual Financial Plan and such information shall not
be exempt from disclosure.
10.2 | Letter of Submittal
Each Offeror shall provide a Letter of Submittal on the Offeror’s letterhead signed by an
authorized Representative of the Offeror’s organization, which individual shall be the
| contact point for all communications from VDOT related to the SFP or the Project. | [13 empty] | The
letter shall not exceed four (4) pages in length and shall meet the following requirements:
|  | Include the authorized Representative’s title, address, phone and fax numbers, and e-
mail addresses;
|  | Provide name and address of lead firm and consortium firms who are to be part of the
Offeror’s team;
|  | Certification Regarding Debarment forms as provided in Appendix C;
|  | If the Offeror is not yet a legal entity or is a joint venture or other enterprise which
consists of parties who will be jointly and severally liable for all the private entity’s
obligations under the interim and/or comprehensive agreement, then all such parties
(including but not limited to the lead contractor and lead designer), or, if applicable,
all joint venture partners/members shall sign the letter;
|  | All signatures shall be original and signed in ink;
|  | Include the written commitment of all signators to be jointly and severally liable for
|  | all | obligations |  | of | the | private | entity | under | the | interim |  | and/or | comprehensive
agreement; and
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
27
|  | Describe any parent guarantees that the Offeror will provide to secure its performance
|  | of | its | obligations |  |  | under | the | interim | and/or |  | comprehensive |  |  | agreement, |  |  | and | any
proposed limits on the liability of the private entity or its guarantors.
10.3 | Executive Summary
| Each Offeror shall provide an Executive Summary. | [10 empty] | The Executive Summary shall not
exceed five (5) pages and should include the following items:
10.3.1 | Brief |  | description |  |  | of | all | significant |  | aspects | of | the | Conceptual |  |  | Proposal |  | and | the
| implementation |  |  |  | team, |  | to | include | the | Offeror’s |  | objectives |  | in | the | development |  |  | and
operation of the Project.
10.3.2 | Declaration |  |  | as | to | whether |  | public | financial | support |  | is | not | necessary |  | in | the | Offeror’s
approach for implementation of the Conceptual Financial Plan.
10.3.3 | Declaration of Offeror’s intent, if selected, to enter into an interim and/or comprehensive
agreement with VDOT for the Project in accordance with the terms of this procurement.
10.3.4 | Declaration that the offer presented in the Conceptual Proposal shall remain in full force
and effect until such time as submission of the Detailed Proposals.
10.3.5 | Declaration that information provided in the Conceptual Proposal meets appropriate state
and federal, standards, statutes and regulations, or reasonably anticipated modifications
of state or federal statutes, regulations or standards.
10.4 | Conceptual Proposal Submittal Criteria
| Offerors |  | are | advised |  |  | that | the | Conceptual | Proposal |  | submittal |  | and |  | evaluation |  | criteria
contained herein has been modified from the Guidelines. These modifications were made
in order to meet the specific needs of the Project and VDOT. Further, the submittal and
evaluation criteria listed herein supersede the criteria listed in the Guidelines.
Offerors should limit their Conceptual Proposal responses to the request for qualifications
| and | information |  |  | identified |  |  | below. | Responses |  | should | focus |  | on | critical | issues |  | for | the
Project, the objectives of the Conceptual Proposals and on the stated evaluation criteria
listed herein.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
28
Section 10.4.1 Qualifications Criteria
.1 | Financial | For all team members who will be providing equity and/or providing the
| Capacity | performance security for the initial construction of the Project, (to include
any parent or related companies from whom financial guarantees will be
provided) the following documentation must be provided:
|  | 1. | Audited financial statements for each of the last five (5) years
prepared:
|  |  |  | a. | in | accordance |  | with | U.S. | Generally |  |  | Accepted
[5 empty] | Accounting |  | Principles |  | (GAAP) |  |  | or | International
Financial Reporting Standards (IFRS);
|  |  |  | b. | in English;
|  |  |  | c. | in US dollars*; and
|  |  |  | d. | including balance sheet, profit and loss statements,
and statement of changes in financial position and
accompanying notes to financial statements.
If the audited financial statements are prepared in accordance
with an accounting standard other than U.S. GAAP or IFRS, a
letter must be provided by a Certified Public Accountant (or
|  |  | equivalent |  | professional |  | accountant) |  |  | discussing |  |  | the | major
differences between the standards upon which these financial
statements are prepared and U.S. GAAP or IFRS.
|  |  | *If | audited | financial | statements |  |  | are | not | available |  | in | U. | S.
|  |  | dollars, | items |  | required | in | 10.4.1.1.1 |  | (d) | converted |  | into | U.S.
|  |  | dollars | will | suffice. | However, |  | a | CPA |  | or | other | accountant
|  |  | professional |  | equivalent |  | letter | describing |  |  |  | assumptions |  | and
|  |  | confirming |  | accuracy | of | calculations |  |  | and | fair | representation
results shall be provided.
|  | 2. | Interim financial statements for the most recent period since the
last fiscal period.
|  | 3. | Most recent Securities and Exchange Commission 10-K and 10-
Q reports, if such reports have been filed.
|  | 4. | Current and planned financial commitments to other projects,
any off-balance sheet liabilities and an assessment of the extent
to which these commitments may affect the Offeror’s ability to
raise the necessary finance for the Project.
|  | 5. | Commitment letters from parent company or related parties who
are proposed to provide financial guarantees to the Project.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
29
.2 | Project | a. On an aggregate basis, identify members of the team that have been
| Finance | involved in successfully financing long-term Public Private Partnership
| Experience | (P3) transportation projects valued in excess of $500 million total (US$)
initial capital costs including a role as an equity investor within the last
ten (10) years.
|  | With | respect | to | the | Offeror’s |  | financing |  | experience, |  | the | following
|  | documentation |  | for | up | to | three | of | the | most | recent | projects | must | be
provided (in US$):
|  |  | 1. | Name of individual team member involved
|  |  | 2. | Name of project
|  |  | 3. | Description of project
|  |  | 4. | Location of project
|  |  | 5. | Total project costs
|  |  | 6. | Year of financial close
|  |  | 7. | Value of financing
|  |  | 8. | Description of financing
|  |  | 9. | Value of equity invested
|  |  | 10. Third |  | party | reference |  | (Name, |  | organization, |  | phone | number,
email)
|  | This | information |  | should | be | provided |  | on | the | Work | History | Form | 1,
Appendix D.
b. Provide a narrative describing the extent and depth of the Offeror’s
experience in financing projects similar to the Project.
|  | With | respect | to | the | Offeror’s |  | financing |  | experience, |  | the | following
additional information must be submitted for each representative project
(maximum five projects):
|  |  | 1. | Team member (firm) name
|  |  | 2. | Name of project
|  |  | 3. | Description of project
|  |  | 4. | Location of project
|  |  | 5. | Year of financial close
|  |  | 6. | Value of financing
|  |  | 7. | Description of financing
|  |  | 8. | Role in financing
|  |  | 9. | Third | party | reference |  | (Name, |  | organization, |  | phone | number,
email)
|  | This | information |  | should | be | provided |  | on | the | Work | History | Form | 1,
Appendix D.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
30
Note: If Offeror chooses to list individual team member experience gained
|  | from | another |  | firm | as | relevant |  | to | the | Offeror’s |  | qualifications, |  |  |  | then | the
Offeror shall also identify these specific team members as Key Personnel.
|  | The | information |  |  | regarding |  | Key | Personnel |  |  | should |  | be | provided |  | on | the
Resume Form, Appendix E.
.3 | Project | What is the direct and relevant experience of the Offeror’s team in the
| Design, | design, |  | construction, |  |  | operations |  |  | and | maintenance |  |  |  | of | infrastructure
| Construction, | projects of similar scope and magnitude as this Project?
Maintenance
| and | List | and | describe |  | a | maximum |  | of | ten | (10) | projects |  |  | that | the | Offeror’s
| Operations | proposed team, to include, the Offeror, and lead team members for design
and construction and operations and maintenance has been involved in,
|  | which | best |  | illustrates |  | current |  | qualifications |  |  |  | relevant |  | to | the | unique
components of this Project.
|  | Provide |  | the | overall |  | history |  | of | performance, |  |  |  | including |  |  | schedule
|  | completion, |  |  | cost | and | budget |  | control, |  | and | assessment |  |  |  | of | liquidated
damages, on all ten (10) projects as indicated above and undertaken by the
Offeror, the design-build Contractor and the operator.
|  | a. | Provide | specific |  | relevant |  |  | experience |  | of | the | Offeror |  |  | and | its | team
members who will be responsible for the operations and maintenance of
the roadway. Identify direct and relevant experience related to operation
of a reversible roadway during an emergency or evacuation event.
|  | This | information |  |  | should |  | be | provided |  | on | the | Work |  | History |  | Form | 3,
Appendix D.
|  | b. | Provide specific relevant experience of the Offeror and its lead team
members which will be responsible for the design and construction of the
|  | roadway, |  | including |  |  | its | record | of | success |  |  | in | the | development |  |  | of
|  | comparable |  |  | projects |  | and | responsibilities. |  |  |  | Identify |  |  | the | design |  | and
construction teams’ prior working relationships, if any.
Provide at least three examples of projects that included the Offeror’s
|  | design team in a leading role. | [6 empty] | Include a minimum of one of the three
projects that involved a greenfield project.
Provide at least three examples of projects that included the Offeror’s
construction team in a leading role. Include a minimum of one of the
three projects that involved a greenfield project.
In addition, provide information as to whether the Offeror, design-build
Contractor have defaulted on any contracts in the last seven (7) years.
Provide details if any.
|  | This | information |  |  | should |  | be | provided |  | on | the | Work |  | History |  | Form | 2,
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
31
Appendix D.
|  | Lead | team |  | members |  | identified |  |  | in | response |  | to | these | criteria |  | will | be
|  | deemed |  | “Key |  | Personnel”. |  |  | The | information |  |  | regarding |  | Key | Personnel
should be provided on the Resume Form, Appendix E.
.4 | Toll Facility | What | is | the |  | extent | and | depth |  | of | the | Offeror’s |  | direct | and |  | relevant
| Operations | experience |  |  | in | undertaking |  | toll |  | operations |  | for | a | project | or | projects |  | of
similar scope and magnitude as this Project in the last ten (10) years?
With respect to the Offeror’s tolling experience the following information
should be submitted for each project (for a maximum of three projects):
|  |  | 1. | Name of team member involved
|  |  | 2. | Name of project
|  |  | 3. | Location of project
|  |  | 4. | Description of project
|  |  | 5. | Description of tolling (manual toll booths, electronic tolling,
video tolling, variable tolling, etc.)
|  |  | 6. | Description of |  |  | tolling responsibilities
|  |  | 7. | Third party reference (Name, organization, phone number,
email)
This information should be provided on the Work History Form 1,
Appendix D.
.5 | Conceptual | Provide an approach to developing a reasonable and viable financial plan
| Financial | that fully funds total project cost.
Plan
With a focus on achieving the Project objectives, the extent to which the
Conceptual Financial Plan submitted demonstrates the following:
|  | 1. | An |  | understanding |  |  |  | of | long-term |  | P3 |  | financing |  | of | major
infrastructure projects;
|  | 2. | An understanding of viable financing options available in the U.S.
markets;
|  | 3. | An |  | understanding |  |  | of | the | unique |  | financing |  | characteristics |  |  | of | the
Project; and
|  | 4. | The plan is achievable in the current U.S. financial markets.
a. The Offeror must provide a qualitative description (maximum three (3)
|  | pages) |  | of | the | Offeror’s |  | approach |  |  | to | financing |  | the | development,
|  | maintenance and operations of the Project. | [9 empty] | At a minimum, this discussion
should address:
|  |  | 1. | Potential sources and uses of funds and a brief description of the
listed funding sources;
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
32
| 2. | Potential payment mechanisms for the Project;
| 3. | Financial support that may be available from team members;
| 4. | No Federal funding or Federal Programs should be assumed;
| 5. | Approaches to user fee and toll regulation including a projected
range of initial toll rates; and
| 6. | Roles | and | responsibilities |  | for | the | public | and | private | sector
parties as it relates to financing.
b. The Offeror must provide its estimated sources and uses of funds as
well as providing the information as described in the Conceptual Finance
Plan | Pro | Forma, | Appendix |  | G. | Traffic | numbers | distinguishing |  |  | between
cars and trucks (% and AADT), revenue numbers and cash flow data shall
be provided separately in ten (10) year increments to the end of the term.
All | information |  | in | section | 10.4.1.6b | shall | be | provided | in | a | Microsoft
Excel spreadsheet electronically.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
33
11 | EVALUATION PROCESS
| VDOT | will | review | and | evaluate | each |  | Conceptual |  | Proposal |  | based |  | on | the | Offerors’
qualifications to finance, design, construct, maintain and operate the Project over the long
term through the demonstration of significant and relevant experience and capabilities
meeting the Project objectives.
The criteria will consider, among other things, the Offerors’ relevant experience with the
development and financing of transportation infrastructure projects of similar complexity
| and | scope; | the | operations | and | maintenance |  |  | of | toll | highways; |  | and | the |  | operations,
maintenance and management of highway corridors and integrated networks.
| The | Conceptual |  | Proposal | evaluation |  | criteria |  | reflect |  | VDOT’s |  | main | objectives |  |  | and
priorities during project development and its evaluation of the Proposals in response to
the SFP.
11.1 | Evaluation Rating System
Conceptual Proposals will be evaluated by applying the rating system as set forth below.
The rating system that will be used for the assessment of the Conceptual Proposals is
| detailed in Table 11.1. |  |  |  | The rating system will have four rating levels for the evaluator.
| Within | each | of | the | rating | levels, | an | evaluator |  | may | provide |  | specific |  | information
differentiating the basis of their evaluation and whether one Offeror is more qualified, but
| is rated within the same rating level. |  |  |  |  | For example, if four Offerors each are rated a Green
proposal response, this would not necessarily signify that all four Offerors are equally
| ranked. | Based on the information provided in the Conceptual Proposal, an evaluator has
the discretion to rank each Offeror, notwithstanding the fact that he/she may have rated
all Offerors as a Green for a particular category.
| Based | on | its | evaluation, |  | VDOT | will | then |  | provide |  | recommendations |  |  |  | to | the
Commonwealth Transportation Commissioner, the IRP and the CTB, as to whether none,
one, or more Conceptual Proposals should be advanced to Phase Four.
| Evaluation Criteria and a rating system have not yet been determined for the RFDP. | [15 empty] | If an
Offeror is selected to advance to Phase Four the evaluation and selection criteria will be
provided in the RFDP.
TABLE 11.1 – VDOT EVALUATION RATING SYSTEM
|  | Adjectival Rating | [5 empty] | Adjectival Rating Description
| Blue | [5 empty] | Conceptual |  |  | Proposal |  | indicates |  |  | significant
[7 empty] | strengths |  | and/or |  | a | number | of | minor |  | strengths
[7 empty] | and | no | weaknesses. |  |  | Submitter |  |  | provides |  | a
[7 empty] | consistently |  |  | outstanding |  |  | level |  | of | quality,
[7 empty] | qualifications, |  |  |  | performance |  |  | or |  | capability
[7 empty] | requirements |  |  | in | a | way | beneficial |  |  | to | the
Commonwealth.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
34
Green | Conceptual |  | Proposal | meets |  | relevant
| qualifications, |  | performance |  | or | capability
requirements necessary for acceptable contract
performance.
Yellow | Conceptual | Proposal | does | not | clearly | meet
| some | relevant | qualifications, |  | performance | or
| capability | requirements |  |  | necessary | for
| acceptable | contract | performance, |  | but | proposal
inadequacies may be correctable.
Red | Conceptual | Proposal | fails | to | express | relevant
| qualifications, |  | performance |  | or | capability
requirements.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010
APPENDIX A
DEFINITIONS
Concessionaire means the individual, company, firm, partnership, corporation,
association or joint venture contemplated to contract with VDOT in conjunction with this
SFP and pursuant to the execution of an Interim and/or Comprehensive Agreement.
| Conceptual |  | Proposals |  | means |  |  | Offeror’s |  | submission |  |  |  |  | of | Statement |  |  | of
Qualifications and Conceptual Financial Plan in response to VDOT’s request for such
proposals.
Consultant means any Person at the time retained by or on behalf of VDOT or
the | Concessionaire, |  | which | Person |  | is | experienced |  |  | and | has |  | a | national |  | and |  | favorable
reputation in the matters for which such Person is so employed.
Contractor means any Person with whom the Concessionaire has entered into
any contract to perform any part of the Work or provide any materials, equipment or
supplies for the Project and/or the Utility Relocations included in the Work, on behalf of
the | Concessionaire, |  | and | any | other | Person |  | with |  | whom | any |  |  | Contractor |  |  | has |  | further
subcontracted any part of the Work, at all tiers.
| CTB | means | the | Commonwealth |  |  | Transportation |  |  |  | Board, |  |  | a | board |  | of | the | State
affiliated with VDOT.
| Detailed |  | Proposals | means |  | short | listed |  | Offerors’ |  | submission |  |  |  |  | of | proposals |  | in
response to VDOT’s request for such proposals under Phase Four of the evaluation and
procurement process.
Electronic Toll Collection means the collection of tolls based on the automatic
identification and classification of vehicles using electronic systems.
| Experience |  | Modification |  | Rating |  |  | (EMR) |  | means |  | a | mandatory |  |  |  | process |  | that
modifies the published rates for rating classifications by taking into account the actual
reported | losses | and | payrolls | of | an | individual |  |  | business. |  | It | is | a | financial |  |  | incentive |  | to
employers to minimize the financial cost of workplace injuries. The rate is based on two
major | issues: | the | number | of | claims |  | and | the | cost | of | each |  | claim |  | reported |  |  | over | an
experience period. The experience period is usually three full policy years, ending one
year prior to the effective date of the modification. To illustrate, a modification effective
January | 1, | 2008 | uses | payrolls | and | losses |  | for | the | policies |  | effective |  |  | January |  |  | 1, | 2004;
January 1, 2005; and January 1, 2006.
| Federal | Highway |  | Administration |  |  |  | (FHWA) |  | means |  | the |  | branch |  | of | the |  | United
States | Department |  | of | Transportation |  |  | which | funds |  | and | oversees |  |  |  | new | highways |  |  | and
highway improvement projects.
Financial Closing Date (Financial Close) means the closing date of the issuance
of tax-exempt bonds or the issuance of taxable debt and/or equity, the proceeds of which,
in either case, are sufficient together with other available funds to finance the completion
of the design and construction of the Project or the related Phase, as applicable
Financial Plan (Conceptual Financial Plan) means Offeror’s conceptual plan
which describe planned use and source of funds to cover anticipated Project costs and
expenditures |  | related | to | the | finance, | design, | construction, |  | operation, |  | maintenance |  | and
handback | phases | of | work, |  | including | annual | updates | for | which | such | plan | and | annual
updates meet the requirements of Section 1904(a) of SAFETEA-LU and FHWA Major
Projects Guidance, March 2007.
| Generally | Accepted |  |  | Accounting | Principles |  | (GAAP) | means |  | a | collection | of
methods used to process, prepare, and present public accounting information representing
such accepted accounting practice as, in the opinion of the Accountant, conforms at the
time to generally accepted accounting principles in the United States of America
| Governmental |  |  | Authority |  | means | any | court, | federal, | state, |  | department,
commission, board, bureau, agency or other regulatory, administrative, or governmental
entity or authority having jurisdictional authority in accordance with State or Federal
Laws.
Implementation Guidelines (Guidelines) means such guidelines presenting the
goals and objectives as governed by the Public Private Transportation Act (PPTA) of
1995 (§ 56-556 et seq. of the Code), as amended.
| International |  | Financial |  | Reporting |  | Standards | (IFRS) |  | means | standards |  | and
interpretations adopted by the International Accounting Standards Board (IASB) which
state how particular types of transactions and other events should be reported in financial
statements. Major financial centers in various countries of each continent apply these
standards | to | promote | uniformity |  | in | financial | reporting | and | practices |  | and | to | generate
financial statements that are understandable in all of the countries they operate.
Key Personnel is defined in Section 10.4.1.5 of the SFP.
Law(s) mean any current or future order, writ, injunction, decree, judgment, law,
ordinance, decision, opinion, ruling, statute, code, rule or regulation of any Governmental
Authority.
Letter of Submittal is defined in Section 10.2 of the SFP.
NEPA means the National Environmental Policy Act, 42 U.S.C. § 4321 et seq., as
amended and as it may be amended from time to time.
Open Road Tolling (ORT) means an electronic toll collection system without
toll plazas, where drivers will be charged the toll without having to stop, slow down, or
stay in a given lane.
- 2 -
Project means collectively, the provision for a new four-lane divided highway
between Interstate-295 in Prince George County and U.S. Route 58 Bypass in the City of
Suffolk, Virginia and as further defined in Article 3 of the SFP.
Regulatory Approvals means all local, regional, state and federal agreements,
studies, findings, permits, approvals, authorizations, certifications, consents, decisions,
exemptions, |  |  | filings, |  | leases, |  | licenses, | registrations, |  |  | rulings |  | and | other | governmental
authorizations |  |  | required |  | to | be | obtained | or | completed |  | under |  | applicable |  | Laws | prior | to
undertaking |  |  | any | particular |  | activity |  | contemplated |  |  | by | this | Agreement. |  | The |  | term
“Regulatory Approvals” includes any supplements to the EIS.
| Representative |  |  |  | means, |  | with | respect |  | to | any | Person, |  | any | director, | officer,
employee, official, lender (or any agent or trustee acting on its behalf), partner, member,
owner, | agent, |  | lawyer, |  | accountant, |  | auditor, |  | professional |  |  | advisor, |  | Consultant, |  | engineer,
contractor, |  | other |  | Person |  | for | whom | such | Person |  | is | at | law | responsible |  | or | other
representative |  |  | of | such | Person |  | and | any | professional |  | advisor, |  | Consultant |  | or | engineer
designated by such Person as its “Representative.”
Responsible Public Entity has the meaning assigned to such term in Section 56-
557 | of | the | PPTA | and, |  | for | purposes |  | hereof, |  | means | the | Virginia |  | Department |  | of
Transportation.
| SFP |  | Documents |  | mean |  | the | documents, |  | whether |  | attached |  | or | incorporated |  | by
reference, furnished by VDOT as part of the Solicitation for Proposals for the Project.
| Solicitation |  |  | for | Proposals |  | (SFP) |  | means |  | VDOT’s |  | request | for | such | proposals
under Phase One of the procurement process for the Project.
State means the Commonwealth of Virginia.
| Statement |  |  | of | Qualifications |  |  | means | a | statement |  | of | the | Offeror’s | experience,
financial capacity, Key Personnel, a current profile of the Offeror teams’ activities, and
other pertinent information relevant to the Project.
Toll Agreement means the agreement signed between the FHWA and a State or
local government or other entity to grant the authority to collect tolls.
VDOT means Virginia Department of Transportation.
Violation Enforcement System means the collective equipment and procedures
that capture a violation transaction, image and the citation process.
Virginia Code means the Code of Virginia of 1950, as amended.
Work means all development and operation [as defined in the PPTA] required to
be furnished and provided by or on behalf of the Concessionaire as contemplated under
an executed comprehensive agreement, including all labor, materials, equipment, services
- 3 -
and documentation required to develop and operate the Project, except for those efforts
which the comprehensive agreement expressly specifies will be performed by VDOT.
- 4 -
APPENDIX B
PPTA
ORDER FORM
ROUTE 460 CORRIDOR IMPROVEMENT PROJECT
SOLICIATION FOR PROPOSALS (SFP)
INFORMATION PACKAGE
FIRM NAME ______________________________________________________________________________________________
COMPLETE MAILING
ADDRESS________________________________________________________________________________________________
_________________________________________________________________________________________________________
(PLEASE GIVE BOTH STREET ADDRESS AND POSTAL DELIVERY ADDRESS)
FIRM TELEPHONE NUMBER________________________________ |  | FIRM FAX NUMBER___________________________
E-MAIL ADDRESS ________________________________________________________
SIGNED:____________________________________________________________________________
FOR QUESTIONS REGARDING THE SFP INFORMATION PACKAGE CONTACT:
MARGIE RAY
VIRGINIA DEPARTMENT OF TRANSPORTATION
1401 EAST BROAD STREET
RICHMOND, VIRGINIA 23219
(804) 786-9537
TO ORDER THE SFP INFORMATION PACKAGE BY TELEPHONE/MAIL/FAX CONTACT:
THE SCHEDULING AND CONTRACT DIVISION PLAN ROOM
VIRGINIA DEPARTMENT OF TRANSPORTATION
1401 EAST BROAD STREET
RICHMOND, VIRGINIA 23219
(804) 786-1898,786-5161 OR 371-9868
FAX TELEPHONE NO. (804) 786-2788 (Ordering by fax using a Master or Visa credit card is the preferred
method)
MASTERCHARGE/VISA NO.___________________________________________________
EXPIRATION DATE:____________________________
THE SFP INFORMATION PACKAGE WILL NOT BE ISSUED PRIOR TO RECEIPT OF PAYMENT
Dear Sir/Madam:
Please send the SFP Information Package designated below. |  | Enclosed is check No.____________in the amount of $__________
made payable to the Treasurer of Virginia.
TO VIEW THE SFP GO TO THE WEBSITE ADDRESS LISTED BELOW
http://route460ppta.org/
SFP NO. | PROJECT | PACKAGES | TOTAL
|  | REQUESTED | ($50.00 per package, price includes
5%Virginia Sales Tax)
|  | # | $
Route 460 Corridor Improvement Project
FOR DEPARTMENTAL USE ONLY
SFP PACKAGE MAILED____________________________ |  | MAILED BY_________________________
TO BE MAILED___________________________________ |  | CHECKED BY_________________________
APPENDIX C
Certification Regarding Debarment
Primary Covered Transactions
Project: | Route 460 Corridor Improvements Project
1) | The prospective primary participant certifies to the best of its knowledge and belief, that it and
its principals:
| a) | Are not presently debarred, suspended, proposed for debarment, declared ineligible, or
voluntarily excluded from covered transactions by any Federal department or agency.
| b) | Have not within a three-year period preceding this proposal been convicted of or had a
civil judgment rendered against them for commission of fraud or a criminal offense in connection
with obtaining, attempting to obtain, or performing a public (Federal, State or local) transaction or
contract under a public transaction; and have not been convicted of any violations of Federal or State
antitrust statutes or commission of embezzlement, theft, forgery, bribery, falsification, or destruction
of records, making false statements, or receiving stolen property;
| c) | Are | not | presently | indicted | for | or | otherwise | criminally | or | civilly | charged | by | a
governmental entity (Federal, State or local) with commission of any of the offenses enumerated in
paragraph 1) b) of this certification; and
| d) | Have not within a three-year period preceding this application/proposal had one or
more public transactions (Federal, State or local) terminated for cause or default.
2) | Where the prospective primary participant is unable to certify to any of the statements in this
certification, such prospective participant shall attach an explanation to this proposal.
The undersigned makes the foregoing statements to be filed with the proposal submitted on behalf of
the Offeror for contracts to be let by the Commonwealth Transportation Board.
______________________________________ | [7 empty] | _________________________
Signature |  |  |  | Date |  |  |  | Title
___________________________________________________________________
Name of Firm
_________________________________________________________________________________________________
Commonwealth of Virginia
Virginia Department of Transportation
Page 1 of 2
APPENDIX C
Certification Regarding Debarment
Lower Tier Covered Transactions
Project: Route 460 Corridor Improvements Project
1) | The prospective lower tier participant certifies, by submission of this proposal, that neither it
nor its principals is presently debarred, suspended, proposed for debarment, declared ineligible, or
voluntarily excluded from participation in this transaction by any Federal department or agency.
2) | Where the prospective lower tier participant is unable to certify to any of the statements in this
certification, such prospective participant shall attach an explanation to this proposal.
The undersigned makes the foregoing statements to be filed with the proposal submitted on behalf of
the Offeror for contracts to be let by the Commonwealth Transportation Board.
____________________________________ |  | __________________
Signature | Date | Title
____________________________________________________________
Name of Firm
_________________________________________________________________________________________________
Commonwealth of Virginia
Virginia Department of Transportation
Page 2 of 2
APPENDIX D
Work History Form 1 (Financial)
List experience with projects similar to the proposed Project, which best illustrates current qualifications relevant to this Project.
a. Team Member or | b. | Name of the Project, | c. Project Owner’s Name & | d. Project | e. | Third Party | f. Year of Financial | g. Financing/Security/Insurance
Firm’s Name |  | Location, Description | Address, Project | Cost |  | Reference Name, | Close or Year | Description/Type | Role/Tolling | Value/Amount/Equity
|  | and Tolling Description | Manager’s Name, Phone |  |  | Organization, | Posted (pertaining |  | Responsibility | Invested
|  | (if applicable) | Number |  |  | Phone Number | to Securities)
(1)
(2)
(3)
(4)
(5)
(6)
(7)
(8)
(9)
(10)
APPENDIX D
Work History Form 2
List experience with projects similar to the proposed Project, which best illustrates current qualifications relevant to this Project.
a. Project Name & | b. Project Owner’s Name & | c. Nature of Firm’s Responsibilities | d. Contract | e. Contract |  |  | f. Estimated Value (in Thousands)
Location | Address, Project |  | Completion Date | Completion | Original | Final or | Dollar Value of Work for | Liquidated
| Manager’s Name, Phone |  | (Original) | Date (Actual | Contract | Estimated | Which Firm Was/Is | Damages/Defaults
| & Fax Number |  |  | or Estimated) | Value | Contract | Responsible
Value
(1)
(2)
(3)
(4)
(5)
(6)
(7)
(8)
(9)
(10)
APPENDIX D
Work History Form 3 – Experience of the Lead Operations and Maintenance Firm* in the Operation and Maintenance of Roadway Facilities
a. Project Name & Location | b. Project Owner’s | c. Nature of Firm’s | d. Lane Miles | e. Duration of Maintenance | f. Estimated Value in Thousands |  | g. Firm’s Number of Employees per
| Name & | Responsibilities | Maintained per | Period (state if ongoing) |  |  | project
| Address, Project |  | project |  | Original Contract Value | Dollar Value of Work for
| Manager’s |  |  |  |  | Which Firm Was/Is
| Name, Phone & |  |  |  |  | Responsible
Fax Number
(1)
(2)
(3)
(4)
(5)
(6)
(7)
(8)
(9)
(10)
*List the experience of Lead Operations and Maintenance Firm only, whether or not future shareholders of the concessionaire.
APPENDIX E
RESUME FORM
Brief Resume of Key Personnel/Offeror’s team members anticipated for this project.
a. | NAME & TITLE:
b. | PROJECT ROLE:
c. | NAME OF FIRM WITH WHICH ASSOCIATED:
d. | YEARS EXPERIENCE: |  | With this firm:
With other firms:
In role as stated in letter “b”:
e. | EDUCATION: | Educational Institution:
Degree(s):
Year:
Specialization:
f. | ACTIVE REGISTRATION: Year First Registered:
Discipline:
Location of Registration:
g. | CERTIFICATIONS:
h. | EXPERIENCE | AND | QUALIFICATIONS | RELEVANT | TO | THE | PROPOSED
PROJECT:
APPENDIX F
Term Sheet for the Development of a Comprehensive Agreement
Page 1 of 23
1 | Introduction
This term sheet identifies and summarizes several key terms and conditions which
will form the basis of, and shall be incorporated into, the Comprehensive Agreement
negotiated by the Department and the Concessionaire. The terms are based on the
premise that the Project will be financed solely with private funds. The terms would be
different for a project relying in whole or in part on public funds.
2 | Definitions
[Reserved]
3 | Basic Roles and Responsibilities
| 3.01 | Basic Agreement
|  | (a) | Concessionaire shall provide appropriate oversight, management,
and reporting of all phases of the Project and its subcontractors such that the
Project is delivered, operated, and maintained in accordance with, and fit for the
purpose intended by, the Comprehensive Agreement.
|  | (b) | Concessionaire shall perform, or cause to be performed, the work
required by the Comprehensive Agreement in accordance the Standard of Care (as
defined in Section 3.02 below).
|  | (c) | Concessionaire may retain subcontractors to perform certain of
Concessionaire’s responsibilities under the Comprehensive Agreement, subject to
Section 24.02.
|  | (d) | VDOT will perform only minimal construction oversight and will
rely on the Concessionaire to directly manage, oversee, and resolve disputes
involving its subcontractors without the involvement of the Department. VDOT
will rely on the Concessionaire’s quality assurance/quality control work and on
the Concessionaire’s certifications that the work complies with contract
requirements. The Concessionaire will be responsible for VDOT’s construction
oversight costs, estimated at two (2) percent of the design and construction costs.
| 3.02 | Standard of Care
|  | (a) | As used herein, “Standard of Care” means performance of the
work in compliance with all of the following standards:
|  |  | (i) | specific standards, methods, and requirements set forth in
the Comprehensive Agreement, including the Technical Requirements;
Page 2 of 23
|  |  | (ii) | all applicable laws, including laws applicable to a
transportation project that has received or receives federal-aid funds;
|  |  | (iii) | all regulatory approvals;
|  |  | (iv) | the application of professional engineering judgment taking
into consideration safety, operational requirements, level of service, and
life cycle costs;
|  |  | (v) | prudent industry practices, methods, techniques, and
standards and using the degree of care that would be expected to be
exercised by a prudent, skilled, and experienced contractor engaged in the
same kinds of undertakings as the Project under the same or similar
circumstances or conditions as those applying to the design, development,
construction, and operation of the Project; and
|  |  | (vi) | the requirements of insurance policies required to be
maintained pursuant to the Comprehensive Agreement.
Neither compliance with a minimum requirement set forth in any specific
standard set forth above, nor achievement of a lowest cost solution, shall be
deemed to either excuse compliance with any more stringent standard set forth
above or comply with the general standards set forth in clauses (iv) and (v).
|  | (b) | Architectural, engineering, and design services shall be procured
from licensed, independent professionals retained directly or indirectly by
Concessionaire or furnished by licensed employees of Concessionaire to the
extent required by applicable law.
| 3.03 | Nature of Parties’ Interests under the Comprehensive Agreement
The Comprehensive Agreement shall not grant to Concessionaire any fee title,
leasehold estate, easement, or other real property interest of any kind in or to the
| Project or the Project right of way. |  |  | Concessionaire’s interests under the
Comprehensive Agreement shall be limited to the Permit described in Section
4.01.
4 | Grant of Permit and Term
| 4.01 | Grant of Permit
Subject to the terms and conditions of the Comprehensive Agreement,
Concessionaire shall have the exclusive right, and the Concessionaire accepts the
obligation: (i) to finance, develop, design, and construct the Project and (ii) from
and after the commencement of public operations of the Project (“Service
Commencement”) and until the end of the Term (as defined below), to manage,
Page 3 of 23
operate, maintain, and improve the Project and to establish, impose, charge,
collect, use, and enforce payment of tolls and related charges (the “Permit”).
| 4.02 | Term of the Comprehensive Agreement
|  | (a) | The Comprehensive Agreement shall take effect on the Agreement
Date and shall remain in effect until the date that is [__ years] from the
Agreement Date, unless earlier terminated in accordance with the terms of the
| Comprehensive Agreement. |  | The “Agreement Date” shall mean the date upon
which the Comprehensive Agreement is executed by the Department and the
Concessionaire.
|  | (b) | The Term may be extended from time to time in accordance with
Section 13.01.
5 | Tolling | Per the terms of the Comprehensive Agreement
| 5.01 | General Requirements
| 5.02 | Toll Rates
| 5.03 | User Confidentiality
Concessionaire shall comply with all applicable law related to confidentiality and
privacy of users of the Project.
| 5.04 | Emergency Suspension of Tolls
6 | Payments to the Department |  | Per the terms of the Comprehensive Agreement
7 | Project Finance
| 7.01 | Concessionaire Financing
|  | (a) | Concessionaire shall be solely responsible for developing a
financial plan and seeking approval from the Department for all aspects of the
financial plan prior to the Agreement Date.
|  | (b) | Concessionaire shall be solely responsible for obtaining any
financing for the development, design, construction, operation, and maintenance
of the Project and the Department shall have no responsibility to meet
Concessionaire’s debt service or payment obligations on any financing obtained
by Concessionaire.
| 7.02 | Financing Assignments
|  | (a) | Per the terms of the Comprehensive Agreement.
Page 4 of 23
| 7.03 | Lender’s Rights and Obligations Relating to Concessionaire Default
|  | (a) | Per the terms of the Comprehensive Agreement.
| 7.04 | Restrictions on Assignment and Transfers
|  | (a) | Per the terms of the Comprehensive Agreement.
8 | Design and Construction
| 8.01 | General Obligations of Concessionaire
|  | (a) | Concessionaire shall perform, or cause to be performed, all design
and construction services and provide all materials, equipment, tools, and labor
necessary to complete the construction of the Project as specified in the scope of
work, together with any Project Enhancements directed or approved by the
| Department (the “Design-Build Services”). |  |  | Design-Build Services shall be
provided at Concessionaire’s sole cost and expense, except as otherwise specified
by the Comprehensive Agreement.
|  | (b) | All development services shall comply with the Standard of Care;
|  | (c) | Concessionaire shall achieve substantial completion not later than
per the terms of the Comprehensive Agreement.
|  | (d) | If the Concessionaire has not achieved Substantial Completion by
the Guaranteed Substantial Completion Date, the Concessionaire shall continue to
perform the Design-Build Services so as to achieve substantial completion within
[24 months] of the Guaranteed Substantial Completion Date (“Outside Substantial
Completion Date”).
| 8.02 | Conditions Precedent to Work
Per the terms of the Comprehensive Agreement
| 8.03 | Quality Management
|  | (a) | Concessionaire shall perform all quality assurance and quality
control activities necessary for the work in accordance with the Technical
Requirements (and specifically the Department’s guidance document entitled,
Minimum Quality Control & Quality Assurance Requirements for Design-Build
& Public-Private Transportation Act Projects).
Page 5 of 23
| (b) | Concessionaire shall require that all of its subcontractors comply
with this Section 8.03.
| (c) | Concessionaire shall certify that all submittals have been
completed in compliance with the requirements of the Comprehensive
Agreement.
8.04 | Design-Build Contract and Amendments
| (a) | Per the terms of the Comprehensive Agreement.
8.05 | Project Design and Construction Documentation
| (a) | Per the terms of the Comprehensive Agreement.
8.06 | Project Schedule
An initial baseline schedule shall be attached to the Comprehensive Agreement
and serve as the basis for monitoring Concessionaire’s performance of the work
until such time as a baseline schedule has been submitted to and approved by the
Department in accordance with the Technical Requirements.
8.07 | Regulatory Approval
| (a) | Except as provided in Section 8.07(b) below, Concessionaire, at its
sole cost and expense, shall obtain and maintain in full force and effect and
comply with all regulatory approvals necessary for the work. |  |  | Responsibility for
obtaining regulatory approvals necessitated by a Department Change or a Project
Enhancement shall be as specified in the accompanying change order.
| (b) | The Department has completed an environmental review in
accordance with the NEPA, on behalf of the FHWA. The FHWA has issued a
Record of Decision. |  | Concessionaire shall comply with the requirements of the
NEPA documents.
8.08 | Acquisition of Right of Way and Utility Relocations
| (a) | Concessionaire, at its sole cost and expense, shall acquire all
Project right of way and shall perform or cause to be performed all activities and
services necessary for the acquisition of all Project right of way and utility
relocations necessary for construction of the Project.
| (b) | All right of way shall be acquired in the name of the state.
Page 6 of 23
| (c) | Concessionaire shall use its best efforts to settle claims with
landowners amicably. |  |  | If, despite Concessionaire’s best efforts, it is unable to
reach agreement with landowners within 90 days, the Department will undertake
any necessary condemnation proceedings. |  |  | Concessionaire shall reimburse the
Department for all costs incurred by the Department in pursing condemnation.
| (d) | The Department will reasonably assist Concessionaire in obtaining
the benefit of all rights the Department has under any current utility easement,
permit, or other right in real property relating to utility relocations.
8.09 | Latent Defects in Existing Assets
[Not applicable]
8.10 | Transportation Management Plan
| (a) | Per the terms of the Comprehensive Agreement.
8.11 | Revisions to the Technical Requirements
Prior to Substantial Completion, the Department may revise the Technical
Requirements pursuant to a Department Change. |  |  |  | Following Substantial
Completion, the Department may, with 30 days’ prior notice to Concessionaire,
revise the Technical Requirements to be consistent with the evolution of
regulations, materials, and best practices on similar limited access facilities. |  |  |  |  | Any
such revision will not be a Compensation Event.
8.12 | Deviations from Technical Requirements
| (a) | Per the terms of the Comprehensive Agreement.
8.13 | Substantial Completion, Final Acceptance, and Damages for Late
Completion
| (a) | Per the terms of the Comprehensive Agreement.
8.14 | Warranties; Defective Design and Construction
| (a) | Concessionaire warrants to the Department that:
|  | (i) | all construction work, including all materials and
equipment furnished as part of the construction work, is new, of good
quality, free of defects, and will be fit for its intended purpose; and
|  | (ii) | the Design-Build Services conform to the Standard of Care.
Page 7 of 23
|  | (b) | In the event of the occurrence of a defect or deficiency in the work,
the Concessionaire shall promptly rectify such defect or deficiency in the
work at Concessionaire’s sole cost and expense throughout the course of
the operating period of the Comprehensive Agreement.
| 8.15 | Performance Security Per the terms of the Comprehensive Agreement
| 8.16 | Project Recovery Schedule
|  | (a) | Per the terms of the Comprehensive Agreement
9 | Operations and Maintenance
| 9.01 | General Responsibilities
|  | (a) | Concessionaire shall perform, or cause to be performed, all
operation and maintenance [O&M] services for the Project at Concessionaire’s
sole cost and expense.
|  | (b) | O&M Services shall comply with the Standard of Care.
| 9.02 | Service Commencement
Concessionaire shall not commence the O&M Services unless and until all
conditions precedent to service commencement as defined in the Comprehensive
| Agreement have been satisfied or waived by the Department. |  |  | Such conditions
precedent shall include the following:
|  | (a) | substantial completion of the construction work;
|  | (b) | issuance of all regulatory approvals necessary to commence
operations; and
|  | (c) | procurement of all required insurance per the terms of the
Comprehensive Agreement.
| 9.03 | O&M Contractor
|  | (a) | Per the terms of the Comprehensive Agreement.
| 9.04 | Annual Budget
|  | (a) | Per the terms of the Comprehensive Agreement
Page 8 of 23
| 9.05 | Maintenance
|  | (a) | Concessionaire shall perform all routine maintenance and the
repair, renewal, reconstruction, and replacement of any portion or component of
the Project (“Major Maintenance”) in accordance with the Technical
Requirements.
|  | (b) | Per the terms of the Comprehensive Agreement.
| 9.06 | Traffic Patrol and Law Enforcement
|  | (a) | The Department shall cause the Virginia State Police to provide
police services, including traffic patrol and law enforcement services, and
emergency services to the Project at a level of service equivalent to that provided
on comparable state highways from time to time.
|  | (b) | Concessionaire shall not engage or permit the engagement of
private security services to provide traffic patrol or traffic law enforcement
services on the Project.
| 9.07 | Handback
Per the terms of the Comprehensive Agreement
10 | Project Oversight
| 10.01 | Department Oversight
Refer to Section 3.01
11 | Performance Point System
| 11.01 | Description of the Performance Point System
|  | (a) | The Department shall use a performance point system to monitor
| Concessionaire’s performance levels following service commencement. |  |  | The
Comprehensive Agreement shall identify certain Concessionaire acts, omissions,
breaches, or failures to perform its obligations that may result in the assessment
| by the Department of performance points (“Performance Shortfalls”). |  |  | The
accumulation of performance points by Concessionaire may trigger the remedies
set forth or referenced per the terms of the Comprehensive Agreement.
|  | (b) | The specific process by which performance points may be
assessed, as well as other general terms and conditions applicable to the
performance point system, will be set forth in the Comprehensive Agreement.
Page 9 of 23
| 11.02 | Assessment of Performance Points
|  | (a) | Per the terms of the Comprehensive Agreement.
12 | Change Orders, Safety Compliance Orders, and Project Enhancements
| 12.01 | Change Orders
|  | (a) | The Department may require a change to Concessionaire’s scope
of work (“Department Change”) pursuant to a change order executed by both
| parties or a directive letter executed by the Department. |  |  | The costs of
implementing a Department Change shall be borne by the Department unless
otherwise agreed by the parties.
|  | (b) | If the Department desires to initiate a Department Change, the
| Department shall deliver to Concessionaire a request for change proposal. |  |  |  | The
request for change proposal will set forth the details of the proposed Department
| Change. | Within 21 days following Concessionaire’s receipt of the request for
change proposal, Concessionaire shall provide the Department with a preliminary
written response, which includes an estimate of the cost of implementing the
| proposed Department Change. |  | Within 60 days after its receipt of the preliminary
written response, the Department may request Concessionaire to prepare and
submit a definitive proposal (“Change Proposal”), which Concessionaire shall
| submit within 60 days of such request. |  | The Change Proposal shall include,
among other things: a detailed estimate of the cost of implementing the proposed
Department Change; the anticipated effect that such proposed Department Change
would have on the baseline schedule, operating revenues, and traffic volumes and
| traffic flow; and the estimated damages to Concessionaire (if any). |  |  | Within 21
days following its receipt of the Change Proposal, the Department shall provide a
preliminary written response as to whether it intends to proceed with the proposed
| Department Change. |  | Within 60 days thereafter, the Department and
Concessionaire shall negotiate a mutually-acceptable change order.
|  | (c) | The Department may deliver to Concessionaire a directive letter
directing Concessionaire to proceed to implement a Department Change at the
Department’s cost on a force account basis as provided in the Technical
Requirements.
| 12.02 | Safety Compliance Orders
|  | (a) | Per the terms of the Comprehensive Agreement.
| 12.03 | Project Enhancements
|  | (a) | Either the Department or Concessionaire may propose to undertake
any additions to, or major modifications of, the Project following service
Page 10 of 23
commencement (“Project Enhancements), subject to the terms or conditions set
forth in the Comprehensive Agreement.
13 | Delay Events, Compensation Events, and Force Majeure
| 13.01 | Delay Events
|  | (a) | If a Delay Event (as in Section 13.01(b)) occurs during the Term,
the Concessionaire may be entitled to an adjustment to the Term, including an
extension of the period required for completion of the Design-Build Services or
an extension of the period for completion of the O&M Services, as applicable.
|  | (b) | Delay Events prior to service commencement that may extend the
period required for completion of the Design-Build Services include the
following:
|  |  | (i) | the implementation of a change order;
|  |  | (ii) | a Force Majeure Event (as defined in Section 13.03);
|  |  | (iii) | discovery of any of the following conditions on the Project
right of way during the Development Period:
|  |  |  | (A) | differing subsurface conditions;
|  |  |  | (B) | unforeseen threatened or endangered species;
|  |  |  | (C) | unforeseen archaeological, paleontological, or
cultural resources; or
|  |  |  | (D) | unforeseen hazardous substances; and
|  |  |  | (E) | unknown utilities.
|  |  | (iv) | a failure to obtain, or a delay in obtaining, any regulatory
approval (provided that such failure or delay could not have been
reasonably avoided or prevented by Concessionaire or its subcontractors);
|  |  | (v) | a change in federal or state law occurring after the
Agreement Date that imposes additional requirements that directly
materially adversely impact performance of the Design-Build Services and
that could not have been reasonably anticipated by a reasonable
contractor; or
Page 11 of 23
|  | (vi) | an injunction or other legal proceeding enjoining or
estopping either the Department or Concessionaire from the performance
of its obligations under the Comprehensive Agreement.
| (c) | Delay Events following service commencement that may extend
the period for completion of the O&M Services include the following:
|  | (i) | a Force Majeure Event (as defined in Section 13.03);
|  | (ii) | a change in federal or state law occurring after the
Agreement Date that imposes additional requirements that directly
materially adversely impact performance of the Design and Construction
Services and that could not have been reasonably anticipated by a
reasonable contractor;
|  | (iii) | a change in state law that has the effect of discriminating
against Concessionaire or the Project, except where such change in state
law is in response to any act or omission on the part of Concessionaire that
is illegal (“Discriminatory Change in State Law”);
|  | (iv) | the implementation of any change order or Project
Enhancement;
|  | (v) | the implementation of a Safety Compliance Order;
|  | (vi) | an injunction or other legal proceeding enjoining or
estopping either the Department or Concessionaire from the performance
of its obligations under the Comprehensive Agreement:
|  | (vii) | Department Caused Delays
| (d) | If Concessionaire experiences a Delay Event, it must submit
written notice to the Department within 30 days following the date on which
Concessionaire first became aware that a Delay Event occurred. |  |  |  | If
Concessionaire fails to submit the notice within that 30 day period, it shall waive
its right to an extension of time. |  |  | The notice shall include the information
specified by the Comprehensive Agreement, which shall include a time impact
analysis demonstrating the impact of the Delay Event to the Project schedule.
13.02 | Compensation Events
| (a) | If a Compensation Event (as defined below) occurs during the
Term, the Concessionaire may be entitled to damages or the Department may be
entitled to positive net cash flows created by such an event.
| (b) | Compensation Events include:
Page 12 of 23
| (i) | the implementation of a change order or Project
Enhancement;
| (ii) | Discriminatory Change in State Law;
| (iii) | [intentionally deleted]; or
| (iv) | Department Caused Delay, as set forth in more detail
below;
| (v) | discovery of any of the following conditions on the Project
right of way during the development period;
|  | (A) | differing subsurface conditions;
|  | (B) | unforeseen threatened or endangered species;
|  | (C) | unforeseen archaeological, paleontological, or
cultural resources; or
|  | (D) | unforeseen hazardous substances.
| (vi) | Department Changes.
(c) | If the Concessionaire is affected by a Compensation Event, it shall
give written notice to the Department within 30 days following the date on which
the Concessionaire first became aware (or should have been aware, using all
reasonable due diligence) that an event has occurred and that it is or will become
a Compensation Event (a “Compensation Event Notice”). |  |  |  | The Compensation
Event Notice shall set forth (i) the Compensation Event and its date of occurrence
in reasonable detail, (ii) the amount claimed as the Concessionaire Damages, and
(iii) details of the calculation thereof including a written analysis and calculation
of the estimated net cost impact, if any, and estimated net revenue impact, if any.
(d) | If, for any reason, the Concessionaire fails to deliver such written
Compensation Event Notice within the foregoing time period, the Concessionaire
shall be deemed to have irrevocably and forever waived and released any Claim
or right to Concessionaire damages or other adverse effects on gross revenues or
on costs, expenses and liabilities attributable to such Compensation Event.
(e) | If the Department determines the Concessionaire is entitled to cost
relief for Department Caused Delay or Department Changes the Concessionaire
shall be entitled to recover from the Department only the direct costs reasonably
and necessarily incurred by the Design Build Contractor as a direct result of the
Page 13 of 23
Department Caused Delay or Department Changes. However, under no
circumstances will such recoverable costs include home office overhead incurred
by the Design Build Contractor’s member companies, nor net revenue impacts nor
financing costs.
| (f) | If the Department determines the Concessionaire is entitled to cost
relief for the implementation of a change order or Project Enhancement,
Discriminatory Change in State Law, differing subsurface conditions, unforeseen
threatened or endangered species, unforeseen archaeological, paleontological, or
cultural resources, or unforeseen hazardous substances the Concessionaire may
request an extension of the Term as necessary to recoup its net cost impacts
and/or net revenue impacts. The Department has no liability for compensation due
to the Compensation Events noted above.
13.03 | Force Majeure Events
| (a) | Force Majeure Event means any of the following acts of nature or
people that can neither be anticipated nor controlled: earthquakes that cause
ground accelerations in excess of the AASHTO bridge design standards for the
site of the Project, floods in excess of the base flood (as defined in the
Department’s Division I Amendment), hurricane force winds, tornados, epidemic
disease declared by US federal government, quarantine restriction of critical
personnel or materials, adverse conflict by or among armed forces, acts of terror,
maritime blockade, |  |  | nuclear or other explosion, radioactive or chemical
contamination or ionizing radiation, riot or other public disorder, industry-wide or
regional strikes or labor disputes, and governmental embargo. |  |  |  | An event is not a
Force Majeure Event if such event is otherwise specifically dealt with in the
Comprehensive Agreement or arises by reason of:
|  | (i) | the negligence or misconduct of Concessionaire or its
subcontractors;
|  | (ii) | any act or omission by Concessionaire or its subcontractors
in breach of the provisions of the Comprehensive Agreement;
|  | (iii) | any defect or deficiency in the design or construction of the
Project;
|  | (iv) | lack or insufficiency of funds or failure to make payment of
monies or provide required security on the part of Concessionaire or its
subcontractors;
|  | (v) | any strike, labor dispute or labor protest directed solely at
Concessionaire or its subcontractors or caused by or attributable to any act
(including any pricing or other practice or method of operation) or
omission of Concessionaire or its subcontractors;
Page 14 of 23
|  | (vi) | damage to the Project caused by an earthquake that causes
ground accelerations in excess of the AASHTO bridge design standards for the
site of the Project, floods in excess of the base flood (as defined in the
Department’s Division I Amendment), hurricane force winds, or tornados if such
damage would not have occurred but for the Project’s failure to have been
designed or constructed in accordance with the Technical Requirements.
| (b) | It is specifically understood that other than earthquakes causing
ground acceleration in excess of the AASHTO bridge design standards for the site
of the Project, floods in excess of the base flood (as defined in the Department’s
Division I Amendment), hurricane force winds or tornadoes, the Concessionaire
shall assume the risk and other weather or conditions resulting from weather shall
not constitute a Force Majeure Event.
| (c) | If a Force Majeure Event occurs after service commencement
which has the effect of causing physical damage or destruction to the Project or a
portion thereof and results in a substantial reduction in Concessionaire’s toll
revenues for a period in excess of 180 consecutive days (a “Significant Force
Majeure Event”), Concessionaire shall provide the Department with a plan for
restoring the Project before the end of the Term. |  |  |  | If the Department determines in
its sole discretion that the Project cannot be restored, the Department may
terminate the Comprehensive Agreement pursuant to Section 20.05. |  |  |  | If
Concessionaire restores the Project, the Department and Concessionaire shall
negotiate an appropriate extension of the Term.
13.04 | Department Caused Delay
(a) Department Caused Delay means a material breach or an inexcusable
delay by the Department in performing any of its obligations during the design-
build period of the development of the Project, and which material breach or an
inexcusable delay by the Department causes the Design Build Contractor a
material increase of its construction costs or a material impact to the critical path
which delays the Guaranteed Substantial Completion Date described in the
Comprehensive Agreement.
For the purposes of this Section, an “inexcusable delay” shall mean a
delay that is attributable solely to error or omission of the Department, and an
inexcusable delay or a material breach specifically excludes delay or breach
attributable to: (a) the submission of incomplete documentation for the
Department’s review, (b) required review or approvals from other Governmental
Authorities necessary or appropriate to the Department’s review, (c) failure to
obtain appropriation and allocation of public funds, (d) consumption of available
float, (e) submittals or requests that are "deemed approved" if no response is
provided within the minimum required response period [typically 21 days], or (f)
Force Majeure Events.
Page 15 of 23
(b) The Concessionaire shall submit its request for Change Order within
30 days after the occurrence of any Department Caused Delay giving rise to the
request for adjustment or relief. The request for Change Order shall include
sufficient information to advise Department of the circumstances giving rise to
the request for adjustment, the amount of adjustment requested and the basis of
such request.
(c) not used
(d) The Concessionaire’s request for Change Order due to Department
Caused Delay may include the price escalation for materials only if the event
causes the Guaranteed Substantial Completion Date to be delayed by at least one
year and such delay is not attributable to the actions or negligence of the
Concessionaire, a Concessionaire Party, or the Design-Build Contractor.
(e) The Department may extend the Guaranteed Substantial Completion
Date only if its delay results in a material impact to the critical path set forth in
the Baseline Schedule.
(f) If for any reason the Concessionaire fails to deliver the request for
Change Order within the time period specified above, the Concessionaire shall be
deemed to have irrevocably and forever waived and released any Claim or right to
cost or schedule relief attributable to any such alleged Department Caused Delay.
(g) If the Department grants to the Concessionaire cost relief, schedule
relief, or both, the Concessionaire shall pass such relief to the Design Build
Contractor pursuant to the terms of the Design-Build Contract.
14 | Hazardous Substances
| 14.01 | Concessionaire’s Responsibility
Concessionaire shall be fully responsible for the the management, handling,
treatment, remediation, removal, transport (where applicable), and disposal of all
hazardous substances, including but not limited to, hazardous substances that
were introduced to the Project or caused by Concessionaire or those whose acts
for which Concessionaire is responsible, or that are discovered on the Project
right of way, in accordance with applicable law and regulatory approvals. The
Concessionaire shall be fully responsible for the costs of the work contemplated
in this Section, except to the extent such work qualifies as a Compensation Event
pursuant to Section 13.02. Hazardous substances that were introduced to the
Project or caused by Concessionaire or those whose acts for which
Concessionaire is responsible shall not be a basis for Delay Events or
Compensation Events.
| 14.02 | Reserved
Page 16 of 23
| 14.03 | Concessionaire’s Indemnity for Hazardous Substances
|  | (a) | Concessionaire shall indemnify, defend, and hold harmless each
State Indemnitee (as defined in Section 15(a) below) from and against all claims,
losses, damages, liabilities, and expenses, including attorneys’ fees and expenses,
arising out of or resulting from:
|  |  | (i) | those hazardous substances introduced to the Project right
of way by Concessionaire, its contractors, its subcontractors, or anyone for
whose acts they may be liable;
|  |  | (ii) | the spreading, migration, release, remediation, storing,
transportation, or disposal of Pre-Existing Hazardous Substances by
Concessionaire, its contractors, its subcontractors, or anyone for whose
acts they may be liable; and
|  |  | (iii) | exacerbation, due to negligence, recklessness, or willful
misconduct of Concessionaire, its contractors, its subcontractors, or
anyone for whose acts they may be liable, of the release, spreading,
migration, or toxicity of hazardous substances on or within the Project
right of way.
15 | Indemnification
| (a) | Concessionaire shall indemnify, defend, and hold harmless the
Department, the Commonwealth Transportation Commissioner, the Commonwealth
Transportation Board, the state, and their respective representatives (“State Indemnitee”)
from and against any losses actually suffered or incurred by such State Indemnitee
(except to the extent such Losses are caused by the negligence or willful misconduct of
such State Indemnitee), due to third party claims that are based upon, arise out of, relate
to, are occasioned by or are attributable to:
|  | (i) | any failure by the Concessionaire to comply with, observe or
perform any of the covenants, obligations, agreements, terms or conditions in the
Comprehensive Agreement or, any breach by the Concessionaire of its
representations or warranties set forth herein;
|  | (ii) | any actual or alleged misconduct, negligence or other culpable act,
error or omission of a Concessionaire Party in connection with the Project;
|  | (iii) | any actual or alleged patent or copyright infringement or other
actual or alleged improper appropriation or use of trade secrets, patents,
proprietary information, know-how, trade marked or service marked materials,
equipment, devices or processes, copyright rights or inventions by a
Page 17 of 23
Concessionaire or any of its contractors or suppliers in connection with the
Project;
|  | (iv) | inverse condemnation, trespass, nuisance or similar taking of or
harm to real property committed or caused by a Concessionaire or any of its
contractors or suppliers in connection with the Project;
|  | (v) | any tax attributable to any transfer of the Concessionaire’s interest
or any part thereof; or
|  | (vi) | any claim for brokerage commissions, fees or other-compensation
by any person who acted on behalf of the Concessionaire, its affiliates, or their
respective representatives in connection with the Comprehensive Agreement, any
transfer of the Concessionaire’s interest, or any part thereof.
| (b) | The indemnities of the Concessionaire shall survive the expiration or
termination of the Comprehensive Agreement and any other Project agreements to which
the Concessionaire is a party and shall continue for six years following the expiration or
termination of the Comprehensive Agreement; provided, that such six-year limitation on
survival shall not apply in the event of fraud or a material misrepresentation with respect
to a particular covenant, agreement, representation or warranty, and, provided further,
that additional indemnification agreements shall be as provided in any Contract and any
other Project agreement to which the Concessionaire becomes a party. |  |  |  | Notwithstanding
the foregoing, the Concessionaire’s indemnification of any State Indemnitee shall be
limited solely to its obligations under the Comprehensive Agreement and any other
Project agreements to which the Concessionaire becomes a party.
| (c) | If a State Indemnitee is enjoined from the operation or use of the Project
as a result of any patent or copyright suit, claim or proceeding, Concessionaire at its sole
cost and expense shall take reasonable steps to procure the right to operate or use the
Project.
16 | Insurance |  | Per the terms of the Comprehensive Agreement
17 | Ownership and Access to Records
| 17.01 | Ownership of Work Product
Per the terms of the Comprehensive Agreement
| 17.02 | Access to Records
|  | (a) | Without limiting any statutory or legal rights, the Department, its
representatives, and any governmental entity allowed access under law, at all
reasonable times and upon advance notice, shall have the right to audit, inspect
Page 18 of 23
and copy all records and documents produced or maintained by Concessionaire
| related to the Project. | Any records and documents furnished to the Department
shall be subject to the Virginia Freedom of Information Act.
| (b) | All records and documents shall be maintained in an organized
fashion, use accounting and control systems in accordance with Generally
Accepted Accounting Principles (“GAAP”), and comply with applicable law,
including federal funding requirements.
| (c) | The Department and the state shall have the right to carry out an
audit of information relating to (i) the design, construction, operation,
maintenance, and repair of the Project or (ii) other information required to be
maintained or delivered by Concessionaire pursuant to the Comprehensive
| Agreement. | Such audit may extend, without limitation, to calculations
undertaken and financial or business reports provided by or on behalf of
Concessionaire.
| (d) | Concessionaire shall maintain all financial and cost accounts, pay
administration, and acquisition and supply records in accordance with records
| retention requirements defined the Federal Acquisition Regulation (“FAR”). |  |  | At
the Department’s request, Concessionaire shall furnish or cause to be furnished to
the Department such information relating to the operation, maintenance, and
repair of the Project as the Department may reasonably request for any purpose
related to the Project and as shall be in the possession and control of
Concessionaire or its subcontractors or consultants.
| (e) | If a federal action is required by a federal agency, Concessionaire
shall make all its Project records available to the agency for inspection and audit
at the agency’s request.
| (f) | In addition, Concessionaire, at its sole cost and expense, shall
cause a reputable independent auditor to annually audit Concessionaire’s books
| and records relating to the Project according to GAAP. |  | Concessionaire shall
cause the independent auditor to deliver the audit report to the Department
promptly after it is completed, but in any event within 120 days of the end of each
of Concessionaire’s fiscal years.
18 | Escrowed Documents | Per the terms of the Comprehensive Agreement
19 | Default and Remedies | Per the terms of the Comprehensive Agreement
20 | Termination and Project Value | Per the terms of the Comprehensive Agreement
Page 19 of 23
21 | Dispute Resolution
| 21.01 | Procedure
|  | (a) | The parties shall attempt to resolve any disputes arising out of the
Comprehensive Agreement at the Project level, through good-faith negotiations
| between designated representatives. |  | If the dispute cannot be resolved at the
Project level, the parties’ senior management representatives shall meet at the
request of either party within a time as set forth in the Comprehensive Agreement
in an attempt to resolve the dispute.
|  | (b) | If the parties’ senior management cannot resolve the dispute, then
| either party may request non-binding mediation. |  |  | Mediation generally shall be a
| condition precedent to instituting a legal action in court. |  |  | However, if the
Department determines, in its sole discretion, that a dispute involves an issue that
poses an immediate or serious threat to the public health, safety, or welfare, the
Department shall be entitled to take whatever steps it deems appropriate and to
initiate litigation of the matter in court without first submitting the dispute to the
dispute resolution procedure.
|  | (d) | All litigation between the parties arising out of or pertaining to the
Comprehensive Agreement shall be filed, heard, and decided in the Circuit Court
for the City of Richmond, Virginia, Division 1, which shall have exclusive
jurisdiction and venue.
|  | (e) | Each party shall bear its own attorneys’ fees and costs in any
dispute or litigation and no party shall seek or accept an award of attorneys’ fees
or costs.
| 21.02 | Duty to Proceed and Continue with Performance
Notwithstanding the existence of any dispute (except a dispute regarding the
cause for terminating the Comprehensive Agreement), Concessionaire shall
continue performance in accordance with the Comprehensive Agreement, or
otherwise as approved or directed by the Department, and the Department shall
perform its obligations under the Comprehensive Agreement.
22 | Reserved Rights Per the terms of the Comprehensive Agreement
23 | Representations and Warranties
The Comprehensive Agreement shall set forth representations and warranties
from both Concessionaire and the Department.
Page 20 of 23
24 | Contracting Practices
| 24.01 | Obligation to Refrain from Discrimination
Concessionaire covenants and agrees that it shall not discriminate and shall
require all contractors not to discriminate against any person, or group of persons,
on account of age, sex, marital status, race, creed, color, national origin, religion,
or sensory, mental, or physical handicap in the performing the work described in
the Comprehensive Agreement; provided that the prohibition against
discrimination on the basis of sensory, mental, or physical handicap shall not
apply if the particular disability prevents the proper performance of the particular
person involved.
| 24.02 | Subcontracting
|  | (a) | Concessionaire may perform its work under the Comprehensive
Agreement by subcontracting to persons with expertise, qualifications, and
| experience to perform the subcontracted work. |  |  |  | All subcontracts shall comply
| with the terms and conditions of the Comprehensive Agreement. |  |  |  | Concessionaire
shall remain fully responsible to the Department for performance of the work and
the acts and omissions of its subcontractors.
|  | (b) | Concessionaire shall not subcontract any part of its work to:
|  |  | (i) | any person then debarred or prohibited from participating
in state or federally-funded projects, or indicted, convicted, pled guilty or
nolo contendere to a violation of law involving fraud, conspiracy,
collusion, bribery, perjury, material misrepresentation, or any other
violation that shows similar lack of moral or ethical integrity;
|  |  | (ii) | a subcontractor (with the exception of contract specialty
items, consultants, manufacturers, suppliers, or haulers) that is not pre-
qualified with the Department; or
|  |  | (iii) | an affiliate, except as provided in Section 24.03.
| 24.03 | Affiliate Contracts
Concessionaire shall not enter into or materially amend a subcontract with an
affiliate without prior notice to and consent of the Department, which consent
shall not be unreasonably withheld or delayed if the subcontract is entered into in
the ordinary course of business and Concessionaire demonstrates to the
Department that the contract or subcontract is on overall terms no less favorable
to Concessionaire than terms the Concessionaire could obtain in an arm’s length
transaction.
Page 21 of 23
| 24.04 | Small, Women-Owned and Minority Business and Disadvantaged
Business Enterprise Reporting
|  | (a) | Concessionaire shall use good faith efforts to achieve the following
goals in performing the Design-Build Services: [__% DBE participation and __%
SWaM participation, such percentages relating to the value of the design-build
contract totaling an aggregate goal of 40% of the value of the design-build
contract].
|  | (b) | Concessionaire shall use good faith efforts to achieve the following
goals in performing the O&M Services: [__% DBE participation and __% SWaM
participation totaling an aggregate goal of 40% of the value of the O&M
Services].
|  | (c) | If the Department determines Concessionaire or its affiliates
(including the design-build contractor and O&M contractor), neither achieves the
goals described in Sections 24.04(a) and (b) above nor demonstrates good faith
efforts, Concessionaire and/or its affiliates may be enjoined or disqualified from
additional work or new contracts with the state, in accordance with current
policies and procedures.
25 | Miscellaneous
| 25.01 | Consequential Damages Waiver
|  | (a) | Except for damages expressly allowed under the Comprehensive
Agreement, neither party shall be liable, whether as a result of breach of contract,
breach of warranty, tort liability (including negligence or strict liability), or
otherwise, for special, indirect, or consequential damages of any nature
whatsoever.
|  | (b) | The consequential damages waiver described in Section 24.01(a)
shall not apply to the following:
|  |  | (i) | indemnification obligations relating to third-party claims;
|  |  | (ii) | recovery of any liquidated damages expressly provided for
in the Comprehensive Agreement;
|  |  | (iii) | recovery of concessionaire damages expressly provided for
in the Comprehensive Agreement;
|  |  | (iv) | recovery of termination damages expressly provided for in
the Comprehensive Agreement;
Page 22 of 23
| (v) | damages arising out of fraud or intentional
misrepresentation;
| (vi) | damages covered by insurance required under the
Comprehensive Agreement.
25.02 | State Allocation of Funds
The Department’s payment of any amounts due and owing by the Department to
Concessionaire under the Comprehensive Agreement shall be subject to
appropriations by the General Assembly and allocation by the CTB.
[THE REMAINDER OF THIS PAGE INTENTIONALLY LEFT BLANK]
Page 23 of 23
APPENDIX G
CONCEPTUAL FINANCIAL PLAN PRO FORMA
All values in millions of USD
NPV figures discounted to January 1, 2010
Income Statement - NPV @ 5%
Revenue
O&M costs
EBITDA
Depreciation
Financing costs
Profit before interest and tax
Net interest
State Tax (paid) / refunded
Federal Tax (paid) / refunded
Profit after tax
Dividends
Retained earnings
Cash Flow Summary - NPV @ 5%
Revenues
Construction
O&M
Lifecycle
Debt costs
Equity costs
Taxes
(Required Public Funds) / Concession Payment
Percentage of Truck Revenue
Percentage of Truck Traffic
Average Initial Truck Toll Rate
Average Initial Car Toll Rate
Maximum Annual Toll Escalation Rate
Cost of debt
Equity IRR (post tax)
Project IRR (post tax, proxy for WACC)
APPENDIX G
CONCEPTUAL FINANCIAL PLAN PRO FORMA
All values in millions of USD
NPV figures discounted to January 1, 2010
Income Statement - Nominal
Revenue
O&M costs
EBITDA
Depreciation
Financing costs
Profit before interest and tax
Net interest
State Tax (paid) / refunded
Federal Tax (paid) / refunded
Profit after tax
Dividends
Retained earnings
Cash Flow Summary - Nominal
Revenues
Construction
O&M
Lifecycle
Debt costs
Equity costs
Taxes
(Required Public Funds) / Concession Payment
Percentage of Truck Revenue
Percentage of Truck Traffic
Average Initial Truck Toll Rate
Average Initial Car Toll Rate
Maximum Annual Toll Escalation Rate
Cost of debt
Equity IRR (post tax)
Project IRR (post tax, proxy for WACC)

## Page 1
Name: “Table 1 of 1 on page 1 of 71”
Table: 1
Vi rgi n ia Dep a rt men t of
Tra nspo rt at ion
SOLICITATION FOR CONCEPTUAL
PROPOSALS
U.S. Route 460 Corridor Improvements Project
through the
Public-Private Transportation Act
May 5, 2010

## Page 2
Name: “Table 1 of 1 on page 2 of 71”
Table: 2
TABLE OF CONTENTS
1 | EXECUTIVE SUMMARY .............................................................................................. 3
1.1 | Introduction..................................................................................................................... 3
1.2 | Purpose............................................................................................................................ 3
1.3 | Project Objectives ........................................................................................................... 4
1.4 | Document Disclosure...................................................................................................... 4
1.5 | Legislative Authority for the Project .............................................................................. 4
1.6 | Procurement Process....................................................................................................... 4
2 | BACKGROUND ............................................................................................................... 6
2.1 | Introduction..................................................................................................................... 6
2.2 | Project Information ......................................................................................................... 6
2.3 | Map of Project................................................................................................................. 6
2.4 | Progress to Date .............................................................................................................. 6
3 | PROJECT SCOPE............................................................................................................ 8
3.1 | Project Requirements ...................................................................................................... 8
| 3.1.1 | Key Assumptions ....................................................................................... 8
| 3.1.2 | Route 460 ................................................................................................... 9
| 3.1.3 | Tolling......................................................................................................... 9
3.2 | Regulatory Approvals ..................................................................................................... 9
4 | GENERAL PROCEDURES AND REQUIREMENTS............................................... 11
4.1 | Short Listing.................................................................................................................. 11
4.2 | Schedule........................................................................................................................ 11
4.3 | VDOT’s Point of Contact and Project Reference ......................................................... 11
4.4 | Advertising the SFP ...................................................................................................... 12
4.5 | SFP Information............................................................................................................ 12
4.6 | Pre-Submittal Responsibilities...................................................................................... 13
4.7 | Delivery of Proposal ..................................................................................................... 13
4.8 | Format of Proposal........................................................................................................ 14
4.9 | Formal Presentation and Interviews.............................................................................. 15
5 | QUESTIONS AND CLARIFICATIONS ..................................................................... 16
6 | RIGHTS AND OBLIGATIONS OF VDOT................................................................. 17
6.1 | Specific Rights and Obligations of VDOT ................................................................... 17
6.2 | Assumption of Liability ................................................................................................ 18
7 | COMPREHENSIVE AGREEMENT – MATERIAL TERMS .................................. 20
8 | MISCELLANEOUS ....................................................................................................... 21
8.1 | Virginia Freedom of Information Act........................................................................... 21
8.2 | Requirement to Keep Team Intact ................................................................................ 22
8.3 | Disadvantaged Business Enterprises/Small, Women and Minority Owned |  | Businesses
22
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 3
Name: “Table 1 of 1 on page 3 of 71”
Table: 3
8.4 | Administrative Requirements ....................................................................................... 22
9 | CONFLICT OF INTEREST.......................................................................................... 25
9.1 | Conflict of Interest Determination ................................................................................ 25
9.2 | Ethics in Public Contracting Act................................................................................... 25
10 | CONTENTS OF CONCEPTUAL PROPOSAL .......................................................... 26
10.1 | Confidentiality .............................................................................................................. 26
10.2 | Letter of Submittal ........................................................................................................ 26
10.3 | Executive Summary ...................................................................................................... 27
10.4 | Conceptual Proposal Submittal Criteria........................................................................ 27
11 | EVALUATION PROCESS ............................................................................................ 33
11.1 | Evaluation Rating System............................................................................................. 33
APPENDICES
A | Definitions
B | Information Package Request Form
C | Certification Regarding Debarment
D | Work History Forms
E | Resume Form
F | Contract Term Sheet
G | Conceptual Financial Plan Pro Forma
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 4
Name: “Table 1 of 1 on page 4 of 71”
Table: 4
3
1 | EXECUTIVE SUMMARY
1.1 | Introduction
The U.S. Route 460 Corridor Improvements Project (Project) is located from the existing
U.S. Route 460 near its Interstate-295 interchange in Prince George County to a new
| interchange |  | with | the | U.S. | Route | 58 | bypass | in | the | City | of | Suffolk. | The | Project | is
comprised of approximately 55 miles of limited access, four-lane, divided highway along
a new alignment.
| In | accordance | with | the | Public-Private |  |  | Transportation |  |  | Act | of | 1995 | (the | “PPTA”), | as
amended, the Virginia Department of Transportation (VDOT) is hereby requesting the
submittal of Conceptual Proposals for the finance, design, construction, operation, and
maintenance of the Project.
Capitalized terms used in this Solicitation for Conceptual Proposals (SFP) are defined in
Appendix A. If a term is not specifically defined in Appendix A, then such term shall
have the definition ascribed to it in this SFP or the SFP Documents.
1.2 | Purpose
The purpose of this SFP is to:
|  | inform the industry of the Project;
|  | identify VDOT’s objectives and priorities for the Project’s delivery;
|  | set out the evaluation criteria and selection process to select the short listed Offerors;
and
|  | request submittal of Statements of Qualifications including a Conceptual Financial
Plan to enable VDOT to identify Offerors qualified to submit Detailed Proposals to
finance, design, construct, operate and maintain the Project.
Offerors must demonstrate their ability to undertake the development and operations of
| the | Project | within | a | legislative, |  | contractual |  | and |  | regulatory |  | environment |  | that | will
| necessitate |  | working | effectively |  | with |  | VDOT, | other |  | Responsible |  | Public |  | Entities, | the
community and other stakeholders.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 5
Name: “Table 1 of 1 on page 5 of 71”
Table: 5
4
1.3 | Project Objectives
VDOT is procuring this Project under the provisions of the PPTA to secure private sector
funds and offset the need for public allocations to fund the Work. A successful project
shall satisfy the following transportation objectives:
|  | Improve travel safety along the corridor;
|  | Create at new westbound emergency evacuation route for Hampton Roads;
|  | Accommodate increases in freight movements along the corridor; and
|  | Improve military strategic connectivity.
1.4 | Document Disclosure
| VDOT | shall | disclose | to | the | public, |  | in | accordance |  | with | the | Virginia | Freedom | of
Information Act, all information received in response to this SFP including any proposed
product, service, or idea for the Project that enhances or augments VDOT’s minimum
| requirements and/or project objectives, unless determined by VDOT to be exempt | [13 empty] | in
| accordance with Section 8.1 of this SFP. | [6 empty] | Noting VDOT’s intent to disclose, Offerors are
expected to submit Conceptual Proposals with no requests or very limited requests for
exceptions to disclosure.
1.5 | Legislative Authority for the Project
The PPTA is the legislative framework enabling the Commonwealth of Virginia (the
“Commonwealth”) to enter into agreements authorizing private entities to develop and/or
| operate | qualifying |  | transportation |  |  | facilities. |  |  | The | Commonwealth |  | of | Virginia | adopted
| Implementation |  | Guidelines |  | (Guidelines) |  |  | in |  | accordance | with | the | PPTA. | The | current
| Guidelines |  | were | revised |  | as | of | December |  |  | 2008 | and | are | available | at
http://www.virginiadot.org/business/ppta-Guidelines.asp. In accordance with § 56-556 et
seq. of the Code of Virginia, VDOT shall be the coordinating Responsible Public Entity
for the Project.
VDOT previously solicited conceptual proposals for this Project on February 15, 2006.
| VDOT | received | three | responses |  |  | to | that | earlier |  | solicitation. | VDOT |  | terminated | that
solicitation process on May 3, 2010.
1.6 | Procurement Process
| This | SFP | commences | the | first-phase |  |  | of | a | procurement | process. |  | The | following | is | a
summary of VDOT’s standard six-phase PPTA procurement process, which is defined in
detail in the Guidelines:
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 6
Name: “Table 1 of 1 on page 6 of 71”
Table: 6
5
1. | Phase | One |  | – |  | Quality |  | Control: |  | a | VDOT | level |  | review | to | determine |  | whether
| Conceptual |  |  | Proposals |  |  | meet |  | the | requirements |  |  | of | the | Law | and | the | Guidelines.
| Please |  | refer |  |  | to | VDOT’s |  | IPD |  | Memorandum |  |  | IPD |  | 05-02 | available |  | at
http://www.virginiadot.org/business/resources/IPD_Memorandum_05_02_0_dlh_
051206.pdf.
2. | Phase Two - Independent Review Panel (IRP): The IRP, which is appointed by
| the | Secretary |  |  |  | of | Transportation, |  |  |  | will | review | and |  | evaluate |  | the | Conceptual
Proposal(s) and provide a recommendation as to whether to advance one or more
of the Conceptual Proposal(s).
3. | Phase Three – Commonwealth Transportation Board (CTB) Approval: The CTB
will review the Conceptual Proposal(s), along with the IRP’s recommendation
and recommend that VDOT either reject the Conceptual Proposal(s) or seek a
Detailed Proposal from one or more of the Offerors.
4. | Phase Four – Submission and Selection of Detailed Proposals: Offerors advancing
| to | Phase | Four |  |  | will | be | requested |  | to | submit | Detailed |  |  | Proposals. |  | VDOT |  | shall
evaluate the Detailed Proposals and select none, one or more proposals by the
Commonwealth Transportation Commissioner for negotiation of an interim and/or
a comprehensive agreement.
5. | Phase | Five |  |  | – | Negotiation |  |  | of | interim | and/or |  | comprehensive |  |  |  | agreement: |  | The
| process |  | of |  | completing |  |  | negotiations |  |  | of | an | interim |  | and/or |  | comprehensive
agreement.
6. | Phase | Six |  | – | Execution |  |  | of | interim |  | and/or | comprehensive |  |  | agreement: |  |  | The | final
stage of review and includes the execution of an interim and/or comprehensive
agreement by the Commonwealth Transportation Commissioner and the selected
Offeror.
VDOT | will | issue |  | a | draft |  | Request |  | for | Detailed |  | Proposals |  | (RFDP) |  | to | the | short | listed
Offerors. |  | Prior to issuing a final RFDP, VDOT will host meetings with the short listed
Offerors with the intent of allowing further development of concepts and issues raised
during the preceding phases of the PPTA procurement process.
The Commonwealth Transportation Commissioner may decide to streamline this process
because | earlier |  | activities |  |  |  | have | included |  |  | substantial |  | public |  | information |  |  | and | public
involvement, including an Independent Review Panel.
While the RFDP will contain specific requirements for Detailed Proposals, as well as a
specific selection criteria process, VDOT anticipates that Detailed Proposals will include,
among other things, requirements for conceptual design plans, a financial plan, a tolling
schedule, |  | and | a | schedule |  |  | for | development, |  |  |  | construction, |  |  | and | implementation |  |  | of
operations and maintenance for the duration of the concession period. | [16 empty] | Based on the
responses to the RFDP, the Commonwealth Transportation Commissioner will make a
selection of a successful Offeror(s), if any, to initiate negotiations for an interim and/or
comprehensive agreement to finance, design, construct, operate and maintain the Project.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 7
Name: “Table 1 of 1 on page 7 of 71”
Table: 7
6
2 | BACKGROUND
2.1 | Introduction
| The | Project | contemplated |  | in | this | SFP | includes | the | construction |  | of | a | new | west-east
transportation link between the existing U.S. Route 460 near its interchange with I-295 in
| Prince | George | County | to | a | new | interchange |  | with | U.S. | Route | 58 | along | the | Suffolk
| Bypass. | The Project includes only minor adjustments to the existing I-295 interchange.
The adjustments to this interchange are minor realignments of two existing ramps, the
westbound U.S. Route 460 to I-295 northbound ramp and the northbound I-295 ramp to
| eastbound | U.S. | Route | 460. |  | The | Project | area | extends |  | approximately |  |  | 55 | miles | and
includes a four-lane divided, limited access highway along a new location.
The proposed improvements will include, among other things, new roadway, drainage,
| communications/intelligent |  |  |  | transportation |  |  | systems, | lighting, |  | flood | protection, |  |  | and | toll
collection facilities.
2.2 | Project Information
VDOT has developed information that may assist Offerors as they develop Conceptual
| Proposals. | Information |  | is |  | available |  | on | VDOT’s | external |  | project |  | website |  | at
| http://route460ppta.org/. |  |  | Additional information is available through the purchase of CD.
Instructions for purchase of the information package are included in Section 4.5.
2.3 | Map of Project
Several illustrations of the Project are included on the external project website at
http://route460ppta.org/.
2.4 | Progress to Date
An overview of the work undertaken by VDOT on the Project to date is briefly described
| below. | Note that all completed studies, reports, and documents referenced below are
provided on VDOT’s external project website at http://route460ppta.org/ or included in
the Information Package.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 8
Name: “Table 1 of 1 on page 8 of 71”
Table: 8
7
Environmental Studies
2005 | VDOT | completed |  |  | its | Draft | Environmental | Impact | Statement |  | (DEIS) |  | and
associated technical reports.
2008 | VDOT completed additional hazardous materials investigations (Phase I and
Phase II Environmental Site Assessments) (Information Package)
2008 | VDOT | completed |  |  | additional |  | cultural | resource | investigations |  | (Information
Package)
2008 | Final Environmental Impact Statement (FEIS) approved by FHWA
2008 | FHWA Issued the Record of Decision.
Geotechnical Studies
2008 | VDOT | completed |  | additional |  |  | geotechnical | borings | along | the | corridor | and | at
| locations anticipated for major structures. | [6 empty] | This information is included in the
Geotechnical Engineering Data Report. (Information Package)
Data from other projects in the vicinity of the Project has been identified and is
included on the Project website at
http://www.virginiadot.org/ppta_projects/route_460/geotechnical_documents.a
sp
Preliminary Engineering
2008 | VDOT | has |  | developed |  | a | Preliminary | Reference | Design | for | the | corridor.
(Information Package)
Procurement
2006 | In compliance with the legislative requirement identified in Section 1.5, VDOT
| initiated a PPTA procurement of the Project. | [6 empty] | VDOT cancelled the procurement
| on | May | 3, | 2010. | Additional |  | Project | information | related |  | to | the | prior
procurement is available on the Project website at http://route460ppta.org/.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 9
Name: “Table 1 of 1 on page 9 of 71”
Table: 9
8
3 | PROJECT SCOPE
The scope includes the development and operation of the proposed Project. The Offeror’s
Conceptual Proposal shall take into consideration the Project objectives and requirements
| listed | herein. |  |  | Short | listed |  | Offerors | that | are | advanced | to | Phase | Four | may | undertake
| further |  | investigations |  |  |  | and | develop |  | Detailed | Proposals |  | in | accordance |  | with | the
environmental, technical, and functional requirements that will be issued at the RFDP
stage.
3.1 | Project Requirements
The Project shall be developed and operated in accordance with applicable Regulatory
Approvals and Laws, AASHTO standards and industry best practices.
3.1.1 | Key Assumptions
| Offerors |  | shall |  | use | the | following |  | key | assumptions | in | developing |  | their | approaches |  | to
financing, designing, constructing, operating, and maintaining the Project:
• | Hurricane |  |  | evacuation |  |  | capabilities |  | and | improving | military |  | strategic |  | connectivity |  | are
| priorities |  |  | of | the | project | and | the | public. | The | Governor | will | consider |  | waiving |  | certain
statutory mandates and regulations in order to facilitate the development of the Project, if
| a | part | of | his | emergency |  | preparedness |  |  | plan, in accordance |  |  | with | the | Code | of | Virginia
§33.1-223.2:5.
• | The Commonwealth will support the Concessionaire’s innovative ideas to increase truck
traffic in the corridor, including truck traffic to and from the Port of Virginia.
• | VDOT will accept a phased approach to develop the Project and a minimum scope of
work for the first phase (e.g., the first phase may include only one interchange at each
terminus, with future interchanges or phases constructed as funding becomes available).
• | The Concessionaire shall complete right of way (ROW) acquisition at its sole cost and
| expense in accordance with all applicable Regulatory Approvals and Laws. | [14 empty] | VDOT will
handle condemnation proceedings, should the need arise.
• | There is no state or federal funding planned or programmed for this Project.
• | VDOT welcomes proposals for innovative financing alternatives.
• | VDOT will perform only minimal construction oversight and will rely primarily on the
| Concessionaire’s |  |  |  |  | quality | assurance/quality |  |  | control | work | and | on | the | Concessionaire’s
certifications that the work complies with contract requirements. The Concessionaire will
be responsible for VDOT’s construction oversight costs, estimated at two (2) percent of
the design and construction costs.
• | Offerors |  | may |  | propose |  | more | efficient |  | operating conditions |  |  | than | currently | provided by
state Law, subject to compliance with all applicable design standards and safety factors.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 10
Name: “Table 1 of 1 on page 10 of 71”
Table: 10
9
• | The | Comprehensive |  |  | Agreement |  |  | will | include |  | provisions |  | to | address |  | a | number | of
commercial issues, including but not limited to the following:
|  | 1. | a concession term of up to 75 years, with the potential to extend the term up to a
maximum of 99 years;
|  | 2. | support for the development of commercial facilities determined to be essential
for the transportation of persons or goods, together with any buildings, structures,
parking areas, appurtenances, and other property needed to operate such facility in
accordance with the Code of Virginia Section 56-557 and applicable Law; and
|  | 3. | funding for compensation events shall be limited as set forth in the term sheet.
• | The | Comprehensive |  |  | Agreement |  |  | will | include | an | enforceable |  |  | goal | for | Disadvantaged
| Business |  | Enterprise |  | (DBE) | and |  | the | Commonwealth’s |  |  | Small, |  | Women, |  | and | Minorities
(SWAM) participation in the Project.
3.1.2 | Route 460
The following requirements shall be implemented on the proposed Project:
|  | Provide | for | 4-lane |  | divided |  | roadway | built |  | to | AASHTO |  | interstate |  | standards |  | and
|  | designed | with |  | sufficient | vertical |  |  | elevation |  | and | clearance | to | enable |  | safe | operation
during a 100-year flood event;
|  | Provide a system for reversing eastbound traffic flow to accommodate westbound
travel on all lanes for hurricane and emergency evacuation; and
|  | Acquire | sufficient |  |  | ROW | to | enable | future |  | expansion | of | phased |  | interchanges |  |  | and
widening from a 4-lane to 6-lane roadway, subject to availability of funding.
3.1.3 | Tolling
| Any | new | roadway |  | on | which | a | toll | would | be | implemented |  | must |  | be | capable | of | fully
electronic toll collection techniques and technologies and employ Open Road Tolling for
| the Project’s main lines. |  |  |  |  | Traditional toll collection systems may be an option for initial
| operations, |  | in | conjunction |  | with |  | open-road |  | tolling. |  | Electronic |  | toll | equipment |  | shall | be
compatible with E-Z Pass or any successor network and VDOT’s existing electronic toll
| collection system. |  |  |  | Offerors may have the option of contracting with VDOT’s Violation
Enforcement and Electronic Toll Collection services.
3.2 | Regulatory Approvals
Offerors shall be responsible for the implementation of all National Environmental Policy
| Act | of | 1969 | (NEPA) |  | commitments |  |  | and | restrictions. |  | The | Project |  | is | subject | to | all
applicable Regulatory Approval and Laws, to include but not limited to the requirements
of the NEPA.
| Offerors |  | shall | be | required | to |  | obtain | all | necessary |  | remaining |  | regulatory |  |  | clearances
| required to accomplish the Project. | [7 empty] | The Offeror shall be responsible for obtaining and
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 11
Name: “Table 1 of 1 on page 11 of 71”
Table: 11
10
coordinating any necessary water quality permits and any modifications of water quality
permits.
If VDOT approves any deviations or change in scope or design proposed by the Offeror,
Offeror shall be responsible for providing VDOT with environmental data in support of
any | re-evaluation | of | the | NEPA | document | that | is | necessary | due | to | such | proposed
deviation or change in scope or design. |  |  |  |  | The Offeror shall reimburse VDOT for its costs
in the preparation of any additionally required environmental documents.
Conceptual Proposals shall be consistent with the environmental documents.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 12
Name: “Table 1 of 1 on page 12 of 71”
Table: 12
11
4 | GENERAL PROCEDURES AND REQUIREMENTS
4.1 | Short Listing
The Conceptual Proposals received in response to this SFP will be used to short list the
most qualified Offerors who will be invited to submit Detailed Proposals. It is anticipated
| that | no | more | than | three | (3) | Offerors | will | be | short-listed. |  |  | Evaluation |  | of | Detailed
Proposals may lead to final selection of one or more Offerors with whom VDOT may
enter into an interim and/or comprehensive agreement to obtain the right and obligation
to finance, design, construct, operate, and maintain the Project.
4.2 | Schedule
VDOT currently anticipates conducting the procurement of the Project in accordance
| with | the | following |  | list | of | milestones | leading |  | to | an | interim |  | and/or | comprehensive
| agreement. |  | This schedule is subject to revision and VDOT reserves the right to modify
this schedule as it finds necessary, in its sole discretion.
|  | Procurement Phase | [11 empty] | Date
| 1. | SFP Document Available to Offerors | [9 empty] | 05/05/10
| 2. | Deadline for Questions or Clarifications | [9 empty] | 06/21/10
| 3. | Conceptual Proposal Submission Deadline | [9 empty] | 08/05/10 (4:00 PM prevailing local time)
| 4. | Quality Control Report Submitted to Secretary | [9 empty] | 08/20/10
| 5. | Secretary Appoints Independent Review Panel | [9 empty] | 09/15/10
| 6. | Local Comments Due | [9 empty] | 10/20/10
| 7. | Independent Review Panel Recommendation | [9 empty] | 11/03/10
| 8. | CTB Resolution | [9 empty] | 11/17/10
| 9. | Request for Detailed Proposals (if applicable) | [9 empty] | 12/20/10
| 10. Detailed Proposal Submission Deadline (if applicable) | [10 empty] | 05/15/11 (4:00 PM prevailing local time)
| 11. Interim and/or Comprehensive Agreement (if applicable) | [10 empty] | 09/15/11
4.3 | VDOT’s Point of Contact and Project Reference
| VDOT’s |  | sole | Point | of | Contact | (POC) | for | the | Project |  | shall | be | the | person | designated
| below. |  | VDOT’s POC is the only individual authorized to discuss this SFP with any
| interested parties, including Offerors. | [5 empty] | All communications with VDOT’s POC shall be in
| writing, as required by the applicable provisions of this SFP. | [11 empty] | Offerors may not rely on
oral responses to any inquiries.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 13
Name: “Table 1 of 1 on page 13 of 71”
Table: 13
12
VDOT’s POC is:
| Name: |  | Margie Ray
| Title: |  | Program Manager
| Address: |  | Innovative Project Delivery Division
Virginia Department of Transportation
1401 East Broad Street
|  |  | Richmond, VA |  | 23219
| Phone: |  | (804) 786-9537
| Fax: |  | (804) 786-7221
| E-Mail: |  | margit.ray@VDOT.Virginia.gov
4.3.1 | VDOT | disclaims |  | the | accuracy | of | information |  | derived |  | from | any | source | other | than
VDOT’s POC and the use of any such information is at the sole risk of the Offerors.
4.3.2 | All written communications to VDOT from the Offerors shall specifically reference the
| correspondence |  | as | being | associated |  | with | the | “Route |  | 460 | Corridor | Improvements
Project”.
4.4 | Advertising the SFP
The SFP shall be advertised on VDOT’s website at http://route460ppta.org/, and on eVA,
| Virginia’s electronic procurement website (www.eva.state.va.us). | [10 empty] | The SFP shall also be
advertised in major regional newspapers in accordance with Innovative Project Delivery
(IPD) Division Memorandum IPD 05-01.0, available for review at
http://www.virginiadot.org/business/resources/IPD_Memorandum_05_01_0_dlh_050930
.pdf.
| Addenda to the SFP will only be posted on the VDOT website above. | [11 empty] | Offerors should
monitor the VDOT website for the posting of any addenda to this SFP.
4.5 | SFP Information
Additional information regarding the Project may be downloaded from VDOT’s website
| at | http://route460ppta.org/. |  |  | An | information |  | package |  |  | which | includes: | preliminary
| reference | design, |  | typical | sections, |  | environmental |  |  | studies, | geotechnical |  | investigation
| reports, | and | other | project | information, |  | is | available |  | to | interested | Offerors |  | on | CD | for
| $50.00. | Interested |  | Offerors | should |  | completed |  | the | Information |  | Package | Order |  | Form
| included as Appendix B. |  |  |  | The instructions for submittal and payment are included on the
form.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 14
Name: “Table 1 of 1 on page 14 of 71”
Table: 14
13
4.6 | Pre-Submittal Responsibilities
Each Offeror shall be solely responsible for examining the SFP, including any addenda,
and any and all conditions which may in any way affect their proposal or the performance
of the Work on the Project, including but not limited, to the following responsibilities:
4.6.1 | Examining and carefully studying the SFP, including any addenda and other information
or data identified in the SFP.
4.6.2 | Visiting | the | Project |  | area | and | becoming |  | familiar |  | with | and | satisfying | itself | as | to | the
general, local, and site conditions that may affect the cost, progress, or performance of its
Work on the Project.
4.6.3 | Becoming familiar with and satisfying itself as to Regulatory Approvals and Laws that
may affect the cost, progress, or performance of its Work on the Project.
4.6.4 | Determining that the SFP and any addenda thereto are sufficient to indicate and convey
understanding of all terms and conditions for the performance of Offeror’s Work on the
Project.
4.6.5 | Providing prompt written notice of all conflicts, errors, ambiguities, or discrepancies that
the Offeror discovers in the SFP and addenda, and any aspects of the SFP and addenda
| that the Offerors do not understand. | [6 empty] | Any failure to do so shall be at Offeror’s sole risk,
and no relief for error or omission will be provided by VDOT.
4.7 | Delivery of Proposal
| Conceptual |  | Proposals |  | are | to | be | sealed | in | mailing | envelopes |  | or | packages | bearing |  | the
| Offeror’s | name, | address |  |  | and | the | words |  | “Route | 460 | Corridor |  | Improvements | Project
| PPTA” clearly written on the outside. | [6 empty] | All Conceptual Proposals must be received by the
| date and time as designated in Section 4.2. | [8 empty] | Conceptual Proposals must be delivered to
| the | VDOT | POC | as | designated |  |  | below. |  | Neither | fax | nor | email | submissions | will |  | be
| accepted. | Hand delivered responses to the SFP must be received by the date and time as
designated in Section 4.2, and must be delivered to:
Mrs. Brenda Williams
Administrative Services Division
Virginia Department of Transportation
1 st Floor Reception Desk
|  |  | 1201 E. |  | Broad Street
|  |  | Richmond, VA |  |  |  | 23219
Offerors are responsible for effecting delivery by the deadline above and late submissions
will be rejected without consideration or evaluation, and will be returned unopened to the
| sender. | VDOT accepts no responsibility for misdirected or lost Conceptual Proposals.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 15
Name: “Table 1 of 1 on page 15 of 71”
Table: 15
14
4.7.1 | The Conceptual Proposals should be as clear and concise as possible in accordance with
the requirements of this SFP, so that a proper evaluation can be made of the Offeror’s
capabilities and intent to complete the proposed Project.
4.7.2 | Offerors | submitting |  |  | Conceptual |  | Proposals |  | to | VDOT | are | required | to | deliver | ten | (10)
| identical | hard |  | copies, | one | (1) | of | which | must | bear | original | signatures |  | and | one | (1)
electronic copy (a “.pdf” file in the most current version of Adobe Acrobat), of their
| Conceptual Proposal for all Volumes on CD-ROM. | [8 empty] | Offerors passing VDOT’s Quality
Control review will be required to submit additional hard copies at VDOT’s request.
4.8 | Format of Proposal
Conceptual Proposals shall follow the format prescribed in this section and the current
| version of the Guidelines as referenced herein. | [8 empty] | Submittals that do not follow the format
prescribed below may be considered non-responsive and may be eliminated from further
consideration.
4.8.1 | Conceptual |  | Proposals |  | should |  | be | prepared | simply |  | and | economically, |  | providing |  | a
straightforward, concise description of the Offeror’s capabilities to complete the Project.
Emphasis should be on completeness and clarity.
4.8.2 | All pages of the Conceptual Proposal shall be numbered in the lower right hand corner.
| Offerors | shall |  | use | cross | referencing |  | rather | than | repetition |  | throughout |  | the | Conceptual
| Proposal. | The Conceptual Proposal shall contain a table of contents which shall follow
the format described herein.
4.8.3 | Conceptual |  | Proposals |  | shall | be | placed | in | a | three-ring |  | binder. | All | documentation
| submitted with the Conceptual Proposal shall be contained in two volumes: | [13 empty] | Volume I
shall contain all of the material requested in Section 4.8.4, with the exception of the
financial commitments and reports, and Volume II shall contain financial statements and
reports. Conceptual Proposals shall also meet the following requirements:
|  | Consist of no more than 50 pages (VDOT will remove and discard all pages in excess
|  | of the stipulated page limit). |  |  |  |  | The following items shall not be counted against the
|  | page limit: |  | Letter of Submittal; Executive Summary; tabs; Certification Regarding
Debarment Forms, Appendix C; financial statements and reports requested in Section
10.4.1.1 and contained in Volume II; Work History Forms, Appendix D; Resume
Forms, Appendix E; and Conceptual Financial Plan Pro Forma, Appendix G;
|  | Except | for | charts, | exhibits, |  | and | other | illustrative |  | and | graphical |  | information, |  | all
information shall be prepared on 8.5”X 11” white paper. Charts, schedules, exhibits
and other illustrative and graphical information may be on 11” x 17” paper, but must
be folded to 8.5” X 11”;
|  | Typed on one (1) side only; and
|  | Separated by numbered tabs with sections corresponding to the order set forth in
|  | Section 4.8.4. |  |  | Tabs should not contain Project-specific information, or they will
count against the page limit.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 16
Name: “Table 1 of 1 on page 16 of 71”
Table: 16
15
|  | All | printing, | except | for | the | front | cover | of | the | Conceptual |  | Proposal | and |  | any
appendices, must be:
|  | o | Times New Roman, with a font of 12-point; and
|  | o | Offeror may use Times New Roman 10 point font for filling out information on
the Work History Forms, Appendix D and the Resume Forms, Appendix E.
4.8.4 | Each Conceptual Proposal shall be organized as follows:
|  | 1. | Letter of Submittal (maximum Four Pages)
|  | 2. | Executive Summary (maximum Five Pages)
|  | 3. | Table of Contents
|  | 4. | Responses to Conceptual Proposal Evaluation Criteria:
|  |  | Section 10.4.1: |  | Qualifications Criteria
.1 Financial Capacity
.2 Project Finance Experience
.3 Design, Construction, Maintenance and Operations
.4 Toll Facility Operations
.5 Conceptual Financial Plan
4.9 | Formal Presentation and Interviews
Offerors may be required to give oral presentations of their Conceptual Proposal to an
| IRP | and/or | the | public. | The | format |  | of | these | presentations |  | may | include | a | formal
| presentation |  | by | Offerors, | followed |  | by |  | questions | from | the | IRP | pertaining |  | to | the
Conceptual Proposals or the presentations. The IRP may also ask Offerors to address
| concerns expressed through the public comment process. | [9 empty] | Such presentations will provide
| opportunities to inform VDOT and the public and/or clarify aspects of the Project. | [14 empty] | The
| presentations |  | will | also | allow | the | IRP | to | seek | clarification | of | Project | elements, |  |  | the
Conceptual Proposal’s response to the Project objectives and needs, complete deliverable
| requirements |  | and | provide | Offerors |  | with |  | the | opportunity | to | further | explain |  | their
| Conceptual Proposal. |  |  | If there is an issue to which the Offerors are unable to respond
during the formal presentation, the IRP may, at their discretion, grant the Offerors a
reasonable period of time in which to submit a written response.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 17
Name: “Table 1 of 1 on page 17 of 71”
Table: 17
16
5 | QUESTIONS AND CLARIFICATIONS
| All | questions |  | and | requests | for | clarification |  | regarding |  | this | SFP | shall | be | submitted |  | in
| writing |  | to | VDOT’s | POC | designated |  | in | Section |  | 4.3. | No | requests | for | additional
information, clarification or any other communication should be directed to any other
| individual. |  |  | VDOT’s | responses |  | to | questions |  | or | requests | for | clarification |  | shall | be | in
| writing and may be accomplished by an addendum to this SFP. | [11 empty] | VDOT will not be bound
by any oral communications, or written interpretations or clarifications that are not set
| forth | in | an | addendum. |  | VDOT, | at | its | sole | discretion, |  | shall | have | the | right | to | seek
| clarifications |  |  | from | any | Offeror | to | fully | understand |  |  | information |  | contained |  | in | the
| Conceptual Proposal. |  |  |  | All questions submitted by the Offerors shall be published on the
VDOT website, in the form in which they were received.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 18
Name: “Table 1 of 1 on page 18 of 71”
Table: 18
17
6 | RIGHTS AND OBLIGATIONS OF VDOT
In connection with this procurement, VDOT reserves to itself all rights (which rights
shall be exercisable by VDOT in its sole discretion) available to it under applicable Law.
6.1 | Specific Rights and Obligations of VDOT
In addition to all rights reserved as specified by Law, VDOT further reserves to itself,
without limitation or with or without cause and with or without notice, the following:
6.1.1 | The right to cancel, withdraw, postpone or extend this SFP in whole or in part at any time
prior to the execution by VDOT of an interim and/or comprehensive agreement, without
incurring any obligations or liabilities.
6.1.2 | The right to issue a new SFP.
6.1.3 | The right to reject any and all submittals, responses and proposals received at any time.
6.1.4 | The right to modify all dates set or projected in this SFP.
6.1.5 | The right to terminate evaluations of responses received at any time.
6.1.6 | The right to suspend and terminate the procurement process for the Project at any time.
6.1.7 | The right to revise and modify, at any time prior to the proposal submittal date, factors it
will consider in evaluating responses to this SFP and to otherwise revise its evaluation
methodology.
6.1.8 | The right to waive or permit corrections to data submitted with any response to this SFP
until such time as VDOT declares in writing that a particular stage or phase of its review
of the responses to this SFP has been completed and closed.
6.1.9 | The right to issue addenda, supplements, and modifications to this SFP.
6.1.10 | The right to permit submittal of addenda and supplements to data previously provided
| with | any | response | to | this | SFP | until | such | time | as | VDOT | declares | in | writing | that | a
particular stage or phase of its review of the responses to this SFP has been completed
and closed.
6.1.11 | The right to hold meetings and conduct discussions and correspondence with one or more
of the Offerors responding to this SFP to seek an improved understanding and evaluation
of the responses to this SFP.
6.1.12 | The right to seek or obtain data from any source that has the potential to improve the
understanding and evaluation of the responses to the SFP, including the right to seek
clarifications from Offerors.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 19
Name: “Table 1 of 1 on page 19 of 71”
Table: 19
18
6.1.13 | The right to permit Offerors to add or delete firms and/or key personnel.
6.1.14 | The right to add or delete the Offeror’s responsibilities from the information contained in
this SFP.
6.1.15 | The right to appoint and change appointees of the Independent Review Panel.
6.1.16 | The | right | to | use | assistance | of | outside | technical, |  |  | financial, | and | legal |  | experts | and
Consultants in the evaluation process.
6.1.17 | The right to waive deficiencies, informalities and irregularities in a proposal, accept and
review a non-conforming proposal or seek clarifications or supplements to a proposal.
6.1.18 | The right to disqualify any Offeror that changes its submittal without VDOT approval.
6.1.19 | The right to respond to all, some, or none of the inquiries, questions and/or request for
clarifications received relative to the SFP.
6.1.20 | The right to use all or part of an unsuccessful Conceptual Proposal if the Offeror of said
proposal accepts a payment, if applicable.
6.1.21 | The | right | to | suspend, | discontinue |  | and/or |  | terminate |  | interim |  | and/or | comprehensive
| agreement |  | negotiations |  | with | any | Offeror | at | any | time | prior | to | the | actual | authorized
execution of such agreement by all parties, subject to appropriate documentation.
6.1.22 | The | right | to | negotiate | with | an | Offeror | without |  | being | bound | by | any | provision | in | the
proposal.
6.1.23 | The right to enter into one or more interim and/or comprehensive agreements with one or
| more | Offerors, |  | as | permitted | by | the | PPTA, | in | furtherance |  | of | the | development |  | and
operation of the Project or any of its components, or to modify or abandon procurement
of the Project.
6.1.24 | The right to request revisions to the Conceptual Proposal.
6.1.25 | The right to short list from among the highest rated Offerors, and to provide an RFDP
| only to those short listed Offerors. | [5 empty] | VDOT anticipates short listing no more than three (3)
| highest | rated |  | Offerors. | VDOT |  | may | increase | or | decrease | the | number |  | of | short | listed
Offerors, if it is in the best interest of VDOT to do so.
6.2 | Assumption of Liability
| VDOT | assumes |  | no | obligations, |  | responsibilities, |  |  | and | liabilities, |  | fiscal | or | otherwise, | to
reimburse all or part of the costs incurred or alleged to have been incurred by parties
| considering a response to and/or responding to this SFP. | [9 empty] | All such costs shall be borne
solely by each Offeror and its team members.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 20
Name: “Table 1 of 1 on page 20 of 71”
Table: 20
19
6.2.1 | In no event shall VDOT be bound by, or be liable for, any obligations with respect to the
Project until such time (if at all) an interim and/or comprehensive agreement, in form and
substance satisfactory to VDOT, has been executed and authorized by VDOT and, then,
only to the extent set forth therein.
6.2.2 | Any and all information made available to the Offerors is made for convenience purposes
only and is without representation or warranty of any kind.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 21
Name: “Table 1 of 1 on page 21 of 71”
Table: 21
20
7 | COMPREHENSIVE AGREEMENT – MATERIAL TERMS
VDOT issues this SFP, inclusive of all appendices and addenda (collectively the “SFP
Documents”) as a preliminary step in the PPTA procurement process, which, if carried
| through | to | the | conclusion, |  | will | result | in | VDOT | entering |  | into | an | interim | and/or
| comprehensive |  |  | agreement | with | the | successful |  | Offeror, | who |  | will | obtain | the | right | and
| obligation to finance, design, construct, operate and maintain the Project. | [12 empty] | Several terms
of the interim and/or comprehensive agreement, which VDOT proposes to execute for the
| Project are included as Appendix F. | [5 empty] | Additionally, a draft comprehensive agreement, will
be included with the RFDP. The RFDP will, among other things, detail the technical
requirements for the design, construction, maintenance and operations components of the
| Project; | the | scope | of | the | services | to | be | provided | by | the | successful |  | Offeror; |  | and
commercial terms.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 22
Name: “Table 1 of 1 on page 22 of 71”
Table: 22
21
8 | MISCELLANEOUS
8.1 | Virginia Freedom of Information Act
8.1.1 | All proposals submitted to VDOT are subject to the disclosure requirements of the PPTA,
Section 2.2-4342 of the Virginia Public Procurement Act, and the Virginia Freedom of
| Information Act (VFOIA) (Section 2.2--3700 et seq.). | [6 empty] | Offerors are advised to familiarize
themselves with the provisions of each Act referenced herein to ensure that documents
| identified as confidential will not be subject to disclosure under VFOIA. | [9 empty] | In no event
shall the Commonwealth, the Commonwealth Transportation Commissioner, or VDOT
be liable to an Offeror for the disclosure of all or a portion of a Conceptual Proposal
submitted pursuant to this request.
8.1.2 | If a responding Offeror has special concerns about information which it desires to make
| available | to | VDOT | but | which | it | believes | constitutes | a | trade | secret, | proprietary
| information, |  | or | other | confidential |  | information | exempted |  | from | disclosure, | such
responding Offeror should specifically and conspicuously designate that information as
such in its proposal and state in writing why protection of that information is needed.
| The Offeror should make a written request to VDOT’s POC. | [7 empty] | The written request shall:
| 1. | Invoke such exemption upon the submission of the materials for which protection
is sought;
| 2. | Identify specifically and conspicuously the data or other materials for which the
protection is sought;
| 3. | State the reasons why protection is necessary; and
| 4. | Indicate that a similar process with the appropriate officials of the affected local
|  | jurisdictions has or will be conducted. | [5 empty] | Failure to take such precautions prior to
submission of a proposal may subject confidential information to disclosure under
the VFOIA.
8.1.3 | Blanket designations that do not identify the specific information shall not be acceptable
| and may be cause for VDOT to treat the entire proposal as public information. | [10 empty] | Nothing
contained in this provision shall modify or amend requirements and obligations imposed
on VDOT by applicable Law, and the applicable Law(s) shall control in the event of a
conflict between the procedures described above and any applicable Law(s).
8.1.4 | In the event that VDOT receives a request for public disclosure of a portion of a proposal,
VDOT will determine whether or not the requested materials are exempt from disclosure.
In the event that VDOT elects to disclose the requested materials, it will endeavor to
provide notice to the Offeror of its intent to disclose.
8.1.5 | Offerors are on notice that VDOT will post on its webpage all responsive Conceptual
Proposals and other relevant information and agreements, in accordance with applicable
Regulatory Approvals and Laws.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 23
Name: “Table 1 of 1 on page 23 of 71”
Table: 23
22
8.1.6 | Offerors are advised that portions of the Project documents may be considered Critical
| Infrastructure |  |  | Information/Sensitive | [5 empty] | Security |  |  | Information |  | (CII/SSI) |  |  | and | any | VFOIA
requests for such documents will be processed in accordance with the Code of Virginia
Section 2.2-3705.2.
8.2 | Requirement to Keep Team Intact
| The | Key | Personnel |  |  | proposed |  |  | by | the | Offeror |  | shall | remain |  | on | Offeror’s |  | team | for | the
duration of the procurement process and, if the Offeror is selected and enters into an
interim and/or a comprehensive agreement, the requirement will be as more specifically
| defined in the comprehensive agreement. | [10 empty] | If circumstances require a proposed change, it
| must | be | submitted |  |  | in | writing |  | to | VDOT’s |  |  | POC. | VDOT |  | will | determine |  | whether |  | to
| authorize |  | a | change, |  |  | which |  | authorization |  |  |  | will | not | be | unreasonably |  |  | withheld.
Unauthorized changes to the Offeror’s Key Personnel at any time during the procurement
process may result in the elimination of the Offeror from further consideration.
8.3 | Disadvantaged |  |  |  | Business |  |  | Enterprises/Small, | [5 empty] | Women |  | and |  | Minority |  | Owned
Businesses
| The | participation |  |  | goals |  | for | this |  | Project |  | will | be | set | forth | in | the | RFDP, | wherein |  | a
| commitment |  |  | will | be |  | required |  | from |  | Offerors |  | to | achieve | the |  | goals. | Offerors |  |  | shall
| anticipate |  | compliance |  |  |  | with | relevant |  |  | Federal |  | and | State | DBE/SWAM |  |  |  | policies |  | and
regulations.
8.4 | Administrative Requirements
In addition to the specific submittal requirements set forth elsewhere in this SFP, all
Offerors shall comply with the following:
8.4.1 | Prior | to | the | execution |  |  | of | an | interim |  | and/or |  | comprehensive |  |  | agreement, |  |  | all | business
entities, except for sole proprietorships, are required to be registered with the Virginia
State Corporation Commission (a Business Registration Guide is available on the Internet
| at | http://www.state.va.us/scc/division/clk/brg.htm). | [11 empty] | Foreign |  | Professional |  |  | Corporations
and Foreign Professional Limited Liability Companies must possess a Commonwealth of
| Virginia |  | Certificate |  |  | of | Authority |  |  | from |  | the | State | Corporation |  |  | Commission |  | to | render
professional services.
| All | Offerors |  | and | Submittals |  |  | must |  | at | the | time | of | their | Conceptual |  |  | Proposal | submittal
comply with the law and nothing herein is intended to contradict, nor supersede, any
| applicable Regulatory Approvals and Laws. | [11 empty] | All Offerors shall be eligible at the time of
their Conceptual Proposal submittal, under the law and relevant regulations, to offer and
| to provide all services proposed and related to the Project. | [13 empty] | Unless exempted by §§ 54.1-
| 401, | 54.1-402, |  |  | or | 54.1-402.1 |  |  | of | the |  | Code | of | Virginia, |  | any | person, |  | partnership,
| corporation, |  |  | or | other |  | entity | offering |  |  | or | practicing |  | architecture, |  |  | engineering, |  |  | or | land
| surveying shall be registered or licensed in accordance with the provision of | [17 empty] | Chapter 4,
Title 54.1 of the Code of Virginia. Offerors shall satisfy, at the time of their Conceptual
Proposal submittal, all commercial and professional registration requirements, including,
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 24
Name: “Table 1 of 1 on page 24 of 71”
Table: 24
23
| but | not | limited | to | the | requirements |  | of | the | State |  | Corporation | Commission |  | and | the
Department of Professional and Occupational Regulations.
8.4.2 | VDOT will not consider for award any proposals submitted by any Offerors and will not
consent to subcontracting any portions of the proposed contract to any subconsultants in
violation of the provisions of the Federal Immigration Reform and Control Act of 1986,
which prohibits employment of illegal aliens.
8.4.3 | Prior to the execution of an interim and/or comprehensive agreement all Offerors must
have internal control systems in place that meet federal requirements for accounting.
| These | systems |  | must |  | comply | with | requirements |  |  | of | 48CFR31, | “Federal | Acquisition
Regulations, Contract Cost Principals and Procedures,” and 23CFR172, “Administration
of Negotiated Contracts.”
8.4.4 | VDOT assures compliance with Title VI of the Civil Rights Act of 1964, as amended.
The Consultant and all subconsultants selected for this Project shall be required to submit
a Title VI Evaluation Report (EEO-D2) when requested by VDOT to respond to the SFP.
This requirement applies to all consulting firms with fifteen (15) or more employees.
8.4.5 | VDOT does not discriminate against an Offeror because of race, religion, color, sex,
national origin, age, disability, or any other basis prohibited by state Law relating to
discrimination in employment.
8.4.6 | Please indicate in the Letter of Submittal, Section 10.2, and by executing and returning
the attached Certification Regarding Debarment Forms, provided in Appendix C, if your
firm, subconsultant, subcontractor, or any person associated therewith in the capacity of
owner, partner, director, officer or any position involving the administration of federal or
state funds:
| 1. | Is currently under suspension, debarment, voluntary exclusion or determination of
ineligibility by any State or federal agency;
| 2. | Has been suspended, debarred, voluntarily excluded or determined ineligible by
any federal agency within the past three years;
| 3. | Has a proposed debarment or suspension pending; or
| 4. | Has been indicted, convicted, or had a civil judgment rendered against it or them
|  | by | a | court | of | competent | jurisdiction |  |  | in | any | matter | involving | fraud | or | official
misconduct within the past three years.
Any of the above conditions will not necessarily result in denial of award, but will be
| considered in determining Offeror responsibility. | [9 empty] | For any condition noted, indicate to
| whom it applies, initiating agency, and dates of action. | [10 empty] | Providing false information may
| result in federal criminal prosecution or administrative sanctions. | [11 empty] | Certifications should
be submitted directly behind the Letter of Submittal.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 25
Name: “Table 1 of 1 on page 25 of 71”
Table: 25
24
8.4.7 | Offerors shall note and comply with the requirements relative to the eVA Business-to-
| Government Vendor system. |  |  |  | The eVA Internet electronic procurement solution, web site
| portal | (http://www.eva.state.va.us), |  |  |  | streamlines |  |  | and | automates |  | government |  | purchasing
| activities | in | the | Commonwealth. |  | The |  | portal | is | the | gateway | for | vendors | to | conduct
| business with state agencies and public bodies. | [8 empty] | All vendors desiring to provide goods
and/or services to the Commonwealth shall participate in the eVA Internet e-procurement
solution through either eVA Basic Vendor Registration Service or eVA Premium Vendor
| Registration |  | Service. | For | more | detail |  | information |  | regarding |  | eVA, | registrations, |  | fee
| schedule, | and | transaction |  | fee, | use | the | website |  | link: | http://www.eva.state.va.us. |  |  |  | All
Offerors must register in eVA; failure to register will result in a Conceptual Proposal
being rejected.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 26
Name: “Table 1 of 1 on page 26 of 71”
Table: 26
25
9 | CONFLICT OF INTEREST
9.1 | Conflict of Interest Determination
9.1.1 | VDOT will apply the procedures set forth in the Innovative Project Delivery Division
Memorandum 07-2.0, dated August 1, 2007, for identification and review of potential
organizational conflicts of interest related to VDOT procurement of contracts under the
PPTA or design-build legislation. This memorandum is available at VDOT’s website at
http://www.virginiadot.org/business/bu-ipd-memo.asp.
9.1.2 | Offerors |  | shall | note | that | portions | of | the | SFP | Documents |  | will | include | work |  | product
developed by the others.
| 1. | The firms listed below will not be allowed to participate as a team member with an
|  | Offeror | for | this | Project | due | to | their |  | participation |  | in | assisting | VDOT |  | with:
|  | procurement |  | documents; |  | negotiations |  |  | strategies |  | and | negotiations; |  |  | business | and
|  | policy | decisions; |  |  | contract | management |  |  | and | administration; |  |  |  | development,
negotiation, and execution of interim and/or comprehensive Agreement; and reports
|  | and contact language. |  |  |  | Any proposal received in violation of this requirement may be
rejected.
|  | Halcrow | Inc.; |  | Public | Resources |  | Advisory |  | Group |  | (PRAG); |  | C&M; |  | Jeffrey | A.
Parker and Associates, KPMG Corporate Finance LLC; Warner Construction
|  | Consultants, |  | Inc.; |  | Capital | Project |  | Strategies, |  | LLC, | and |  | Nossaman |  | LLP | /
Nossaman, O’Conner & Hannan LLP
| 2. | The firms listed below have completed work that is available to prospective Offerors
|  | and | VDOT | has | determined | that, |  | at | this | time, | they | would | not | have | a | conflict | of
interest if they chose to pursue the Project with a private developer.
Parsons Brinkerhoff, Michael Baker and Rummel, Klepper, and Kahl LLP
9.2 | Ethics in Public Contracting Act
VDOT may, in its sole discretion, disqualify the Offeror from further consideration for
the award of the contract if it is found by VDOT that there is a violation of the Ethics in
Public Contracting Act, Section 2.2-4367 of the Virginia Code, or any similar statute
involving the Offeror in the procurement of the contract.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 27
Name: “Table 1 of 1 on page 27 of 71”
Table: 27
26
10 | CONTENTS OF CONCEPTUAL PROPOSAL
The Conceptual Proposals should provide sufficient information to facilitate evaluation of
| the Offeror’s qualifications and Conceptual Financial Plan. | [10 empty] | Section 10 describes the type
of information that must be included in the Conceptual Proposals. The format for the
presentation of such information within the Conceptual Proposal is described in Section
4.8.
| Offerors |  | shall | be | aware | that | VDOT | reserves | the | right |  | to | conduct | an | independent
investigation of any information, including prior experience, identified in a proposal by
| contacting |  |  | project | references, |  | accessing | public | information, |  |  |  | contacting |  | independent
| parties, |  | or | any | other | means. | VDOT | also | reserves |  | the | right | to | request | additional
information from an Offeror during the evaluation of its Conceptual Proposal.
10.1 | Confidentiality
| Confidentiality requests should be consistent with Section 8.1 of this SFP. | [12 empty] | It is VDOT’s
| policy to be transparent throughout the entire procurement process. | [11 empty] | The classification of
| the entire Conceptual Proposal as confidential is not acceptable. | [11 empty] | Offerors shall clearly
disclose any anticipated source and amount of public funds, programs or services in the
Executive Summary and in the Conceptual Financial Plan and such information shall not
be exempt from disclosure.
10.2 | Letter of Submittal
Each Offeror shall provide a Letter of Submittal on the Offeror’s letterhead signed by an
authorized Representative of the Offeror’s organization, which individual shall be the
| contact point for all communications from VDOT related to the SFP or the Project. | [13 empty] | The
letter shall not exceed four (4) pages in length and shall meet the following requirements:
|  | Include the authorized Representative’s title, address, phone and fax numbers, and e-
mail addresses;
|  | Provide name and address of lead firm and consortium firms who are to be part of the
Offeror’s team;
|  | Certification Regarding Debarment forms as provided in Appendix C;
|  | If the Offeror is not yet a legal entity or is a joint venture or other enterprise which
consists of parties who will be jointly and severally liable for all the private entity’s
obligations under the interim and/or comprehensive agreement, then all such parties
(including but not limited to the lead contractor and lead designer), or, if applicable,
all joint venture partners/members shall sign the letter;
|  | All signatures shall be original and signed in ink;
|  | Include the written commitment of all signators to be jointly and severally liable for
|  | all | obligations |  | of | the | private | entity | under | the | interim |  | and/or | comprehensive
agreement; and
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 28
Name: “Table 1 of 1 on page 28 of 71”
Table: 28
27
|  | Describe any parent guarantees that the Offeror will provide to secure its performance
|  | of | its | obligations |  |  | under | the | interim | and/or |  | comprehensive |  |  | agreement, |  |  | and | any
proposed limits on the liability of the private entity or its guarantors.
10.3 | Executive Summary
| Each Offeror shall provide an Executive Summary. | [10 empty] | The Executive Summary shall not
exceed five (5) pages and should include the following items:
10.3.1 | Brief |  | description |  |  | of | all | significant |  | aspects | of | the | Conceptual |  |  | Proposal |  | and | the
| implementation |  |  |  | team, |  | to | include | the | Offeror’s |  | objectives |  | in | the | development |  |  | and
operation of the Project.
10.3.2 | Declaration |  |  | as | to | whether |  | public | financial | support |  | is | not | necessary |  | in | the | Offeror’s
approach for implementation of the Conceptual Financial Plan.
10.3.3 | Declaration of Offeror’s intent, if selected, to enter into an interim and/or comprehensive
agreement with VDOT for the Project in accordance with the terms of this procurement.
10.3.4 | Declaration that the offer presented in the Conceptual Proposal shall remain in full force
and effect until such time as submission of the Detailed Proposals.
10.3.5 | Declaration that information provided in the Conceptual Proposal meets appropriate state
and federal, standards, statutes and regulations, or reasonably anticipated modifications
of state or federal statutes, regulations or standards.
10.4 | Conceptual Proposal Submittal Criteria
| Offerors |  | are | advised |  |  | that | the | Conceptual | Proposal |  | submittal |  | and |  | evaluation |  | criteria
contained herein has been modified from the Guidelines. These modifications were made
in order to meet the specific needs of the Project and VDOT. Further, the submittal and
evaluation criteria listed herein supersede the criteria listed in the Guidelines.
Offerors should limit their Conceptual Proposal responses to the request for qualifications
| and | information |  |  | identified |  |  | below. | Responses |  | should | focus |  | on | critical | issues |  | for | the
Project, the objectives of the Conceptual Proposals and on the stated evaluation criteria
listed herein.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 29
Name: “Table 1 of 1 on page 29 of 71”
Table: 29
28
Section 10.4.1 Qualifications Criteria
.1 | Financial | For all team members who will be providing equity and/or providing the
| Capacity | performance security for the initial construction of the Project, (to include
any parent or related companies from whom financial guarantees will be
provided) the following documentation must be provided:
|  | 1. | Audited financial statements for each of the last five (5) years
prepared:
|  |  |  | a. | in | accordance |  | with | U.S. | Generally |  |  | Accepted
[5 empty] | Accounting |  | Principles |  | (GAAP) |  |  | or | International
Financial Reporting Standards (IFRS);
|  |  |  | b. | in English;
|  |  |  | c. | in US dollars*; and
|  |  |  | d. | including balance sheet, profit and loss statements,
and statement of changes in financial position and
accompanying notes to financial statements.
If the audited financial statements are prepared in accordance
with an accounting standard other than U.S. GAAP or IFRS, a
letter must be provided by a Certified Public Accountant (or
|  |  | equivalent |  | professional |  | accountant) |  |  | discussing |  |  | the | major
differences between the standards upon which these financial
statements are prepared and U.S. GAAP or IFRS.
|  |  | *If | audited | financial | statements |  |  | are | not | available |  | in | U. | S.
|  |  | dollars, | items |  | required | in | 10.4.1.1.1 |  | (d) | converted |  | into | U.S.
|  |  | dollars | will | suffice. | However, |  | a | CPA |  | or | other | accountant
|  |  | professional |  | equivalent |  | letter | describing |  |  |  | assumptions |  | and
|  |  | confirming |  | accuracy | of | calculations |  |  | and | fair | representation
results shall be provided.
|  | 2. | Interim financial statements for the most recent period since the
last fiscal period.
|  | 3. | Most recent Securities and Exchange Commission 10-K and 10-
Q reports, if such reports have been filed.
|  | 4. | Current and planned financial commitments to other projects,
any off-balance sheet liabilities and an assessment of the extent
to which these commitments may affect the Offeror’s ability to
raise the necessary finance for the Project.
|  | 5. | Commitment letters from parent company or related parties who
are proposed to provide financial guarantees to the Project.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 30
Name: “Table 1 of 1 on page 30 of 71”
Table: 30
29
.2 | Project | a. On an aggregate basis, identify members of the team that have been
| Finance | involved in successfully financing long-term Public Private Partnership
| Experience | (P3) transportation projects valued in excess of $500 million total (US$)
initial capital costs including a role as an equity investor within the last
ten (10) years.
|  | With | respect | to | the | Offeror’s |  | financing |  | experience, |  | the | following
|  | documentation |  | for | up | to | three | of | the | most | recent | projects | must | be
provided (in US$):
|  |  | 1. | Name of individual team member involved
|  |  | 2. | Name of project
|  |  | 3. | Description of project
|  |  | 4. | Location of project
|  |  | 5. | Total project costs
|  |  | 6. | Year of financial close
|  |  | 7. | Value of financing
|  |  | 8. | Description of financing
|  |  | 9. | Value of equity invested
|  |  | 10. Third |  | party | reference |  | (Name, |  | organization, |  | phone | number,
email)
|  | This | information |  | should | be | provided |  | on | the | Work | History | Form | 1,
Appendix D.
b. Provide a narrative describing the extent and depth of the Offeror’s
experience in financing projects similar to the Project.
|  | With | respect | to | the | Offeror’s |  | financing |  | experience, |  | the | following
additional information must be submitted for each representative project
(maximum five projects):
|  |  | 1. | Team member (firm) name
|  |  | 2. | Name of project
|  |  | 3. | Description of project
|  |  | 4. | Location of project
|  |  | 5. | Year of financial close
|  |  | 6. | Value of financing
|  |  | 7. | Description of financing
|  |  | 8. | Role in financing
|  |  | 9. | Third | party | reference |  | (Name, |  | organization, |  | phone | number,
email)
|  | This | information |  | should | be | provided |  | on | the | Work | History | Form | 1,
Appendix D.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 31
Name: “Table 1 of 1 on page 31 of 71”
Table: 31
30
Note: If Offeror chooses to list individual team member experience gained
|  | from | another |  | firm | as | relevant |  | to | the | Offeror’s |  | qualifications, |  |  |  | then | the
Offeror shall also identify these specific team members as Key Personnel.
|  | The | information |  |  | regarding |  | Key | Personnel |  |  | should |  | be | provided |  | on | the
Resume Form, Appendix E.
.3 | Project | What is the direct and relevant experience of the Offeror’s team in the
| Design, | design, |  | construction, |  |  | operations |  |  | and | maintenance |  |  |  | of | infrastructure
| Construction, | projects of similar scope and magnitude as this Project?
Maintenance
| and | List | and | describe |  | a | maximum |  | of | ten | (10) | projects |  |  | that | the | Offeror’s
| Operations | proposed team, to include, the Offeror, and lead team members for design
and construction and operations and maintenance has been involved in,
|  | which | best |  | illustrates |  | current |  | qualifications |  |  |  | relevant |  | to | the | unique
components of this Project.
|  | Provide |  | the | overall |  | history |  | of | performance, |  |  |  | including |  |  | schedule
|  | completion, |  |  | cost | and | budget |  | control, |  | and | assessment |  |  |  | of | liquidated
damages, on all ten (10) projects as indicated above and undertaken by the
Offeror, the design-build Contractor and the operator.
|  | a. | Provide | specific |  | relevant |  |  | experience |  | of | the | Offeror |  |  | and | its | team
members who will be responsible for the operations and maintenance of
the roadway. Identify direct and relevant experience related to operation
of a reversible roadway during an emergency or evacuation event.
|  | This | information |  |  | should |  | be | provided |  | on | the | Work |  | History |  | Form | 3,
Appendix D.
|  | b. | Provide specific relevant experience of the Offeror and its lead team
members which will be responsible for the design and construction of the
|  | roadway, |  | including |  |  | its | record | of | success |  |  | in | the | development |  |  | of
|  | comparable |  |  | projects |  | and | responsibilities. |  |  |  | Identify |  |  | the | design |  | and
construction teams’ prior working relationships, if any.
Provide at least three examples of projects that included the Offeror’s
|  | design team in a leading role. | [6 empty] | Include a minimum of one of the three
projects that involved a greenfield project.
Provide at least three examples of projects that included the Offeror’s
construction team in a leading role. Include a minimum of one of the
three projects that involved a greenfield project.
In addition, provide information as to whether the Offeror, design-build
Contractor have defaulted on any contracts in the last seven (7) years.
Provide details if any.
|  | This | information |  |  | should |  | be | provided |  | on | the | Work |  | History |  | Form | 2,
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 32
Name: “Table 1 of 1 on page 32 of 71”
Table: 32
31
Appendix D.
|  | Lead | team |  | members |  | identified |  |  | in | response |  | to | these | criteria |  | will | be
|  | deemed |  | “Key |  | Personnel”. |  |  | The | information |  |  | regarding |  | Key | Personnel
should be provided on the Resume Form, Appendix E.
.4 | Toll Facility | What | is | the |  | extent | and | depth |  | of | the | Offeror’s |  | direct | and |  | relevant
| Operations | experience |  |  | in | undertaking |  | toll |  | operations |  | for | a | project | or | projects |  | of
similar scope and magnitude as this Project in the last ten (10) years?
With respect to the Offeror’s tolling experience the following information
should be submitted for each project (for a maximum of three projects):
|  |  | 1. | Name of team member involved
|  |  | 2. | Name of project
|  |  | 3. | Location of project
|  |  | 4. | Description of project
|  |  | 5. | Description of tolling (manual toll booths, electronic tolling,
video tolling, variable tolling, etc.)
|  |  | 6. | Description of |  |  | tolling responsibilities
|  |  | 7. | Third party reference (Name, organization, phone number,
email)
This information should be provided on the Work History Form 1,
Appendix D.
.5 | Conceptual | Provide an approach to developing a reasonable and viable financial plan
| Financial | that fully funds total project cost.
Plan
With a focus on achieving the Project objectives, the extent to which the
Conceptual Financial Plan submitted demonstrates the following:
|  | 1. | An |  | understanding |  |  |  | of | long-term |  | P3 |  | financing |  | of | major
infrastructure projects;
|  | 2. | An understanding of viable financing options available in the U.S.
markets;
|  | 3. | An |  | understanding |  |  | of | the | unique |  | financing |  | characteristics |  |  | of | the
Project; and
|  | 4. | The plan is achievable in the current U.S. financial markets.
a. The Offeror must provide a qualitative description (maximum three (3)
|  | pages) |  | of | the | Offeror’s |  | approach |  |  | to | financing |  | the | development,
|  | maintenance and operations of the Project. | [9 empty] | At a minimum, this discussion
should address:
|  |  | 1. | Potential sources and uses of funds and a brief description of the
listed funding sources;
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 33
Name: “Table 1 of 1 on page 33 of 71”
Table: 33
32
| 2. | Potential payment mechanisms for the Project;
| 3. | Financial support that may be available from team members;
| 4. | No Federal funding or Federal Programs should be assumed;
| 5. | Approaches to user fee and toll regulation including a projected
range of initial toll rates; and
| 6. | Roles | and | responsibilities |  | for | the | public | and | private | sector
parties as it relates to financing.
b. The Offeror must provide its estimated sources and uses of funds as
well as providing the information as described in the Conceptual Finance
Plan | Pro | Forma, | Appendix |  | G. | Traffic | numbers | distinguishing |  |  | between
cars and trucks (% and AADT), revenue numbers and cash flow data shall
be provided separately in ten (10) year increments to the end of the term.
All | information |  | in | section | 10.4.1.6b | shall | be | provided | in | a | Microsoft
Excel spreadsheet electronically.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 34
Name: “Table 1 of 1 on page 34 of 71”
Table: 34
33
11 | EVALUATION PROCESS
| VDOT | will | review | and | evaluate | each |  | Conceptual |  | Proposal |  | based |  | on | the | Offerors’
qualifications to finance, design, construct, maintain and operate the Project over the long
term through the demonstration of significant and relevant experience and capabilities
meeting the Project objectives.
The criteria will consider, among other things, the Offerors’ relevant experience with the
development and financing of transportation infrastructure projects of similar complexity
| and | scope; | the | operations | and | maintenance |  |  | of | toll | highways; |  | and | the |  | operations,
maintenance and management of highway corridors and integrated networks.
| The | Conceptual |  | Proposal | evaluation |  | criteria |  | reflect |  | VDOT’s |  | main | objectives |  |  | and
priorities during project development and its evaluation of the Proposals in response to
the SFP.
11.1 | Evaluation Rating System
Conceptual Proposals will be evaluated by applying the rating system as set forth below.
The rating system that will be used for the assessment of the Conceptual Proposals is
| detailed in Table 11.1. |  |  |  | The rating system will have four rating levels for the evaluator.
| Within | each | of | the | rating | levels, | an | evaluator |  | may | provide |  | specific |  | information
differentiating the basis of their evaluation and whether one Offeror is more qualified, but
| is rated within the same rating level. |  |  |  |  | For example, if four Offerors each are rated a Green
proposal response, this would not necessarily signify that all four Offerors are equally
| ranked. | Based on the information provided in the Conceptual Proposal, an evaluator has
the discretion to rank each Offeror, notwithstanding the fact that he/she may have rated
all Offerors as a Green for a particular category.
| Based | on | its | evaluation, |  | VDOT | will | then |  | provide |  | recommendations |  |  |  | to | the
Commonwealth Transportation Commissioner, the IRP and the CTB, as to whether none,
one, or more Conceptual Proposals should be advanced to Phase Four.
| Evaluation Criteria and a rating system have not yet been determined for the RFDP. | [15 empty] | If an
Offeror is selected to advance to Phase Four the evaluation and selection criteria will be
provided in the RFDP.
TABLE 11.1 – VDOT EVALUATION RATING SYSTEM
|  | Adjectival Rating | [5 empty] | Adjectival Rating Description
| Blue | [5 empty] | Conceptual |  |  | Proposal |  | indicates |  |  | significant
[7 empty] | strengths |  | and/or |  | a | number | of | minor |  | strengths
[7 empty] | and | no | weaknesses. |  |  | Submitter |  |  | provides |  | a
[7 empty] | consistently |  |  | outstanding |  |  | level |  | of | quality,
[7 empty] | qualifications, |  |  |  | performance |  |  | or |  | capability
[7 empty] | requirements |  |  | in | a | way | beneficial |  |  | to | the
Commonwealth.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 35
Name: “Table 1 of 1 on page 35 of 71”
Table: 35
34
Green | Conceptual |  | Proposal | meets |  | relevant
| qualifications, |  | performance |  | or | capability
requirements necessary for acceptable contract
performance.
Yellow | Conceptual | Proposal | does | not | clearly | meet
| some | relevant | qualifications, |  | performance | or
| capability | requirements |  |  | necessary | for
| acceptable | contract | performance, |  | but | proposal
inadequacies may be correctable.
Red | Conceptual | Proposal | fails | to | express | relevant
| qualifications, |  | performance |  | or | capability
requirements.
Solicitation for Conceptual Proposals • U.S. Route 460 Corridor Improvements Project • May 2010

## Page 36
Name: “Table 1 of 1 on page 36 of 71”
Table: 36
APPENDIX A
DEFINITIONS
Concessionaire means the individual, company, firm, partnership, corporation,
association or joint venture contemplated to contract with VDOT in conjunction with this
SFP and pursuant to the execution of an Interim and/or Comprehensive Agreement.
| Conceptual |  | Proposals |  | means |  |  | Offeror’s |  | submission |  |  |  |  | of | Statement |  |  | of
Qualifications and Conceptual Financial Plan in response to VDOT’s request for such
proposals.
Consultant means any Person at the time retained by or on behalf of VDOT or
the | Concessionaire, |  | which | Person |  | is | experienced |  |  | and | has |  | a | national |  | and |  | favorable
reputation in the matters for which such Person is so employed.
Contractor means any Person with whom the Concessionaire has entered into
any contract to perform any part of the Work or provide any materials, equipment or
supplies for the Project and/or the Utility Relocations included in the Work, on behalf of
the | Concessionaire, |  | and | any | other | Person |  | with |  | whom | any |  |  | Contractor |  |  | has |  | further
subcontracted any part of the Work, at all tiers.
| CTB | means | the | Commonwealth |  |  | Transportation |  |  |  | Board, |  |  | a | board |  | of | the | State
affiliated with VDOT.
| Detailed |  | Proposals | means |  | short | listed |  | Offerors’ |  | submission |  |  |  |  | of | proposals |  | in
response to VDOT’s request for such proposals under Phase Four of the evaluation and
procurement process.
Electronic Toll Collection means the collection of tolls based on the automatic
identification and classification of vehicles using electronic systems.
| Experience |  | Modification |  | Rating |  |  | (EMR) |  | means |  | a | mandatory |  |  |  | process |  | that
modifies the published rates for rating classifications by taking into account the actual
reported | losses | and | payrolls | of | an | individual |  |  | business. |  | It | is | a | financial |  |  | incentive |  | to
employers to minimize the financial cost of workplace injuries. The rate is based on two
major | issues: | the | number | of | claims |  | and | the | cost | of | each |  | claim |  | reported |  |  | over | an
experience period. The experience period is usually three full policy years, ending one
year prior to the effective date of the modification. To illustrate, a modification effective
January | 1, | 2008 | uses | payrolls | and | losses |  | for | the | policies |  | effective |  |  | January |  |  | 1, | 2004;
January 1, 2005; and January 1, 2006.
| Federal | Highway |  | Administration |  |  |  | (FHWA) |  | means |  | the |  | branch |  | of | the |  | United
States | Department |  | of | Transportation |  |  | which | funds |  | and | oversees |  |  |  | new | highways |  |  | and
highway improvement projects.

## Page 37
Name: “Table 1 of 1 on page 37 of 71”
Table: 37
Financial Closing Date (Financial Close) means the closing date of the issuance
of tax-exempt bonds or the issuance of taxable debt and/or equity, the proceeds of which,
in either case, are sufficient together with other available funds to finance the completion
of the design and construction of the Project or the related Phase, as applicable
Financial Plan (Conceptual Financial Plan) means Offeror’s conceptual plan
which describe planned use and source of funds to cover anticipated Project costs and
expenditures |  | related | to | the | finance, | design, | construction, |  | operation, |  | maintenance |  | and
handback | phases | of | work, |  | including | annual | updates | for | which | such | plan | and | annual
updates meet the requirements of Section 1904(a) of SAFETEA-LU and FHWA Major
Projects Guidance, March 2007.
| Generally | Accepted |  |  | Accounting | Principles |  | (GAAP) | means |  | a | collection | of
methods used to process, prepare, and present public accounting information representing
such accepted accounting practice as, in the opinion of the Accountant, conforms at the
time to generally accepted accounting principles in the United States of America
| Governmental |  |  | Authority |  | means | any | court, | federal, | state, |  | department,
commission, board, bureau, agency or other regulatory, administrative, or governmental
entity or authority having jurisdictional authority in accordance with State or Federal
Laws.
Implementation Guidelines (Guidelines) means such guidelines presenting the
goals and objectives as governed by the Public Private Transportation Act (PPTA) of
1995 (§ 56-556 et seq. of the Code), as amended.
| International |  | Financial |  | Reporting |  | Standards | (IFRS) |  | means | standards |  | and
interpretations adopted by the International Accounting Standards Board (IASB) which
state how particular types of transactions and other events should be reported in financial
statements. Major financial centers in various countries of each continent apply these
standards | to | promote | uniformity |  | in | financial | reporting | and | practices |  | and | to | generate
financial statements that are understandable in all of the countries they operate.
Key Personnel is defined in Section 10.4.1.5 of the SFP.
Law(s) mean any current or future order, writ, injunction, decree, judgment, law,
ordinance, decision, opinion, ruling, statute, code, rule or regulation of any Governmental
Authority.
Letter of Submittal is defined in Section 10.2 of the SFP.
NEPA means the National Environmental Policy Act, 42 U.S.C. § 4321 et seq., as
amended and as it may be amended from time to time.
Open Road Tolling (ORT) means an electronic toll collection system without
toll plazas, where drivers will be charged the toll without having to stop, slow down, or
stay in a given lane.
- 2 -

## Page 38
Name: “Table 1 of 1 on page 38 of 71”
Table: 38
Project means collectively, the provision for a new four-lane divided highway
between Interstate-295 in Prince George County and U.S. Route 58 Bypass in the City of
Suffolk, Virginia and as further defined in Article 3 of the SFP.
Regulatory Approvals means all local, regional, state and federal agreements,
studies, findings, permits, approvals, authorizations, certifications, consents, decisions,
exemptions, |  |  | filings, |  | leases, |  | licenses, | registrations, |  |  | rulings |  | and | other | governmental
authorizations |  |  | required |  | to | be | obtained | or | completed |  | under |  | applicable |  | Laws | prior | to
undertaking |  |  | any | particular |  | activity |  | contemplated |  |  | by | this | Agreement. |  | The |  | term
“Regulatory Approvals” includes any supplements to the EIS.
| Representative |  |  |  | means, |  | with | respect |  | to | any | Person, |  | any | director, | officer,
employee, official, lender (or any agent or trustee acting on its behalf), partner, member,
owner, | agent, |  | lawyer, |  | accountant, |  | auditor, |  | professional |  |  | advisor, |  | Consultant, |  | engineer,
contractor, |  | other |  | Person |  | for | whom | such | Person |  | is | at | law | responsible |  | or | other
representative |  |  | of | such | Person |  | and | any | professional |  | advisor, |  | Consultant |  | or | engineer
designated by such Person as its “Representative.”
Responsible Public Entity has the meaning assigned to such term in Section 56-
557 | of | the | PPTA | and, |  | for | purposes |  | hereof, |  | means | the | Virginia |  | Department |  | of
Transportation.
| SFP |  | Documents |  | mean |  | the | documents, |  | whether |  | attached |  | or | incorporated |  | by
reference, furnished by VDOT as part of the Solicitation for Proposals for the Project.
| Solicitation |  |  | for | Proposals |  | (SFP) |  | means |  | VDOT’s |  | request | for | such | proposals
under Phase One of the procurement process for the Project.
State means the Commonwealth of Virginia.
| Statement |  |  | of | Qualifications |  |  | means | a | statement |  | of | the | Offeror’s | experience,
financial capacity, Key Personnel, a current profile of the Offeror teams’ activities, and
other pertinent information relevant to the Project.
Toll Agreement means the agreement signed between the FHWA and a State or
local government or other entity to grant the authority to collect tolls.
VDOT means Virginia Department of Transportation.
Violation Enforcement System means the collective equipment and procedures
that capture a violation transaction, image and the citation process.
Virginia Code means the Code of Virginia of 1950, as amended.
Work means all development and operation [as defined in the PPTA] required to
be furnished and provided by or on behalf of the Concessionaire as contemplated under
an executed comprehensive agreement, including all labor, materials, equipment, services
- 3 -

## Page 39
Name: “Table 1 of 1 on page 39 of 71”
Table: 39
and documentation required to develop and operate the Project, except for those efforts
which the comprehensive agreement expressly specifies will be performed by VDOT.
- 4 -

## Page 40
Name: “Table 1 of 1 on page 40 of 71”
Table: 40
APPENDIX B
PPTA
ORDER FORM
ROUTE 460 CORRIDOR IMPROVEMENT PROJECT
SOLICIATION FOR PROPOSALS (SFP)
INFORMATION PACKAGE
FIRM NAME ______________________________________________________________________________________________
COMPLETE MAILING
ADDRESS________________________________________________________________________________________________
_________________________________________________________________________________________________________
(PLEASE GIVE BOTH STREET ADDRESS AND POSTAL DELIVERY ADDRESS)
FIRM TELEPHONE NUMBER________________________________ |  | FIRM FAX NUMBER___________________________
E-MAIL ADDRESS ________________________________________________________
SIGNED:____________________________________________________________________________
FOR QUESTIONS REGARDING THE SFP INFORMATION PACKAGE CONTACT:
MARGIE RAY
VIRGINIA DEPARTMENT OF TRANSPORTATION
1401 EAST BROAD STREET
RICHMOND, VIRGINIA 23219
(804) 786-9537
TO ORDER THE SFP INFORMATION PACKAGE BY TELEPHONE/MAIL/FAX CONTACT:
THE SCHEDULING AND CONTRACT DIVISION PLAN ROOM
VIRGINIA DEPARTMENT OF TRANSPORTATION
1401 EAST BROAD STREET
RICHMOND, VIRGINIA 23219
(804) 786-1898,786-5161 OR 371-9868
FAX TELEPHONE NO. (804) 786-2788 (Ordering by fax using a Master or Visa credit card is the preferred
method)
MASTERCHARGE/VISA NO.___________________________________________________
EXPIRATION DATE:____________________________
THE SFP INFORMATION PACKAGE WILL NOT BE ISSUED PRIOR TO RECEIPT OF PAYMENT
Dear Sir/Madam:
Please send the SFP Information Package designated below. |  | Enclosed is check No.____________in the amount of $__________
made payable to the Treasurer of Virginia.
TO VIEW THE SFP GO TO THE WEBSITE ADDRESS LISTED BELOW
http://route460ppta.org/
SFP NO. | PROJECT | PACKAGES | TOTAL
|  | REQUESTED | ($50.00 per package, price includes
5%Virginia Sales Tax)
|  | # | $
Route 460 Corridor Improvement Project
FOR DEPARTMENTAL USE ONLY
SFP PACKAGE MAILED____________________________ |  | MAILED BY_________________________
TO BE MAILED___________________________________ |  | CHECKED BY_________________________

## Page 41
Name: “Table 1 of 1 on page 41 of 71”
Table: 41
APPENDIX C
Certification Regarding Debarment
Primary Covered Transactions
Project: | Route 460 Corridor Improvements Project
1) | The prospective primary participant certifies to the best of its knowledge and belief, that it and
its principals:
| a) | Are not presently debarred, suspended, proposed for debarment, declared ineligible, or
voluntarily excluded from covered transactions by any Federal department or agency.
| b) | Have not within a three-year period preceding this proposal been convicted of or had a
civil judgment rendered against them for commission of fraud or a criminal offense in connection
with obtaining, attempting to obtain, or performing a public (Federal, State or local) transaction or
contract under a public transaction; and have not been convicted of any violations of Federal or State
antitrust statutes or commission of embezzlement, theft, forgery, bribery, falsification, or destruction
of records, making false statements, or receiving stolen property;
| c) | Are | not | presently | indicted | for | or | otherwise | criminally | or | civilly | charged | by | a
governmental entity (Federal, State or local) with commission of any of the offenses enumerated in
paragraph 1) b) of this certification; and
| d) | Have not within a three-year period preceding this application/proposal had one or
more public transactions (Federal, State or local) terminated for cause or default.
2) | Where the prospective primary participant is unable to certify to any of the statements in this
certification, such prospective participant shall attach an explanation to this proposal.
The undersigned makes the foregoing statements to be filed with the proposal submitted on behalf of
the Offeror for contracts to be let by the Commonwealth Transportation Board.
______________________________________ | [7 empty] | _________________________
Signature |  |  |  | Date |  |  |  | Title
___________________________________________________________________
Name of Firm
_________________________________________________________________________________________________
Commonwealth of Virginia
Virginia Department of Transportation
Page 1 of 2

## Page 42
Name: “Table 1 of 1 on page 42 of 71”
Table: 42
APPENDIX C
Certification Regarding Debarment
Lower Tier Covered Transactions
Project: Route 460 Corridor Improvements Project
1) | The prospective lower tier participant certifies, by submission of this proposal, that neither it
nor its principals is presently debarred, suspended, proposed for debarment, declared ineligible, or
voluntarily excluded from participation in this transaction by any Federal department or agency.
2) | Where the prospective lower tier participant is unable to certify to any of the statements in this
certification, such prospective participant shall attach an explanation to this proposal.
The undersigned makes the foregoing statements to be filed with the proposal submitted on behalf of
the Offeror for contracts to be let by the Commonwealth Transportation Board.
____________________________________ |  | __________________
Signature | Date | Title
____________________________________________________________
Name of Firm
_________________________________________________________________________________________________
Commonwealth of Virginia
Virginia Department of Transportation
Page 2 of 2

## Page 43
Name: “Table 1 of 1 on page 43 of 71”
Table: 43
APPENDIX D
Work History Form 1 (Financial)
List experience with projects similar to the proposed Project, which best illustrates current qualifications relevant to this Project.
a. Team Member or | b. | Name of the Project, | c. Project Owner’s Name & | d. Project | e. | Third Party | f. Year of Financial | g. Financing/Security/Insurance
Firm’s Name |  | Location, Description | Address, Project | Cost |  | Reference Name, | Close or Year | Description/Type | Role/Tolling | Value/Amount/Equity
|  | and Tolling Description | Manager’s Name, Phone |  |  | Organization, | Posted (pertaining |  | Responsibility | Invested
|  | (if applicable) | Number |  |  | Phone Number | to Securities)
(1)
(2)
(3)
(4)
(5)
(6)
(7)
(8)
(9)
(10)

## Page 44
Name: “Table 1 of 1 on page 44 of 71”
Table: 44
APPENDIX D
Work History Form 2
List experience with projects similar to the proposed Project, which best illustrates current qualifications relevant to this Project.
a. Project Name & | b. Project Owner’s Name & | c. Nature of Firm’s Responsibilities | d. Contract | e. Contract |  |  | f. Estimated Value (in Thousands)
Location | Address, Project |  | Completion Date | Completion | Original | Final or | Dollar Value of Work for | Liquidated
| Manager’s Name, Phone |  | (Original) | Date (Actual | Contract | Estimated | Which Firm Was/Is | Damages/Defaults
| & Fax Number |  |  | or Estimated) | Value | Contract | Responsible
Value
(1)
(2)
(3)
(4)
(5)
(6)
(7)
(8)
(9)
(10)

## Page 45
Name: “Table 1 of 1 on page 45 of 71”
Table: 45
APPENDIX D
Work History Form 3 – Experience of the Lead Operations and Maintenance Firm* in the Operation and Maintenance of Roadway Facilities
a. Project Name & Location | b. Project Owner’s | c. Nature of Firm’s | d. Lane Miles | e. Duration of Maintenance | f. Estimated Value in Thousands |  | g. Firm’s Number of Employees per
| Name & | Responsibilities | Maintained per | Period (state if ongoing) |  |  | project
| Address, Project |  | project |  | Original Contract Value | Dollar Value of Work for
| Manager’s |  |  |  |  | Which Firm Was/Is
| Name, Phone & |  |  |  |  | Responsible
Fax Number
(1)
(2)
(3)
(4)
(5)
(6)
(7)
(8)
(9)
(10)
*List the experience of Lead Operations and Maintenance Firm only, whether or not future shareholders of the concessionaire.

## Page 46
Name: “Table 1 of 1 on page 46 of 71”
Table: 46
APPENDIX E
RESUME FORM
Brief Resume of Key Personnel/Offeror’s team members anticipated for this project.
a. | NAME & TITLE:
b. | PROJECT ROLE:
c. | NAME OF FIRM WITH WHICH ASSOCIATED:
d. | YEARS EXPERIENCE: |  | With this firm:
With other firms:
In role as stated in letter “b”:
e. | EDUCATION: | Educational Institution:
Degree(s):
Year:
Specialization:
f. | ACTIVE REGISTRATION: Year First Registered:
Discipline:
Location of Registration:
g. | CERTIFICATIONS:
h. | EXPERIENCE | AND | QUALIFICATIONS | RELEVANT | TO | THE | PROPOSED
PROJECT:

## Page 47
Name: “Table 1 of 1 on page 47 of 71”
Table: 47
APPENDIX F
Term Sheet for the Development of a Comprehensive Agreement
Page 1 of 23

## Page 48
Name: “Table 1 of 1 on page 48 of 71”
Table: 48
1 | Introduction
This term sheet identifies and summarizes several key terms and conditions which
will form the basis of, and shall be incorporated into, the Comprehensive Agreement
negotiated by the Department and the Concessionaire. The terms are based on the
premise that the Project will be financed solely with private funds. The terms would be
different for a project relying in whole or in part on public funds.
2 | Definitions
[Reserved]
3 | Basic Roles and Responsibilities
| 3.01 | Basic Agreement
|  | (a) | Concessionaire shall provide appropriate oversight, management,
and reporting of all phases of the Project and its subcontractors such that the
Project is delivered, operated, and maintained in accordance with, and fit for the
purpose intended by, the Comprehensive Agreement.
|  | (b) | Concessionaire shall perform, or cause to be performed, the work
required by the Comprehensive Agreement in accordance the Standard of Care (as
defined in Section 3.02 below).
|  | (c) | Concessionaire may retain subcontractors to perform certain of
Concessionaire’s responsibilities under the Comprehensive Agreement, subject to
Section 24.02.
|  | (d) | VDOT will perform only minimal construction oversight and will
rely on the Concessionaire to directly manage, oversee, and resolve disputes
involving its subcontractors without the involvement of the Department. VDOT
will rely on the Concessionaire’s quality assurance/quality control work and on
the Concessionaire’s certifications that the work complies with contract
requirements. The Concessionaire will be responsible for VDOT’s construction
oversight costs, estimated at two (2) percent of the design and construction costs.
| 3.02 | Standard of Care
|  | (a) | As used herein, “Standard of Care” means performance of the
work in compliance with all of the following standards:
|  |  | (i) | specific standards, methods, and requirements set forth in
the Comprehensive Agreement, including the Technical Requirements;
Page 2 of 23

## Page 49
Name: “Table 1 of 1 on page 49 of 71”
Table: 49
|  |  | (ii) | all applicable laws, including laws applicable to a
transportation project that has received or receives federal-aid funds;
|  |  | (iii) | all regulatory approvals;
|  |  | (iv) | the application of professional engineering judgment taking
into consideration safety, operational requirements, level of service, and
life cycle costs;
|  |  | (v) | prudent industry practices, methods, techniques, and
standards and using the degree of care that would be expected to be
exercised by a prudent, skilled, and experienced contractor engaged in the
same kinds of undertakings as the Project under the same or similar
circumstances or conditions as those applying to the design, development,
construction, and operation of the Project; and
|  |  | (vi) | the requirements of insurance policies required to be
maintained pursuant to the Comprehensive Agreement.
Neither compliance with a minimum requirement set forth in any specific
standard set forth above, nor achievement of a lowest cost solution, shall be
deemed to either excuse compliance with any more stringent standard set forth
above or comply with the general standards set forth in clauses (iv) and (v).
|  | (b) | Architectural, engineering, and design services shall be procured
from licensed, independent professionals retained directly or indirectly by
Concessionaire or furnished by licensed employees of Concessionaire to the
extent required by applicable law.
| 3.03 | Nature of Parties’ Interests under the Comprehensive Agreement
The Comprehensive Agreement shall not grant to Concessionaire any fee title,
leasehold estate, easement, or other real property interest of any kind in or to the
| Project or the Project right of way. |  |  | Concessionaire’s interests under the
Comprehensive Agreement shall be limited to the Permit described in Section
4.01.
4 | Grant of Permit and Term
| 4.01 | Grant of Permit
Subject to the terms and conditions of the Comprehensive Agreement,
Concessionaire shall have the exclusive right, and the Concessionaire accepts the
obligation: (i) to finance, develop, design, and construct the Project and (ii) from
and after the commencement of public operations of the Project (“Service
Commencement”) and until the end of the Term (as defined below), to manage,
Page 3 of 23

## Page 50
Name: “Table 1 of 1 on page 50 of 71”
Table: 50
operate, maintain, and improve the Project and to establish, impose, charge,
collect, use, and enforce payment of tolls and related charges (the “Permit”).
| 4.02 | Term of the Comprehensive Agreement
|  | (a) | The Comprehensive Agreement shall take effect on the Agreement
Date and shall remain in effect until the date that is [__ years] from the
Agreement Date, unless earlier terminated in accordance with the terms of the
| Comprehensive Agreement. |  | The “Agreement Date” shall mean the date upon
which the Comprehensive Agreement is executed by the Department and the
Concessionaire.
|  | (b) | The Term may be extended from time to time in accordance with
Section 13.01.
5 | Tolling | Per the terms of the Comprehensive Agreement
| 5.01 | General Requirements
| 5.02 | Toll Rates
| 5.03 | User Confidentiality
Concessionaire shall comply with all applicable law related to confidentiality and
privacy of users of the Project.
| 5.04 | Emergency Suspension of Tolls
6 | Payments to the Department |  | Per the terms of the Comprehensive Agreement
7 | Project Finance
| 7.01 | Concessionaire Financing
|  | (a) | Concessionaire shall be solely responsible for developing a
financial plan and seeking approval from the Department for all aspects of the
financial plan prior to the Agreement Date.
|  | (b) | Concessionaire shall be solely responsible for obtaining any
financing for the development, design, construction, operation, and maintenance
of the Project and the Department shall have no responsibility to meet
Concessionaire’s debt service or payment obligations on any financing obtained
by Concessionaire.
| 7.02 | Financing Assignments
|  | (a) | Per the terms of the Comprehensive Agreement.
Page 4 of 23

## Page 51
Name: “Table 1 of 1 on page 51 of 71”
Table: 51
| 7.03 | Lender’s Rights and Obligations Relating to Concessionaire Default
|  | (a) | Per the terms of the Comprehensive Agreement.
| 7.04 | Restrictions on Assignment and Transfers
|  | (a) | Per the terms of the Comprehensive Agreement.
8 | Design and Construction
| 8.01 | General Obligations of Concessionaire
|  | (a) | Concessionaire shall perform, or cause to be performed, all design
and construction services and provide all materials, equipment, tools, and labor
necessary to complete the construction of the Project as specified in the scope of
work, together with any Project Enhancements directed or approved by the
| Department (the “Design-Build Services”). |  |  | Design-Build Services shall be
provided at Concessionaire’s sole cost and expense, except as otherwise specified
by the Comprehensive Agreement.
|  | (b) | All development services shall comply with the Standard of Care;
|  | (c) | Concessionaire shall achieve substantial completion not later than
per the terms of the Comprehensive Agreement.
|  | (d) | If the Concessionaire has not achieved Substantial Completion by
the Guaranteed Substantial Completion Date, the Concessionaire shall continue to
perform the Design-Build Services so as to achieve substantial completion within
[24 months] of the Guaranteed Substantial Completion Date (“Outside Substantial
Completion Date”).
| 8.02 | Conditions Precedent to Work
Per the terms of the Comprehensive Agreement
| 8.03 | Quality Management
|  | (a) | Concessionaire shall perform all quality assurance and quality
control activities necessary for the work in accordance with the Technical
Requirements (and specifically the Department’s guidance document entitled,
Minimum Quality Control & Quality Assurance Requirements for Design-Build
& Public-Private Transportation Act Projects).
Page 5 of 23

## Page 52
Name: “Table 1 of 1 on page 52 of 71”
Table: 52
| (b) | Concessionaire shall require that all of its subcontractors comply
with this Section 8.03.
| (c) | Concessionaire shall certify that all submittals have been
completed in compliance with the requirements of the Comprehensive
Agreement.
8.04 | Design-Build Contract and Amendments
| (a) | Per the terms of the Comprehensive Agreement.
8.05 | Project Design and Construction Documentation
| (a) | Per the terms of the Comprehensive Agreement.
8.06 | Project Schedule
An initial baseline schedule shall be attached to the Comprehensive Agreement
and serve as the basis for monitoring Concessionaire’s performance of the work
until such time as a baseline schedule has been submitted to and approved by the
Department in accordance with the Technical Requirements.
8.07 | Regulatory Approval
| (a) | Except as provided in Section 8.07(b) below, Concessionaire, at its
sole cost and expense, shall obtain and maintain in full force and effect and
comply with all regulatory approvals necessary for the work. |  |  | Responsibility for
obtaining regulatory approvals necessitated by a Department Change or a Project
Enhancement shall be as specified in the accompanying change order.
| (b) | The Department has completed an environmental review in
accordance with the NEPA, on behalf of the FHWA. The FHWA has issued a
Record of Decision. |  | Concessionaire shall comply with the requirements of the
NEPA documents.
8.08 | Acquisition of Right of Way and Utility Relocations
| (a) | Concessionaire, at its sole cost and expense, shall acquire all
Project right of way and shall perform or cause to be performed all activities and
services necessary for the acquisition of all Project right of way and utility
relocations necessary for construction of the Project.
| (b) | All right of way shall be acquired in the name of the state.
Page 6 of 23

## Page 53
Name: “Table 1 of 1 on page 53 of 71”
Table: 53
| (c) | Concessionaire shall use its best efforts to settle claims with
landowners amicably. |  |  | If, despite Concessionaire’s best efforts, it is unable to
reach agreement with landowners within 90 days, the Department will undertake
any necessary condemnation proceedings. |  |  | Concessionaire shall reimburse the
Department for all costs incurred by the Department in pursing condemnation.
| (d) | The Department will reasonably assist Concessionaire in obtaining
the benefit of all rights the Department has under any current utility easement,
permit, or other right in real property relating to utility relocations.
8.09 | Latent Defects in Existing Assets
[Not applicable]
8.10 | Transportation Management Plan
| (a) | Per the terms of the Comprehensive Agreement.
8.11 | Revisions to the Technical Requirements
Prior to Substantial Completion, the Department may revise the Technical
Requirements pursuant to a Department Change. |  |  |  | Following Substantial
Completion, the Department may, with 30 days’ prior notice to Concessionaire,
revise the Technical Requirements to be consistent with the evolution of
regulations, materials, and best practices on similar limited access facilities. |  |  |  |  | Any
such revision will not be a Compensation Event.
8.12 | Deviations from Technical Requirements
| (a) | Per the terms of the Comprehensive Agreement.
8.13 | Substantial Completion, Final Acceptance, and Damages for Late
Completion
| (a) | Per the terms of the Comprehensive Agreement.
8.14 | Warranties; Defective Design and Construction
| (a) | Concessionaire warrants to the Department that:
|  | (i) | all construction work, including all materials and
equipment furnished as part of the construction work, is new, of good
quality, free of defects, and will be fit for its intended purpose; and
|  | (ii) | the Design-Build Services conform to the Standard of Care.
Page 7 of 23

## Page 54
Name: “Table 1 of 1 on page 54 of 71”
Table: 54
|  | (b) | In the event of the occurrence of a defect or deficiency in the work,
the Concessionaire shall promptly rectify such defect or deficiency in the
work at Concessionaire’s sole cost and expense throughout the course of
the operating period of the Comprehensive Agreement.
| 8.15 | Performance Security Per the terms of the Comprehensive Agreement
| 8.16 | Project Recovery Schedule
|  | (a) | Per the terms of the Comprehensive Agreement
9 | Operations and Maintenance
| 9.01 | General Responsibilities
|  | (a) | Concessionaire shall perform, or cause to be performed, all
operation and maintenance [O&M] services for the Project at Concessionaire’s
sole cost and expense.
|  | (b) | O&M Services shall comply with the Standard of Care.
| 9.02 | Service Commencement
Concessionaire shall not commence the O&M Services unless and until all
conditions precedent to service commencement as defined in the Comprehensive
| Agreement have been satisfied or waived by the Department. |  |  | Such conditions
precedent shall include the following:
|  | (a) | substantial completion of the construction work;
|  | (b) | issuance of all regulatory approvals necessary to commence
operations; and
|  | (c) | procurement of all required insurance per the terms of the
Comprehensive Agreement.
| 9.03 | O&M Contractor
|  | (a) | Per the terms of the Comprehensive Agreement.
| 9.04 | Annual Budget
|  | (a) | Per the terms of the Comprehensive Agreement
Page 8 of 23

## Page 55
Name: “Table 1 of 1 on page 55 of 71”
Table: 55
| 9.05 | Maintenance
|  | (a) | Concessionaire shall perform all routine maintenance and the
repair, renewal, reconstruction, and replacement of any portion or component of
the Project (“Major Maintenance”) in accordance with the Technical
Requirements.
|  | (b) | Per the terms of the Comprehensive Agreement.
| 9.06 | Traffic Patrol and Law Enforcement
|  | (a) | The Department shall cause the Virginia State Police to provide
police services, including traffic patrol and law enforcement services, and
emergency services to the Project at a level of service equivalent to that provided
on comparable state highways from time to time.
|  | (b) | Concessionaire shall not engage or permit the engagement of
private security services to provide traffic patrol or traffic law enforcement
services on the Project.
| 9.07 | Handback
Per the terms of the Comprehensive Agreement
10 | Project Oversight
| 10.01 | Department Oversight
Refer to Section 3.01
11 | Performance Point System
| 11.01 | Description of the Performance Point System
|  | (a) | The Department shall use a performance point system to monitor
| Concessionaire’s performance levels following service commencement. |  |  | The
Comprehensive Agreement shall identify certain Concessionaire acts, omissions,
breaches, or failures to perform its obligations that may result in the assessment
| by the Department of performance points (“Performance Shortfalls”). |  |  | The
accumulation of performance points by Concessionaire may trigger the remedies
set forth or referenced per the terms of the Comprehensive Agreement.
|  | (b) | The specific process by which performance points may be
assessed, as well as other general terms and conditions applicable to the
performance point system, will be set forth in the Comprehensive Agreement.
Page 9 of 23

## Page 56
Name: “Table 1 of 1 on page 56 of 71”
Table: 56
| 11.02 | Assessment of Performance Points
|  | (a) | Per the terms of the Comprehensive Agreement.
12 | Change Orders, Safety Compliance Orders, and Project Enhancements
| 12.01 | Change Orders
|  | (a) | The Department may require a change to Concessionaire’s scope
of work (“Department Change”) pursuant to a change order executed by both
| parties or a directive letter executed by the Department. |  |  | The costs of
implementing a Department Change shall be borne by the Department unless
otherwise agreed by the parties.
|  | (b) | If the Department desires to initiate a Department Change, the
| Department shall deliver to Concessionaire a request for change proposal. |  |  |  | The
request for change proposal will set forth the details of the proposed Department
| Change. | Within 21 days following Concessionaire’s receipt of the request for
change proposal, Concessionaire shall provide the Department with a preliminary
written response, which includes an estimate of the cost of implementing the
| proposed Department Change. |  | Within 60 days after its receipt of the preliminary
written response, the Department may request Concessionaire to prepare and
submit a definitive proposal (“Change Proposal”), which Concessionaire shall
| submit within 60 days of such request. |  | The Change Proposal shall include,
among other things: a detailed estimate of the cost of implementing the proposed
Department Change; the anticipated effect that such proposed Department Change
would have on the baseline schedule, operating revenues, and traffic volumes and
| traffic flow; and the estimated damages to Concessionaire (if any). |  |  | Within 21
days following its receipt of the Change Proposal, the Department shall provide a
preliminary written response as to whether it intends to proceed with the proposed
| Department Change. |  | Within 60 days thereafter, the Department and
Concessionaire shall negotiate a mutually-acceptable change order.
|  | (c) | The Department may deliver to Concessionaire a directive letter
directing Concessionaire to proceed to implement a Department Change at the
Department’s cost on a force account basis as provided in the Technical
Requirements.
| 12.02 | Safety Compliance Orders
|  | (a) | Per the terms of the Comprehensive Agreement.
| 12.03 | Project Enhancements
|  | (a) | Either the Department or Concessionaire may propose to undertake
any additions to, or major modifications of, the Project following service
Page 10 of 23

## Page 57
Name: “Table 1 of 1 on page 57 of 71”
Table: 57
commencement (“Project Enhancements), subject to the terms or conditions set
forth in the Comprehensive Agreement.
13 | Delay Events, Compensation Events, and Force Majeure
| 13.01 | Delay Events
|  | (a) | If a Delay Event (as in Section 13.01(b)) occurs during the Term,
the Concessionaire may be entitled to an adjustment to the Term, including an
extension of the period required for completion of the Design-Build Services or
an extension of the period for completion of the O&M Services, as applicable.
|  | (b) | Delay Events prior to service commencement that may extend the
period required for completion of the Design-Build Services include the
following:
|  |  | (i) | the implementation of a change order;
|  |  | (ii) | a Force Majeure Event (as defined in Section 13.03);
|  |  | (iii) | discovery of any of the following conditions on the Project
right of way during the Development Period:
|  |  |  | (A) | differing subsurface conditions;
|  |  |  | (B) | unforeseen threatened or endangered species;
|  |  |  | (C) | unforeseen archaeological, paleontological, or
cultural resources; or
|  |  |  | (D) | unforeseen hazardous substances; and
|  |  |  | (E) | unknown utilities.
|  |  | (iv) | a failure to obtain, or a delay in obtaining, any regulatory
approval (provided that such failure or delay could not have been
reasonably avoided or prevented by Concessionaire or its subcontractors);
|  |  | (v) | a change in federal or state law occurring after the
Agreement Date that imposes additional requirements that directly
materially adversely impact performance of the Design-Build Services and
that could not have been reasonably anticipated by a reasonable
contractor; or
Page 11 of 23

## Page 58
Name: “Table 1 of 1 on page 58 of 71”
Table: 58
|  | (vi) | an injunction or other legal proceeding enjoining or
estopping either the Department or Concessionaire from the performance
of its obligations under the Comprehensive Agreement.
| (c) | Delay Events following service commencement that may extend
the period for completion of the O&M Services include the following:
|  | (i) | a Force Majeure Event (as defined in Section 13.03);
|  | (ii) | a change in federal or state law occurring after the
Agreement Date that imposes additional requirements that directly
materially adversely impact performance of the Design and Construction
Services and that could not have been reasonably anticipated by a
reasonable contractor;
|  | (iii) | a change in state law that has the effect of discriminating
against Concessionaire or the Project, except where such change in state
law is in response to any act or omission on the part of Concessionaire that
is illegal (“Discriminatory Change in State Law”);
|  | (iv) | the implementation of any change order or Project
Enhancement;
|  | (v) | the implementation of a Safety Compliance Order;
|  | (vi) | an injunction or other legal proceeding enjoining or
estopping either the Department or Concessionaire from the performance
of its obligations under the Comprehensive Agreement:
|  | (vii) | Department Caused Delays
| (d) | If Concessionaire experiences a Delay Event, it must submit
written notice to the Department within 30 days following the date on which
Concessionaire first became aware that a Delay Event occurred. |  |  |  | If
Concessionaire fails to submit the notice within that 30 day period, it shall waive
its right to an extension of time. |  |  | The notice shall include the information
specified by the Comprehensive Agreement, which shall include a time impact
analysis demonstrating the impact of the Delay Event to the Project schedule.
13.02 | Compensation Events
| (a) | If a Compensation Event (as defined below) occurs during the
Term, the Concessionaire may be entitled to damages or the Department may be
entitled to positive net cash flows created by such an event.
| (b) | Compensation Events include:
Page 12 of 23

## Page 59
Name: “Table 1 of 1 on page 59 of 71”
Table: 59
| (i) | the implementation of a change order or Project
Enhancement;
| (ii) | Discriminatory Change in State Law;
| (iii) | [intentionally deleted]; or
| (iv) | Department Caused Delay, as set forth in more detail
below;
| (v) | discovery of any of the following conditions on the Project
right of way during the development period;
|  | (A) | differing subsurface conditions;
|  | (B) | unforeseen threatened or endangered species;
|  | (C) | unforeseen archaeological, paleontological, or
cultural resources; or
|  | (D) | unforeseen hazardous substances.
| (vi) | Department Changes.
(c) | If the Concessionaire is affected by a Compensation Event, it shall
give written notice to the Department within 30 days following the date on which
the Concessionaire first became aware (or should have been aware, using all
reasonable due diligence) that an event has occurred and that it is or will become
a Compensation Event (a “Compensation Event Notice”). |  |  |  | The Compensation
Event Notice shall set forth (i) the Compensation Event and its date of occurrence
in reasonable detail, (ii) the amount claimed as the Concessionaire Damages, and
(iii) details of the calculation thereof including a written analysis and calculation
of the estimated net cost impact, if any, and estimated net revenue impact, if any.
(d) | If, for any reason, the Concessionaire fails to deliver such written
Compensation Event Notice within the foregoing time period, the Concessionaire
shall be deemed to have irrevocably and forever waived and released any Claim
or right to Concessionaire damages or other adverse effects on gross revenues or
on costs, expenses and liabilities attributable to such Compensation Event.
(e) | If the Department determines the Concessionaire is entitled to cost
relief for Department Caused Delay or Department Changes the Concessionaire
shall be entitled to recover from the Department only the direct costs reasonably
and necessarily incurred by the Design Build Contractor as a direct result of the
Page 13 of 23

## Page 60
Name: “Table 1 of 1 on page 60 of 71”
Table: 60
Department Caused Delay or Department Changes. However, under no
circumstances will such recoverable costs include home office overhead incurred
by the Design Build Contractor’s member companies, nor net revenue impacts nor
financing costs.
| (f) | If the Department determines the Concessionaire is entitled to cost
relief for the implementation of a change order or Project Enhancement,
Discriminatory Change in State Law, differing subsurface conditions, unforeseen
threatened or endangered species, unforeseen archaeological, paleontological, or
cultural resources, or unforeseen hazardous substances the Concessionaire may
request an extension of the Term as necessary to recoup its net cost impacts
and/or net revenue impacts. The Department has no liability for compensation due
to the Compensation Events noted above.
13.03 | Force Majeure Events
| (a) | Force Majeure Event means any of the following acts of nature or
people that can neither be anticipated nor controlled: earthquakes that cause
ground accelerations in excess of the AASHTO bridge design standards for the
site of the Project, floods in excess of the base flood (as defined in the
Department’s Division I Amendment), hurricane force winds, tornados, epidemic
disease declared by US federal government, quarantine restriction of critical
personnel or materials, adverse conflict by or among armed forces, acts of terror,
maritime blockade, |  |  | nuclear or other explosion, radioactive or chemical
contamination or ionizing radiation, riot or other public disorder, industry-wide or
regional strikes or labor disputes, and governmental embargo. |  |  |  | An event is not a
Force Majeure Event if such event is otherwise specifically dealt with in the
Comprehensive Agreement or arises by reason of:
|  | (i) | the negligence or misconduct of Concessionaire or its
subcontractors;
|  | (ii) | any act or omission by Concessionaire or its subcontractors
in breach of the provisions of the Comprehensive Agreement;
|  | (iii) | any defect or deficiency in the design or construction of the
Project;
|  | (iv) | lack or insufficiency of funds or failure to make payment of
monies or provide required security on the part of Concessionaire or its
subcontractors;
|  | (v) | any strike, labor dispute or labor protest directed solely at
Concessionaire or its subcontractors or caused by or attributable to any act
(including any pricing or other practice or method of operation) or
omission of Concessionaire or its subcontractors;
Page 14 of 23

## Page 61
Name: “Table 1 of 1 on page 61 of 71”
Table: 61
|  | (vi) | damage to the Project caused by an earthquake that causes
ground accelerations in excess of the AASHTO bridge design standards for the
site of the Project, floods in excess of the base flood (as defined in the
Department’s Division I Amendment), hurricane force winds, or tornados if such
damage would not have occurred but for the Project’s failure to have been
designed or constructed in accordance with the Technical Requirements.
| (b) | It is specifically understood that other than earthquakes causing
ground acceleration in excess of the AASHTO bridge design standards for the site
of the Project, floods in excess of the base flood (as defined in the Department’s
Division I Amendment), hurricane force winds or tornadoes, the Concessionaire
shall assume the risk and other weather or conditions resulting from weather shall
not constitute a Force Majeure Event.
| (c) | If a Force Majeure Event occurs after service commencement
which has the effect of causing physical damage or destruction to the Project or a
portion thereof and results in a substantial reduction in Concessionaire’s toll
revenues for a period in excess of 180 consecutive days (a “Significant Force
Majeure Event”), Concessionaire shall provide the Department with a plan for
restoring the Project before the end of the Term. |  |  |  | If the Department determines in
its sole discretion that the Project cannot be restored, the Department may
terminate the Comprehensive Agreement pursuant to Section 20.05. |  |  |  | If
Concessionaire restores the Project, the Department and Concessionaire shall
negotiate an appropriate extension of the Term.
13.04 | Department Caused Delay
(a) Department Caused Delay means a material breach or an inexcusable
delay by the Department in performing any of its obligations during the design-
build period of the development of the Project, and which material breach or an
inexcusable delay by the Department causes the Design Build Contractor a
material increase of its construction costs or a material impact to the critical path
which delays the Guaranteed Substantial Completion Date described in the
Comprehensive Agreement.
For the purposes of this Section, an “inexcusable delay” shall mean a
delay that is attributable solely to error or omission of the Department, and an
inexcusable delay or a material breach specifically excludes delay or breach
attributable to: (a) the submission of incomplete documentation for the
Department’s review, (b) required review or approvals from other Governmental
Authorities necessary or appropriate to the Department’s review, (c) failure to
obtain appropriation and allocation of public funds, (d) consumption of available
float, (e) submittals or requests that are "deemed approved" if no response is
provided within the minimum required response period [typically 21 days], or (f)
Force Majeure Events.
Page 15 of 23

## Page 62
Name: “Table 1 of 1 on page 62 of 71”
Table: 62
(b) The Concessionaire shall submit its request for Change Order within
30 days after the occurrence of any Department Caused Delay giving rise to the
request for adjustment or relief. The request for Change Order shall include
sufficient information to advise Department of the circumstances giving rise to
the request for adjustment, the amount of adjustment requested and the basis of
such request.
(c) not used
(d) The Concessionaire’s request for Change Order due to Department
Caused Delay may include the price escalation for materials only if the event
causes the Guaranteed Substantial Completion Date to be delayed by at least one
year and such delay is not attributable to the actions or negligence of the
Concessionaire, a Concessionaire Party, or the Design-Build Contractor.
(e) The Department may extend the Guaranteed Substantial Completion
Date only if its delay results in a material impact to the critical path set forth in
the Baseline Schedule.
(f) If for any reason the Concessionaire fails to deliver the request for
Change Order within the time period specified above, the Concessionaire shall be
deemed to have irrevocably and forever waived and released any Claim or right to
cost or schedule relief attributable to any such alleged Department Caused Delay.
(g) If the Department grants to the Concessionaire cost relief, schedule
relief, or both, the Concessionaire shall pass such relief to the Design Build
Contractor pursuant to the terms of the Design-Build Contract.
14 | Hazardous Substances
| 14.01 | Concessionaire’s Responsibility
Concessionaire shall be fully responsible for the the management, handling,
treatment, remediation, removal, transport (where applicable), and disposal of all
hazardous substances, including but not limited to, hazardous substances that
were introduced to the Project or caused by Concessionaire or those whose acts
for which Concessionaire is responsible, or that are discovered on the Project
right of way, in accordance with applicable law and regulatory approvals. The
Concessionaire shall be fully responsible for the costs of the work contemplated
in this Section, except to the extent such work qualifies as a Compensation Event
pursuant to Section 13.02. Hazardous substances that were introduced to the
Project or caused by Concessionaire or those whose acts for which
Concessionaire is responsible shall not be a basis for Delay Events or
Compensation Events.
| 14.02 | Reserved
Page 16 of 23

## Page 63
Name: “Table 1 of 1 on page 63 of 71”
Table: 63
| 14.03 | Concessionaire’s Indemnity for Hazardous Substances
|  | (a) | Concessionaire shall indemnify, defend, and hold harmless each
State Indemnitee (as defined in Section 15(a) below) from and against all claims,
losses, damages, liabilities, and expenses, including attorneys’ fees and expenses,
arising out of or resulting from:
|  |  | (i) | those hazardous substances introduced to the Project right
of way by Concessionaire, its contractors, its subcontractors, or anyone for
whose acts they may be liable;
|  |  | (ii) | the spreading, migration, release, remediation, storing,
transportation, or disposal of Pre-Existing Hazardous Substances by
Concessionaire, its contractors, its subcontractors, or anyone for whose
acts they may be liable; and
|  |  | (iii) | exacerbation, due to negligence, recklessness, or willful
misconduct of Concessionaire, its contractors, its subcontractors, or
anyone for whose acts they may be liable, of the release, spreading,
migration, or toxicity of hazardous substances on or within the Project
right of way.
15 | Indemnification
| (a) | Concessionaire shall indemnify, defend, and hold harmless the
Department, the Commonwealth Transportation Commissioner, the Commonwealth
Transportation Board, the state, and their respective representatives (“State Indemnitee”)
from and against any losses actually suffered or incurred by such State Indemnitee
(except to the extent such Losses are caused by the negligence or willful misconduct of
such State Indemnitee), due to third party claims that are based upon, arise out of, relate
to, are occasioned by or are attributable to:
|  | (i) | any failure by the Concessionaire to comply with, observe or
perform any of the covenants, obligations, agreements, terms or conditions in the
Comprehensive Agreement or, any breach by the Concessionaire of its
representations or warranties set forth herein;
|  | (ii) | any actual or alleged misconduct, negligence or other culpable act,
error or omission of a Concessionaire Party in connection with the Project;
|  | (iii) | any actual or alleged patent or copyright infringement or other
actual or alleged improper appropriation or use of trade secrets, patents,
proprietary information, know-how, trade marked or service marked materials,
equipment, devices or processes, copyright rights or inventions by a
Page 17 of 23

## Page 64
Name: “Table 1 of 1 on page 64 of 71”
Table: 64
Concessionaire or any of its contractors or suppliers in connection with the
Project;
|  | (iv) | inverse condemnation, trespass, nuisance or similar taking of or
harm to real property committed or caused by a Concessionaire or any of its
contractors or suppliers in connection with the Project;
|  | (v) | any tax attributable to any transfer of the Concessionaire’s interest
or any part thereof; or
|  | (vi) | any claim for brokerage commissions, fees or other-compensation
by any person who acted on behalf of the Concessionaire, its affiliates, or their
respective representatives in connection with the Comprehensive Agreement, any
transfer of the Concessionaire’s interest, or any part thereof.
| (b) | The indemnities of the Concessionaire shall survive the expiration or
termination of the Comprehensive Agreement and any other Project agreements to which
the Concessionaire is a party and shall continue for six years following the expiration or
termination of the Comprehensive Agreement; provided, that such six-year limitation on
survival shall not apply in the event of fraud or a material misrepresentation with respect
to a particular covenant, agreement, representation or warranty, and, provided further,
that additional indemnification agreements shall be as provided in any Contract and any
other Project agreement to which the Concessionaire becomes a party. |  |  |  | Notwithstanding
the foregoing, the Concessionaire’s indemnification of any State Indemnitee shall be
limited solely to its obligations under the Comprehensive Agreement and any other
Project agreements to which the Concessionaire becomes a party.
| (c) | If a State Indemnitee is enjoined from the operation or use of the Project
as a result of any patent or copyright suit, claim or proceeding, Concessionaire at its sole
cost and expense shall take reasonable steps to procure the right to operate or use the
Project.
16 | Insurance |  | Per the terms of the Comprehensive Agreement
17 | Ownership and Access to Records
| 17.01 | Ownership of Work Product
Per the terms of the Comprehensive Agreement
| 17.02 | Access to Records
|  | (a) | Without limiting any statutory or legal rights, the Department, its
representatives, and any governmental entity allowed access under law, at all
reasonable times and upon advance notice, shall have the right to audit, inspect
Page 18 of 23

## Page 65
Name: “Table 1 of 1 on page 65 of 71”
Table: 65
and copy all records and documents produced or maintained by Concessionaire
| related to the Project. | Any records and documents furnished to the Department
shall be subject to the Virginia Freedom of Information Act.
| (b) | All records and documents shall be maintained in an organized
fashion, use accounting and control systems in accordance with Generally
Accepted Accounting Principles (“GAAP”), and comply with applicable law,
including federal funding requirements.
| (c) | The Department and the state shall have the right to carry out an
audit of information relating to (i) the design, construction, operation,
maintenance, and repair of the Project or (ii) other information required to be
maintained or delivered by Concessionaire pursuant to the Comprehensive
| Agreement. | Such audit may extend, without limitation, to calculations
undertaken and financial or business reports provided by or on behalf of
Concessionaire.
| (d) | Concessionaire shall maintain all financial and cost accounts, pay
administration, and acquisition and supply records in accordance with records
| retention requirements defined the Federal Acquisition Regulation (“FAR”). |  |  | At
the Department’s request, Concessionaire shall furnish or cause to be furnished to
the Department such information relating to the operation, maintenance, and
repair of the Project as the Department may reasonably request for any purpose
related to the Project and as shall be in the possession and control of
Concessionaire or its subcontractors or consultants.
| (e) | If a federal action is required by a federal agency, Concessionaire
shall make all its Project records available to the agency for inspection and audit
at the agency’s request.
| (f) | In addition, Concessionaire, at its sole cost and expense, shall
cause a reputable independent auditor to annually audit Concessionaire’s books
| and records relating to the Project according to GAAP. |  | Concessionaire shall
cause the independent auditor to deliver the audit report to the Department
promptly after it is completed, but in any event within 120 days of the end of each
of Concessionaire’s fiscal years.
18 | Escrowed Documents | Per the terms of the Comprehensive Agreement
19 | Default and Remedies | Per the terms of the Comprehensive Agreement
20 | Termination and Project Value | Per the terms of the Comprehensive Agreement
Page 19 of 23

## Page 66
Name: “Table 1 of 1 on page 66 of 71”
Table: 66
21 | Dispute Resolution
| 21.01 | Procedure
|  | (a) | The parties shall attempt to resolve any disputes arising out of the
Comprehensive Agreement at the Project level, through good-faith negotiations
| between designated representatives. |  | If the dispute cannot be resolved at the
Project level, the parties’ senior management representatives shall meet at the
request of either party within a time as set forth in the Comprehensive Agreement
in an attempt to resolve the dispute.
|  | (b) | If the parties’ senior management cannot resolve the dispute, then
| either party may request non-binding mediation. |  |  | Mediation generally shall be a
| condition precedent to instituting a legal action in court. |  |  | However, if the
Department determines, in its sole discretion, that a dispute involves an issue that
poses an immediate or serious threat to the public health, safety, or welfare, the
Department shall be entitled to take whatever steps it deems appropriate and to
initiate litigation of the matter in court without first submitting the dispute to the
dispute resolution procedure.
|  | (d) | All litigation between the parties arising out of or pertaining to the
Comprehensive Agreement shall be filed, heard, and decided in the Circuit Court
for the City of Richmond, Virginia, Division 1, which shall have exclusive
jurisdiction and venue.
|  | (e) | Each party shall bear its own attorneys’ fees and costs in any
dispute or litigation and no party shall seek or accept an award of attorneys’ fees
or costs.
| 21.02 | Duty to Proceed and Continue with Performance
Notwithstanding the existence of any dispute (except a dispute regarding the
cause for terminating the Comprehensive Agreement), Concessionaire shall
continue performance in accordance with the Comprehensive Agreement, or
otherwise as approved or directed by the Department, and the Department shall
perform its obligations under the Comprehensive Agreement.
22 | Reserved Rights Per the terms of the Comprehensive Agreement
23 | Representations and Warranties
The Comprehensive Agreement shall set forth representations and warranties
from both Concessionaire and the Department.
Page 20 of 23

## Page 67
Name: “Table 1 of 1 on page 67 of 71”
Table: 67
24 | Contracting Practices
| 24.01 | Obligation to Refrain from Discrimination
Concessionaire covenants and agrees that it shall not discriminate and shall
require all contractors not to discriminate against any person, or group of persons,
on account of age, sex, marital status, race, creed, color, national origin, religion,
or sensory, mental, or physical handicap in the performing the work described in
the Comprehensive Agreement; provided that the prohibition against
discrimination on the basis of sensory, mental, or physical handicap shall not
apply if the particular disability prevents the proper performance of the particular
person involved.
| 24.02 | Subcontracting
|  | (a) | Concessionaire may perform its work under the Comprehensive
Agreement by subcontracting to persons with expertise, qualifications, and
| experience to perform the subcontracted work. |  |  |  | All subcontracts shall comply
| with the terms and conditions of the Comprehensive Agreement. |  |  |  | Concessionaire
shall remain fully responsible to the Department for performance of the work and
the acts and omissions of its subcontractors.
|  | (b) | Concessionaire shall not subcontract any part of its work to:
|  |  | (i) | any person then debarred or prohibited from participating
in state or federally-funded projects, or indicted, convicted, pled guilty or
nolo contendere to a violation of law involving fraud, conspiracy,
collusion, bribery, perjury, material misrepresentation, or any other
violation that shows similar lack of moral or ethical integrity;
|  |  | (ii) | a subcontractor (with the exception of contract specialty
items, consultants, manufacturers, suppliers, or haulers) that is not pre-
qualified with the Department; or
|  |  | (iii) | an affiliate, except as provided in Section 24.03.
| 24.03 | Affiliate Contracts
Concessionaire shall not enter into or materially amend a subcontract with an
affiliate without prior notice to and consent of the Department, which consent
shall not be unreasonably withheld or delayed if the subcontract is entered into in
the ordinary course of business and Concessionaire demonstrates to the
Department that the contract or subcontract is on overall terms no less favorable
to Concessionaire than terms the Concessionaire could obtain in an arm’s length
transaction.
Page 21 of 23

## Page 68
Name: “Table 1 of 1 on page 68 of 71”
Table: 68
| 24.04 | Small, Women-Owned and Minority Business and Disadvantaged
Business Enterprise Reporting
|  | (a) | Concessionaire shall use good faith efforts to achieve the following
goals in performing the Design-Build Services: [__% DBE participation and __%
SWaM participation, such percentages relating to the value of the design-build
contract totaling an aggregate goal of 40% of the value of the design-build
contract].
|  | (b) | Concessionaire shall use good faith efforts to achieve the following
goals in performing the O&M Services: [__% DBE participation and __% SWaM
participation totaling an aggregate goal of 40% of the value of the O&M
Services].
|  | (c) | If the Department determines Concessionaire or its affiliates
(including the design-build contractor and O&M contractor), neither achieves the
goals described in Sections 24.04(a) and (b) above nor demonstrates good faith
efforts, Concessionaire and/or its affiliates may be enjoined or disqualified from
additional work or new contracts with the state, in accordance with current
policies and procedures.
25 | Miscellaneous
| 25.01 | Consequential Damages Waiver
|  | (a) | Except for damages expressly allowed under the Comprehensive
Agreement, neither party shall be liable, whether as a result of breach of contract,
breach of warranty, tort liability (including negligence or strict liability), or
otherwise, for special, indirect, or consequential damages of any nature
whatsoever.
|  | (b) | The consequential damages waiver described in Section 24.01(a)
shall not apply to the following:
|  |  | (i) | indemnification obligations relating to third-party claims;
|  |  | (ii) | recovery of any liquidated damages expressly provided for
in the Comprehensive Agreement;
|  |  | (iii) | recovery of concessionaire damages expressly provided for
in the Comprehensive Agreement;
|  |  | (iv) | recovery of termination damages expressly provided for in
the Comprehensive Agreement;
Page 22 of 23

## Page 69
Name: “Table 1 of 1 on page 69 of 71”
Table: 69
| (v) | damages arising out of fraud or intentional
misrepresentation;
| (vi) | damages covered by insurance required under the
Comprehensive Agreement.
25.02 | State Allocation of Funds
The Department’s payment of any amounts due and owing by the Department to
Concessionaire under the Comprehensive Agreement shall be subject to
appropriations by the General Assembly and allocation by the CTB.
[THE REMAINDER OF THIS PAGE INTENTIONALLY LEFT BLANK]
Page 23 of 23

## Page 70
Name: “Table 1 of 1 on page 70 of 71”
Table: 70
APPENDIX G
CONCEPTUAL FINANCIAL PLAN PRO FORMA
All values in millions of USD
NPV figures discounted to January 1, 2010
Income Statement - NPV @ 5%
Revenue
O&M costs
EBITDA
Depreciation
Financing costs
Profit before interest and tax
Net interest
State Tax (paid) / refunded
Federal Tax (paid) / refunded
Profit after tax
Dividends
Retained earnings
Cash Flow Summary - NPV @ 5%
Revenues
Construction
O&M
Lifecycle
Debt costs
Equity costs
Taxes
(Required Public Funds) / Concession Payment
Percentage of Truck Revenue
Percentage of Truck Traffic
Average Initial Truck Toll Rate
Average Initial Car Toll Rate
Maximum Annual Toll Escalation Rate
Cost of debt
Equity IRR (post tax)
Project IRR (post tax, proxy for WACC)

## Page 71
Name: “Table 1 of 1 on page 71 of 71”
Table: 71
APPENDIX G
CONCEPTUAL FINANCIAL PLAN PRO FORMA
All values in millions of USD
NPV figures discounted to January 1, 2010
Income Statement - Nominal
Revenue
O&M costs
EBITDA
Depreciation
Financing costs
Profit before interest and tax
Net interest
State Tax (paid) / refunded
Federal Tax (paid) / refunded
Profit after tax
Dividends
Retained earnings
Cash Flow Summary - Nominal
Revenues
Construction
O&M
Lifecycle
Debt costs
Equity costs
Taxes
(Required Public Funds) / Concession Payment
Percentage of Truck Revenue
Percentage of Truck Traffic
Average Initial Truck Toll Rate
Average Initial Car Toll Rate
Maximum Annual Toll Escalation Rate
Cost of debt
Equity IRR (post tax)
Project IRR (post tax, proxy for WACC)